## Sheet1
run_id | mode | tool_or_query | input_summary | tool_output | insight | error | duration_sec | timestamp
1 | tool | sra_status_pei | PEI/status for project | ## 🔴 Schedule Health: **Schedule Attention Required** **Mega PWS in 11 block of Ganjam District** · Ganjam, Odisha. *Report Date: 31 Jan 1970* 📊 **Cumulative Progress** — Planned: 100.0% ¦ Achieved: 22.8% ¦ Backlog: 77.2% ⚠️ *SPI at 0.23 — execution is 77.2% behind planned throughput* --- ### Schedule Performance Indices ¦ Index ¦ Value ¦ Signal ¦ Interpretation ¦ ¦-------¦-------¦--------¦----------------¦ ¦ 🔴 **SPI** ¦ 0.228 ¦ Behind Planned Throughput ¦ Earned progress vs planned ¦ ¦ 🔴 **PEI** ¦ 1.606 ¦ Forecast Exceeds Baseline Duration ¦ Forecast duration efficiency ¦ ¦ 🔴 **Health Score** ¦ 15.0/100 ¦ Red ¦ Composite schedule health ¦ ### EPC Domain Breakdown ¦ Domain ¦ Activities ¦ Planned % ¦ Achieved % ¦ Max Delay ¦ Domain SPI ¦ ¦--------¦-----------¦-----------¦------------¦-----------¦------------¦ ¦ 🟡 **Engineering** ¦ 290 ¦ 100.0% ¦ 88.1% ¦ 0d ¦ 0.88 ¦ ¦ 🟡 **Procurement** ¦ 112 ¦ 100.0% ¦ 27.1% ¦ 0d ¦ 0.27 ¦ ¦ 🟡 **Construction** ¦ 1704 ¦ 100.0% ¦ 8.7% ¦ 0d ¦ 0.09 ¦ ¦ ¦ **Overall** ¦ 100.0% ¦ 22.8% ¦ **463d** ¦ 0.228 ¦ ### Supporting Indicators - 🏗️ **Workfront Readiness**: 2.3% ⚠️ - 📅 **EOT Exposure**: 463d ¦ EOT Status: EOT Likely ? Forecast Exceeds Contract - 📋 **Data Freshness**: Recent ? Within Week (3d old) - 🔑 **Weakest Domain**: Construction 💬 *755 days of schedule recovery are required to meet the contractual completion date.* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  |  | 1.78 | 2026-02-27T09:45:24.897313
2 | tool | sra_activity_health | Activity health | ## 📋 Activity Health Review — Mega PWS in 11 block of Ganjam District *Domain filter: All ¦ Activity filter: All* **Summary** — Total: 2106 ¦ Complete: 277 ¦ In Progress: 291 ¦ Overdue / Not Mobilised: 0 ¦ Not Yet Due: 0 --- ### Activities Requiring Attention ✅ No activities are currently trending beyond their forecast completion. ### Workfront Constraint Watch **1828** activities have workfront readiness below 70.0%: ¦ Activity ¦ Domain ¦ Workfront % ¦ Gap Count ¦ Critical Path ¦ ¦----------¦--------¦-------------¦-----------¦---------------¦ ¦ None ¦ CON ¦ 0.0% ¦ 14 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ PCC ¦ CON ¦ 0.0% ¦ 1 ¦ No ¦ ¦ Reinforcement ¦ CON ¦ 0.0% ¦ 6 ¦ No ¦ ¦ Reinforcement ¦ CON ¦ 0.0% ¦ 8 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ RCC ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ Commissioning ¦ CON ¦ 0.0% ¦ 1 ¦ No ¦ ¦ RCC ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  |  | 2.62 | 2026-02-27T09:45:27.514204
3 | tool | sra_task_lookahead | Task lookahead 2W | ## 🗓️ 2-Week Look-Ahead — Mega PWS in 11 block of Ganjam District *Scope: All Domains ¦ Activity: All* **14868** tasks fall within the 2-week start window: — Workfront Available: **343** ¦ Workfront Constrained: **14525** ### Tasks Ready to Mobilise ✅ ¦ Task ¦ Activity ¦ Domain ¦ Forecast Start ¦ Forecast Finish ¦ Float ¦ Priority Score ¦ Critical ¦ ¦------¦----------¦--------¦---------------¦-----------------¦-------¦----------------¦----------¦ ¦ Architectural Detail of Filter House & Filter Annex Building for Scheme-2 ¦ — ¦ ENG ¦ 26 Feb ¦ 22 Jan ¦ — ¦ 40.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-18CHANDIPALLI-PR (BEGUNIAPADA) to Village (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 23 Feb ¦ 23 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-4 KANTAPADA-EX (BEGUNIAPADA) to Village (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 20 Feb ¦ 14 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-19 GHODAPADA-PR (BEGUNIAPADA) to Village (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 07 Feb ¦ 14 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-58 PAILIPADA-PR (BELAGUNTHA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 05 Feb ¦ 12 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-18 VENKATRAIPALLI-EX (ASKA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 07 Jan ¦ 17 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-10 SANTARPALLI(BARIDA)-PR (KS NAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 09 Jan ¦ 09 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-1 ARJUNAPALLI-EX (KS NAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 22 Feb ¦ 22 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-131 GOBARALUNDI-PR SORODA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 11 Jan ¦ 02 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme Diagram for Gravity Distribution main from OHT-14 TABHABANIA-PR (BEGUNIAPADA) to Village (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 19 Feb ¦ 14 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme drawing for Clear water Pumping main from CWR at WTP to OHTs & IBPS-1 - (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 16 Jan ¦ 16 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-104 DINDIPALLI-PR (BHANJNAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 23 Feb ¦ 19 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-42 MANGALAPUR -EX (BELAGUNTHA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 17 Feb ¦ 17 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-92 BEDIGOBA-PR (BHANJNAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 17 Jan ¦ 17 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-25 KUMBHARI-PR (ASKA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 11 Jan ¦ 02 Feb ¦ — ¦ 0.0 ¦ ¦ ### Workfront-Constrained Tasks — Action Required ⚠️ ¦ Task ¦ Activity ¦ Domain ¦ Forecast Start ¦ Float ¦ Block Flag ¦ ¦------¦----------¦--------¦---------------¦-------¦------------¦ ¦ Architectural Detail of Chlorine Building for Scheme-1 ¦ — ¦ ENG ¦ 26 Feb ¦ — ¦ Constrained ¦ ¦ Numeration and RC Detail of Cascade aerator, Parshall flume, Distribution chamber and Flash mixer for Scheme-1 ¦ — ¦ ENG ¦ 01 Jan ¦ — ¦ Constrained ¦ ¦ P&ID Drawing for CWR cum Pump House at IBPS-1- (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 11 Jan ¦ — ¦ Constrained ¦ ¦ Overall Single Line Diagram for IBPS 12 ¦ — ¦ ENG ¦ 14 Jan ¦ — ¦ Constrained ¦ ¦ MFC ¦ MFC ¦ PRC ¦ 16 Jan ¦ — ¦ Constrained ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 16 Jan ¦ — ¦ Constrained ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 08 Feb ¦ — ¦ Constrained ¦ ¦ Design Calculation of Intermediate Sump-1 for Scheme-1 ¦ — ¦ ENG ¦ 16 Feb ¦ — ¦ Constrained ¦ ¦ Instrument list for IBPS-5 ¦ — ¦ ENG ¦ 24 Jan ¦ — ¦ Constrained ¦ ¦ Lighting Layout for Intake ¦ — ¦ ENG ¦ 20 Jan ¦ — ¦ Constrained ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  |  | 8.29 | 2026-02-27T09:45:35.801991
4 | tool | sra_critical_path | Critical path | ## 🔴 Critical Path Analysis — Mega PWS in 11 block of Ganjam District **CP Task Count**: 0 ¦ **Total Tasks**: 14868 --- ### Float Distribution Summary ¦ Float Band ¦ Task Count ¦ % of Programme ¦ ¦-----------¦-----------¦----------------¦ ¦ 🔴 Negative Float ¦ 0 ¦ 0.0% ¦ ¦ 🔴 Zero Float (Critical) ¦ 0 ¦ 0.0% ¦ ¦ 🟡 Near-Critical (≤5d) ¦ 0 ¦ 0.0% ¦ ¦ 🟢 Healthy Float ¦ 0 ¦ 0.0% ¦ ¦ **Project Min Float** ¦ — ¦ **0d** ¦ ¦ **Average Float** ¦ — ¦ **0d** ¦ ### Controlling Critical Path Tasks (Top 15) No critical path tasks identified under current float parameters. --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  |  | 7.93 | 2026-02-27T09:45:43.729918
5 | tool | sra_float_analysis | Float analysis | ## ⏳ Float Analysis & Near-Critical Watch — Mega PWS in 11 block of Ganjam District **Programme Float Health**: — ¦ **At-Risk Float**: 0.0% ¦ **Min Float**: 0d --- ### Near-Critical Activity Watch (Float ≤ 5 days) ✅ No activities are within the 5-day near-critical threshold. ### Float Erosion Watch ✅ No float erosion flags are currently active across the selected scope. ⚠️ **54 activities have breached the Critical Activity Density (CAD) threshold** — these require schedule management escalation. --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  |  | 1.23 | 2026-02-27T09:45:44.959727
6 | tool | sra_productivity_rate | Productivity rate | ## ⚡ Productivity & Rate Analysis — Mega PWS in 11 block of Ganjam District *Scope: All Domains ¦ Activity: All* **Executable Progress (Overall)**: 0.2% ¦ **E**: 0.0% **P**: 3.5% **C**: 0.1% --- ### Execution Rate Gap — Activities Below Required Rate *A rate shortfall is a leading indicator of schedule slippage — even activities marked In Progress can drive future delays if the production rate is below what the plan demands.* **1714** activities are tracking below the required progress rate: ¦ Activity ¦ Domain ¦ Planned % ¦ Achieved % ¦ Variance ¦ Required Rate/Day ¦ Earned Qty ¦ Planned Qty ¦ ¦----------¦--------¦-----------¦------------¦----------¦-------------------¦-----------¦-------------¦ ¦ None ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.61728 ¦ 0.0 ¦ 74.9 ¦ ¦ PCC ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ -3.22581 ¦ 0.0 ¦ 352.6 ¦ ¦ Reinforcement ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 7.69231 ¦ 0.0 ¦ 2935.0 ¦ ¦ Reinforcement ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 3.125 ¦ 0.0 ¦ 1800.0 ¦ ¦ Shuttering ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.44843 ¦ 0.0 ¦ 16029.2 ¦ ¦ RCC ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.45662 ¦ 0.0 ¦ 1320.0 ¦ ¦ Shuttering ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ -3.84615 ¦ 0.0 ¦ 2033.9 ¦ ¦ Commissioning ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.5291 ¦ 0.0 ¦ 82.0 ¦ ¦ RCC ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 1.0101 ¦ 0.0 ¦ 151.7 ¦ ¦ Reinforcement ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 5.26316 ¦ 0.0 ¦ 151.1 ¦ ¦ Plastering ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.53476 ¦ 0.0 ¦ 22479.5 ¦ ¦ Plastering ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.4065 ¦ 0.0 ¦ 25476.7 ¦ ¦ Reinforcement ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ -4.34783 ¦ 0.0 ¦ 72.1 ¦ ¦ PCC ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 11.11111 ¦ 0.0 ¦ 102.7 ¦ ¦ Shuttering ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.45045 ¦ 0.0 ¦ 106864.3 ¦ ¦ Reinforcement ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.65359 ¦ 0.0 ¦ 51.9 ¦ ¦ Material Receipt Note ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.50761 ¦ 0.0 ¦ 6525.0 ¦ ¦ None ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.72993 ¦ 0.0 ¦ 38993.5 ¦ ¦ PCC ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ -3.44828 ¦ 0.0 ¦ 77.7 ¦ ¦ None ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ -2.94118 ¦ 0.0 ¦ 1230.0 ¦ ### Top Contributors to Project Progress ¦ Activity ¦ Domain ¦ Contribution % ¦ SPI ¦ Status ¦ ¦----------¦--------¦----------------¦-----¦--------¦ ¦ Laying & Jointing ¦ CON ¦ 3.1% ¦ 0.37 ¦ In Progress ¦ ¦ Laying & Jointing ¦ CON ¦ 2.1% ¦ 0.00 ¦ Pending ¦ ¦ Laying & Jointing ¦ CON ¦ 1.6% ¦ 0.76 ¦ In Progress ¦ ¦ Purchase Order ¦ PRC ¦ 1.0% ¦ 0.28 ¦ In Progress ¦ ¦ None ¦ CON ¦ 0.9% ¦ 0.21 ¦ In Progress ¦ ¦ Inspection ¦ PRC ¦ 0.8% ¦ 0.28 ¦ In Progress ¦ ¦ Laying & Jointing ¦ CON ¦ 0.8% ¦ 0.29 ¦ In Progress ¦ ¦ HSC Installation ¦ CON ¦ 0.7% ¦ 1.00 ¦ In Progress ¦ ¦ Laying & Jointing ¦ CON ¦ 0.6% ¦ 0.00 ¦ Pending ¦ ¦ Laying & Jointing ¦ CON ¦ 0.6% ¦ 0.41 ¦ In Progress ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  |  | 1.45 | 2026-02-27T09:45:46.406516
7 | tool | sra_baseline_management | Baseline management | ## 📐 Baseline Management — Mega PWS in 11 block of Ganjam District ### Approved Schedule Reference Points ¦ Baseline Marker ¦ Date ¦ Notes ¦ ¦----------------¦------¦-------¦ ¦ **Original Baseline Start** ¦ 01 Jan 1970 ¦ JCR-approved programme start ¦ ¦ **Original Baseline Finish** ¦ 31 Jan 1970 ¦ JCR-approved completion ¦ ¦ **JCR Approved Date** ¦ 01 Jan 1970 ¦ Joint Construction Review ¦ ¦ **PMS Approved Date** ¦ 01 Jan 1970 ¦ Project Management Schedule ¦ ¦ **Rescheduled Baseline** ¦ 21 Jan 1970 ¦ Current approved revision ¦ ¦ **Contractual Completion** ¦ 01 Jan 1970 ¦ Client contract date ¦ ¦ **Forecast Completion** ¦ 24 Jan 1970 ¦ Current projection ¦ ### Baseline Drift Summary ¦ Drift Metric ¦ Value ¦ Assessment ¦ ¦-------------¦-------¦------------¦ ¦ Baseline vs Rescheduled Slip ¦ -14 ¦ Approved revision from original ¦ ¦ Current vs Rescheduled Slip ¦ 555 ¦ Forecast drift from revision ¦ ¦ Overall Slip Days ¦ 541d ¦ Baseline to forecast ¦ ¦ Schedule Variance ¦ -541d ¦ Earned vs planned ¦ ¦ **Baseline Integrity** ¦ **Significant Drift ? Review Required** ¦ ⬜ ¦ ### Activities with Baseline Drift ✅ All activities are tracking within their approved baseline parameters. --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  |  | 1.26 | 2026-02-27T09:45:47.668840
8 | tool | sra_schedule_quality | Schedule quality | ## 🔎 Schedule Quality & Integrity — Mega PWS in 11 block of Ganjam District ### Data Freshness ¦ Indicator ¦ Value ¦ ¦-----------¦-------¦ ¦ Dashboard As-On Date ¦ 31 Jan 1970 ¦ ¦ Data Age ¦ 3d ¦ ¦ Freshness Status ¦ Recent ? Within Week ¦ ### Look-Ahead Compliance (LAC) *LAC measures the percentage of look-ahead commitments that were executed on time. A reading below 80% indicates a disconnect between short-term planning and site execution.* ¦ Domain ¦ LAC (Week) ¦ LAC (Month) ¦ Overdue Rules ¦ At-Risk 7d ¦ At-Risk 30d ¦ Pending ¦ ¦--------¦------------¦-------------¦---------------¦-----------¦------------¦--------¦ ¦ 🔴 **Construction** ¦ 0.0% ¦ 0.0% ¦ 1 ¦ 1 ¦ 1 ¦ 1 ¦ ¦ 🔴 **Procurement** ¦ 0.0% ¦ 0.0% ¦ 1 ¦ 0 ¦ 0 ¦ 0 ¦ ### Activity Completion Health ¦ Status ¦ Count ¦ Rate ¦ ¦--------¦-------¦------¦ ¦ Total Activities ¦ 14868 ¦ — ¦ ¦ Complete ¦ 2348 ¦ 15.8% ¦ ¦ In Progress ¦ 1878 ¦ — ¦ ¦ Overdue / Not Mobilised ¦ 1323 ¦ 8.9% ¦ ¦ Not Yet Due ¦ — ¦ — ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  |  | 0.03 | 2026-02-27T09:45:47.696502
9 | tool | sra_drill_delay | Drill delay | ## 🔍 Delay & Risk Analysis — Mega PWS in 11 block of Ganjam District **Location**: Ganjam, Odisha. ¦ **Forecast Delay (Overall)**: 463d **Delay by Domain** — E: 390d P: 476d C: 463d 🔴 **Delay Hotspot Domain**: Procurement ¦ **Concentration Domain**: Procurement ⚠️ **Delay Risk Classification**: High ? Escalate --- ### Top Activities Contributing to Schedule Slippage **1980** activities are tracking beyond their forecast completion (0 on critical path): ¦ Activity ¦ Domain ¦ Status ¦ Delay (d) ¦ Critical ¦ Workfront ¦ Delay Source ¦ Severity ¦ ¦----------¦--------¦--------¦-----------¦----------¦-----------¦--------------¦----------¦ ¦ None ¦ ENG ¦ Complete ¦ 60d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ None ¦ ENG ¦ Complete ¦ 60d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Dispatch ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Material Receipt Note ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Plastering ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ None ¦ ENG ¦ Complete ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Inspection ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ None ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ RCC ¦ CON ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Shuttering ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Laying & Jointing ¦ CON ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ None ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ RCC ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Manufacturing Clearence ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Reinforcement ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ### Workfront & Access Constraints **1828** active activities have workfront readiness below 70.0% — unresolved constraints are a primary driver of execution shortfall: ¦ Activity ¦ Domain ¦ Readiness % ¦ Gap Count ¦ Critical ¦ ¦----------¦--------¦-------------¦-----------¦----------¦ ¦ None ¦ CON ¦ 0.0% ¦ 14 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ PCC ¦ CON ¦ 0.0% ¦ 1 ¦ No ¦ ¦ Reinforcement ¦ CON ¦ 0.0% ¦ 6 ¦ No ¦ ¦ Reinforcement ¦ CON ¦ 0.0% ¦ 8 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ RCC ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ Commissioning ¦ CON ¦ 0.0% ¦ 1 ¦ No ¦ ¦ RCC ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ### Summary Statistics - Total Activities: **2106** - Activities with Forecast Slippage: **1980** - Critical Path Activities Slipping: **0** - Average Activity Delay: **23.9d** - Workfront-Constrained Activities: **1828** --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  |  | 1.26 | 2026-02-27T09:45:48.959107
10 | tool | sra_procurement_alignment | Procurement alignment | ## 📦 Procurement & Material Schedule Alignment — Mega PWS in 11 block of Ganjam District ### Procurement LAC Compliance ¦ Metric ¦ Week ¦ Month ¦ RAG ¦ ¦--------¦------¦-------¦-----¦ ¦ 🔴 PRC LAC Compliance ¦ 0.0% ¦ 0.0% ¦ Red ¦ ### Procurement Rule Status ¦ Rule Category ¦ Count ¦ ¦--------------¦-------¦ ¦ Overdue Rules ¦ 🔴 1 ¦ ¦ At Risk (7-day window) ¦ 🟡 0 ¦ ¦ At Risk (30-day window) ¦ 🟡 0 ¦ ¦ Pending ¦ 0 ¦ ¦ Completed ¦ 0 ¦ ### Activity-Level Procurement Risk **5** activities have procurement rules at risk of non-compliance: ¦ Activity ¦ Domain ¦ Total Rules ¦ Overdue ¦ At Risk 7d ¦ At Risk 30d ¦ LAC Week ¦ ¦----------¦--------¦-------------¦---------¦------------¦------------¦----------¦ ¦ Dispatch ¦ PRC ¦ 1 ¦ 🔴 1 ¦ 🟡 0 ¦ 0 ¦ 0.0% ¦ ¦ None ¦ PRC ¦ 1 ¦ 🔴 1 ¦ 🟡 0 ¦ 0 ¦ 0.0% ¦ ¦ Inspection ¦ PRC ¦ 1 ¦ 🔴 1 ¦ 🟡 0 ¦ 0 ¦ 0.0% ¦ ¦ Manufacturing Clearence ¦ PRC ¦ 1 ¦ 🔴 1 ¦ 🟡 0 ¦ 0 ¦ 0.0% ¦ ¦ Purchase Order ¦ PRC ¦ 1 ¦ 🔴 1 ¦ 🟡 0 ¦ 0 ¦ 0.0% ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  |  | 1.95 | 2026-02-27T09:45:50.907015
11 | tool | sra_eot_exposure | EOT exposure | ## ⚖️ EOT Exposure & Contractual Buffer — Mega PWS in 11 block of Ganjam District ¦ Contractual Metric ¦ Value ¦ Assessment ¦ ¦-------------------¦-------¦------------¦ ¦ Contractual Completion Date ¦ 01 Jan 1970 ¦ Client contract ¦ ¦ Forecast Completion Date ¦ 24 Jan 1970 ¦ Current projection ¦ ¦ Days to Contractual End ¦ -240d ¦ Remaining contractual window ¦ ¦ Days to Forecast End ¦ 515d ¦ Remaining programme window ¦ ¦ **EOT Exposure** ¦ **463d** ¦ 🔴 Delay beyond contractual end ¦ ¦ EOT Buffer ¦ -755d ¦ Approved buffer before breach ¦ ¦ **EOT RAG Status** ¦ **Red** ¦ 🔴 ¦ ¦ EOT Eligibility ¦ EOT Likely ? Forecast Exceeds Contract ¦ Contractual entitlement assessment ¦ ### Schedule Recovery Requirement ¦ Recovery Metric ¦ Value ¦ ¦----------------¦-------¦ ¦ Schedule Recovery Required ¦ 755d ¦ ¦ Recovery SPI Required ¦ -3.034 ¦ ¦ Recovery Plan Status ¦ Formal Recovery Plan Required ¦ ¦ Compression Headroom ¦ 0.0% ¦ ⚠️ **The project is currently tracking 463 days beyond the contractual completion date.** An EOT submission may be warranted — review entitlement basis. --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  |  | 0.02 | 2026-02-27T09:45:50.926742
12 | tool | sra_recovery_advise | Recovery advise | ## 🔧 Recovery Planning — Mega PWS in 11 block of Ganjam District ### Current Programme Position ¦ Metric ¦ Value ¦ ¦--------¦-------¦ ¦ PEI ¦ 1.606 ¦ ¦ SPI ¦ 0.228 ¦ ¦ Forecast Delay ¦ 463d ¦ ¦ Recovery Required ¦ 755d ¦ ¦ Workfront Readiness ¦ 0% ¦ ¦ Compression Headroom ¦ 0.0% ¦ ¦ Recovery Plan Status ¦ Formal Recovery Plan Required ¦ --- ### Recovery Strategy Options **Option 1 — Resource Augmentation** 👷 - Deploy additional crews to critical path and near-critical activities - Targeted resource type: labor - Applicable where workfront is available and site capacity permits - Estimated programme recovery: 3–5 days per fortnight of augmentation - Risk level: Medium — quality assurance protocols must be maintained **Option 2 — Schedule Compression (Crashing)** ⏱️ - Introduce extended working hours or additional shifts on critical path activities - Compression headroom available: 0.0% - Estimated programme recovery: 5–8 days - Risk level: Medium — premium cost increase of approximately 12–18% **Option 3 — Fast-Tracking** 🚀 - Introduce concurrent execution of activities currently sequenced in series - Applicable where logical dependencies permit parallel working - Estimated programme recovery: 4–7 days - Risk level: High — increased coordination and interface management required **Option 4 — Resequencing & Scope Deferral** 📋 - Advance high-priority critical path deliverables; defer non-critical scope - Requires stakeholder alignment and change management approval - Estimated programme recovery: 2–4 days - Risk level: Low-Medium — contract implications to be assessed **Option 5 — Workfront Constraint Resolution** 🚧 - Only 0% of activities have confirmed workfront availability - 2101 activities are constrained by material delivery, RoW, or access clearance - Resolving constraints unlocks execution capacity and is the highest-leverage intervention - Coordinate with procurement, land, and logistics teams immediately - Estimated programme recovery: 5–12 days depending on constraint type - Risk level: Low — this is process-driven, not cost-driven --- 💬 *Select an option to simulate its schedule impact, or request that a recovery action be logged for the site planning team.* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  |  | 1.3 | 2026-02-27T09:45:52.222008
13 | tool | sra_simulate | Simulate shuttering | ## 📊 Scenario Analysis — Mega PWS in 11 block of Ganjam District **Scenario**: Deploy 2 × shuttering_gang --- ### Projected Programme Impact ¦ Metric ¦ Current ¦ Projected ¦ Change ¦ ¦--------¦---------¦-----------¦--------¦ ¦ Forecast Delay ¦ 463d ¦ 325d ¦ **−138d** ¦ ¦ SPI ¦ 0.228 ¦ 0.258 ¦ +0.030 ¦ ¦ Productivity Rate ¦ Baseline ¦ +30.0% ¦ ✅ Enhanced ¦ ### Cost Impact - **Incremental Cost Estimate**: ₹50,000 - **Cost per Day Recovered**: ₹362 ### Risk & Implementation Considerations - Coordination overhead with newly mobilised teams; site induction and productivity ramp-up period applies. - Confirm impact on concurrent activities and interface obligations before deployment - Review against EOT entitlement basis if acceleration cost is to be claimed --- 💬 *Shall I log this scenario as an approved recovery action for the planning team?* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  |  | 0.02 | 2026-02-27T09:45:52.239206
14 | tool | sra_create_action | Create action | ## ✅ Recovery Action Logged **Action ID**: `ACT-101-20260227094552` --- ### Action Record ¦ Field ¦ Detail ¦ ¦-------¦--------¦ ¦ Project ¦ Mega PWS in 11 block of Ganjam District (Key: 101) ¦ ¦ Action ¦ Approve Option 1 ¦ ¦ Assigned To ¦ Unassigned — Pending Nomination ¦ ¦ Status ¦ 🟡 **Open — Pending Execution** ¦ ¦ Logged ¦ 27 Feb 2026 09:45 ¦ ### Current Programme Context - PEI: 1.606 - SPI: 0.228 - Forecast Delay: 463d - EOT Exposure: 463d 💡 *This action has been logged for tracking. The assigned team member will receive notification for follow-through.* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  |  | 0.02 | 2026-02-27T09:45:52.255475
15 | tool | sra_accountability_trace | Accountability trace | ## 📝 Accountability & Reporting Traceability — Mega PWS in 11 block of Ganjam District *Scope: All Domains ¦ Activity: All* ### Report-Flagged Tasks (Current Period) **11899** tasks are flagged for narrative reporting this period: ¦ Task ¦ Activity ¦ Domain ¦ Health RAG ¦ Accountability ¦ Narrative Label ¦ ¦------¦----------¦--------¦------------¦----------------¦----------------¦ ¦ Plastering ESR tank portion ¦ Plastering ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ PO ¦ PO ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Background ¦ ¦ PR ¦ PR ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Background ¦ ¦ Shuttering- upto FGL ¦ Shuttering ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Disposal of excess earth ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Plastering ¦ Plastering ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Stainless steel Ladder ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Shuttering - upto bottom slab ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ SS handrail ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Commissioning ¦ Commissioning ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Hard barrication ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Earthwork in Excavation in ordinary soil 1.5m - 3m ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Reinforcement - upto bottom slab ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ RCC - Vertical Side wall upto Roof slab ¦ RCC ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Shuttering - Vertical Side wall upto half height ¦ Shuttering ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Hard barrication ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ RCC - upto 100% staging height ¦ RCC ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Reinforcement - upto GL ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ SS handrail ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Shuttering - Vertical Side wall upto half height ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ### Delay Attribution Trace **14868** tasks have delay attribution records — relevant for variance reporting and potential EOT substantiation: ¦ Task ¦ Activity ¦ Domain ¦ Delay (d) ¦ Attribution ¦ Baseline Drift ¦ ¦------¦----------¦--------¦-----------¦-------------¦----------------¦ ¦ Plastering ESR tank portion ¦ Plastering ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Numeration and RC Detail of ESR of 80KL Capacity 10m Staging height at Pangidi for Scheme-I ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Numeration and RC Detail of ESR of 230KL Capacity 12m Staging height at Chingudighai for Scheme-I ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ PO ¦ PO ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ PR ¦ PR ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Shuttering- upto FGL ¦ Shuttering ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Disposal of excess earth ¦ — ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Plastering ¦ Plastering ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Stainless steel Ladder ¦ — ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Shuttering - upto bottom slab ¦ — ¦ CON ¦ 0d ¦ No Attributable Delay ¦ Significant Slip ? Over 1 Month ¦ ¦ SS handrail ¦ — ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Commissioning ¦ Commissioning ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Hard barrication ¦ — ¦ CON ¦ 0d ¦ No Attributable Delay ¦ Significant Slip ? Over 1 Month ¦ ¦ Earthwork in Excavation in ordinary soil 1.5m - 3m ¦ — ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Reinforcement - upto bottom slab ¦ — ¦ CON ¦ 0d ¦ No Attributable Delay ¦ Significant Slip ? Over 1 Month ¦ ### Recovery Candidate Tasks - **Crash Candidates** (eligible for resource augmentation): 823 - **Fast-Track Candidates** (eligible for concurrent working): 0 ### As-Built vs Baseline Duration (Completed Tasks) ¦ Task ¦ Baseline Duration ¦ As-Built Duration ¦ Duration Variance ¦ ¦------¦------------------¦-------------------¦------------------¦ ¦ Numeration and RC Detail of ESR of 80KL Capacity 10m Staging height at Pangidi for Scheme-I ¦ 40d ¦ 319d ¦ 🔴 279d ¦ ¦ Numeration and RC Detail of ESR of 230KL Capacity 12m Staging height at Chingudighai for Scheme-I ¦ 40d ¦ 148d ¦ 🔴 108d ¦ ¦ Numeration and RC Detail of GLSR of 425KL Capacity at Barida for Scheme-II ¦ 45d ¦ 286d ¦ 🔴 241d ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-316 KENDUPADARA-PR(ASKA) to Village (Ganjam Scheme-1) ¦ 46d ¦ 46d ¦ ✅ 0d ¦ ¦ Numeration and RC Detail of ESR of 210KL Capacity 16m Staging height at Debabhumi for Scheme-I ¦ 40d ¦ 162d ¦ 🔴 122d ¦ ¦ Numeration and RC Detail of Cascade aerator, Parshall flume, Distribution chamber and Flash mixer for Scheme-1 ¦ 45d ¦ 581d ¦ 🔴 536d ¦ ¦ Reinforcement - upto 100% staging height ¦ 10d ¦ 71d ¦ 🔴 61d ¦ ¦ Numeration and RC Detail of Filter Annex Building for Scheme-1 ¦ 40d ¦ 328d ¦ 🔴 288d ¦ ¦ Design Calculation of ESR of 325KL Capacity 16m Staging height at Saurachachina for Scheme-II ¦ 45d ¦ 290d ¦ 🔴 245d ¦ ¦ Hydraulic Flow Diagram for WTP ¦ 45d ¦ 302d ¦ 🔴 257d ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  |  | 7.99 | 2026-02-27T09:46:00.249939
16 | tool | sra_explain_formula | Explain SPI | ## 📐 Schedule Metric Reference Guide *Live context: Mega PWS in 11 block of Ganjam District (Key: 101)* --- ### 📈 SPI — Schedule Performance Index **Formula**: `SPI = Earned Progress % / Planned Progress %` Measures whether work is being executed at the rate the programme demands. An SPI of 1.0 means the project is earning exactly what was planned. Below 1.0 indicates the execution rate is lagging — the gap compounds over time on a critical path. ¦ Value ¦ Signal ¦ Interpretation ¦ ¦-------¦--------¦----------------¦ ¦ SPI > 1.0 ¦ 🟢 Ahead of Programme ¦ Execution exceeds plan ¦ ¦ SPI = 1.0 ¦ ✅ On Programme ¦ Performance exactly as planned ¦ ¦ SPI < 1.0 ¦ 🔴 Behind Programme ¦ Execution rate below plan ¦ *Current SPI: **0.228** — Behind by 77.2%* --- 💡 *Ask about a specific metric for a live calculation against your project — e.g. 'Explain SPI for project 101'* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  |  | 0.02 | 2026-02-27T09:46:00.270099
17 | tool | sra_sql_agent | SQL fallback (project list) | ## ⚠️ Query Syntax Issue The database reported a syntax or access error: > column "project_key" does not exist HINT: Perhaps you meant to reference the column "tbl_01_project_summary.Project_Key". **Query attempted:** ```sql SELECT Project_Key, Project_Name, Project_Location, SPI_Overall, Project_Execution_Index, Max_Forecast_Delay_Days_Overall, EOT_Exposure_Days, Schedule_Health_RAG, Schedule_Health_Score, Data_Freshness_Label FROM tbl_01_project_summary WHERE Project_Key = 101 ORDER BY Max_Forecast_Delay_Days_Overall DESC NULLS LAST LIMIT 500 ``` Please review the column names and table references. Column names follow the `PascalCase_With_Underscores` convention. |  |  | 0.14 | 2026-02-27T09:46:00.405548