## SUMMARY
LAYER | CATEGORY | TOOL NAME | TOTAL | PASS | WARN | FAIL | SKIP | AVG DURATION SEC | ERRORS
L0 | SQL-EDGE | sra_sql_agent | 6 | 2 | 4 | 0 | 0 | 0
L0 | SQL-NL | sra_sql_agent | 14 | 5 | 9 | 0 | 0 | 0.1
L0 | SQL-RAW | sra_sql_agent | 9 | 5 | 4 | 0 | 0 | 0.1
L1 | Activity | sra_activity_health | 5 | 0 | 5 | 0 | 0 | 0.23
L1 | Health | sra_status_pei | 4 | 0 | 4 | 0 | 0 | 0.32
L1 | LookAhead | sra_task_lookahead | 6 | 5 | 1 | 0 | 0 | 2.94
L2 | CritPath | sra_critical_path | 3 | 1 | 2 | 0 | 0 | 1.49
L2 | Float | sra_float_analysis | 5 | 4 | 1 | 0 | 0 | 0.44
L2 | Rate | sra_productivity_rate | 5 | 3 | 2 | 0 | 0 | 0.42
L3 | Baseline | sra_baseline_management | 3 | 1 | 2 | 0 | 0 | 0.21
L3 | Quality | sra_schedule_quality | 3 | 1 | 2 | 0 | 0 | 0.01
L4 | Delay | sra_drill_delay | 5 | 3 | 2 | 0 | 0 | 0.33
L4 | EOT | sra_eot_exposure | 3 | 1 | 2 | 0 | 0 | 0.01
L4 | Procurement | sra_procurement_alignment | 3 | 1 | 2 | 0 | 0 | 0.34
L5 | Actions | sra_create_action | 8 | 6 | 2 | 0 | 0 | 0.01
L5 | Recovery | sra_recovery_advise | 6 | 5 | 1 | 0 | 0 | 0.43
L5 | Simulate | sra_simulate | 8 | 6 | 2 | 0 | 0 | 0.01
L6 | Accountability | sra_accountability_trace | 5 | 4 | 1 | 0 | 0 | 3.03
L6 | Formula | sra_explain_formula | 8 | 2 | 6 | 0 | 0 | 0.01

## LAYER_1_Health
RUN ID | MODE | LAYER | CATEGORY | TEST NAME | TOOL NAME | INPUT SUMMARY | KWARGS | STATUS | VALIDATION NOTE | DURATION SEC | ERROR | TOOL OUTPUT | INSIGHT | TIMESTAMP
1 | tool | L1 | Health | PEI — Full project health snapshot | sra_status_pei | PEI — Full project health snapshot | {'project_key': '101'} | WARN | Expected keywords missing: ['Programme'] | 0.61 |  | ## 🔴 Schedule Health: **Schedule Attention Required** **Mega PWS in 11 block of Ganjam District** · Ganjam, Odisha. *Report Date: 31 Jan 1970* 📊 **Cumulative Progress** — Planned: 100.0% ¦ Achieved: 22.8% ¦ Backlog: 77.2% ⚠️ *SPI at 0.23 — execution is 77.2% behind planned throughput* --- ### Schedule Performance Indices ¦ Index ¦ Value ¦ Signal ¦ Interpretation ¦ ¦-------¦-------¦--------¦----------------¦ ¦ 🔴 **SPI** ¦ 0.228 ¦ Behind Planned Throughput ¦ Earned progress vs planned ¦ ¦ 🔴 **PEI** ¦ 1.606 ¦ Forecast Exceeds Baseline Duration ¦ Forecast duration efficiency ¦ ¦ 🔴 **Health Score** ¦ 15.0/100 ¦ Red ¦ Composite schedule health ¦ ### EPC Domain Breakdown ¦ Domain ¦ Activities ¦ Planned % ¦ Achieved % ¦ Max Delay ¦ Domain SPI ¦ ¦--------¦-----------¦-----------¦------------¦-----------¦------------¦ ¦ 🟡 **Engineering** ¦ 290 ¦ 100.0% ¦ 88.1% ¦ 0d ¦ 0.88 ¦ ¦ 🟡 **Procurement** ¦ 112 ¦ 100.0% ¦ 27.1% ¦ 0d ¦ 0.27 ¦ ¦ 🟡 **Construction** ¦ 1704 ¦ 100.0% ¦ 8.7% ¦ 0d ¦ 0.09 ¦ ¦ ¦ **Overall** ¦ 100.0% ¦ 22.8% ¦ **463d** ¦ 0.228 ¦ ### Supporting Indicators - 🏗️ **Workfront Readiness**: 2.3% ⚠️ - 📅 **EOT Exposure**: 463d ¦ EOT Status: EOT Likely ? Forecast Exceeds Contract - 📋 **Data Freshness**: Recent ? Within Week (3d old) - 🔑 **Weakest Domain**: Construction 💬 *755 days of schedule recovery are required to meet the contractual completion date.* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:10.550486
2 | tool | L1 | Health | PEI — Missing project key (should list projects) | sra_status_pei | PEI — Missing project key (should list projects) | {} | WARN | Expected keywords missing: ['SPI', 'PEI', 'Programme'] | 0 |  | 📋 **Please specify the project to assess.** Available projects: (Unable to retrieve project list) 💡 Example: *What is the schedule health of project 101?* |  | 2026-02-27T09:56:10.551490
3 | tool | L1 | Health | PEI — Invalid project key (non-numeric) | sra_status_pei | PEI — Invalid project key (non-numeric) | {'project_key': 'ABC'} | WARN | Soft error in output: 'Invalid project key' | 0 |  | Invalid project key `ABC`. Please provide a numeric value (e.g. 101). |  | 2026-02-27T09:56:10.552487
4 | tool | L1 | Health | PEI — Non-existent project key | sra_status_pei | PEI — Non-existent project key | {'project_key': '9999'} | WARN | Soft error in output: 'No schedule data found' | 0.02 |  | No schedule data found for project key **9999**. Please verify the project reference. |  | 2026-02-27T09:56:10.567709
5 | tool | L1 | Activity | Activity — All activities, all domains | sra_activity_health | Activity — All activities, all domains | {'project_key': '101'} | WARN | Expected keywords missing: ['Status'] | 0.44 |  | ## 📋 Activity Health Review — Mega PWS in 11 block of Ganjam District *Domain filter: All ¦ Activity filter: All* **Summary** — Total: 2106 ¦ Complete: 277 ¦ In Progress: 291 ¦ Overdue / Not Mobilised: 0 ¦ Not Yet Due: 0 --- ### Activities Requiring Attention ✅ No activities are currently trending beyond their forecast completion. ### Workfront Constraint Watch **1828** activities have workfront readiness below 70.0%: ¦ Activity ¦ Domain ¦ Workfront % ¦ Gap Count ¦ Critical Path ¦ ¦----------¦--------¦-------------¦-----------¦---------------¦ ¦ None ¦ CON ¦ 0.0% ¦ 14 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ PCC ¦ CON ¦ 0.0% ¦ 1 ¦ No ¦ ¦ Reinforcement ¦ CON ¦ 0.0% ¦ 6 ¦ No ¦ ¦ Reinforcement ¦ CON ¦ 0.0% ¦ 8 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ RCC ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ Commissioning ¦ CON ¦ 0.0% ¦ 1 ¦ No ¦ ¦ RCC ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:11.005943
6 | tool | L1 | Activity | Activity — Engineering domain filter (ENG) | sra_activity_health | Activity — Engineering domain filter (ENG) | {'project_key': '101', 'domain_code': 'ENG'} | WARN | Expected keywords missing: ['Status'] | 0.1 |  | ## 📋 Activity Health Review — Mega PWS in 11 block of Ganjam District *Domain filter: ENG ¦ Activity filter: All* **Summary** — Total: 290 ¦ Complete: 194 ¦ In Progress: 72 ¦ Overdue / Not Mobilised: 0 ¦ Not Yet Due: 0 --- ### Activities Requiring Attention ✅ No activities are currently trending beyond their forecast completion. ### Workfront Constraint Watch **95** activities have workfront readiness below 70.0%: ¦ Activity ¦ Domain ¦ Workfront % ¦ Gap Count ¦ Critical Path ¦ ¦----------¦--------¦-------------¦-----------¦---------------¦ ¦ None ¦ ENG ¦ 0.0% ¦ 8 ¦ No ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 8 ¦ No ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 8 ¦ No ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 4 ¦ No ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 12 ¦ No ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 4 ¦ No ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 13 ¦ No ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 4 ¦ No ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 3 ¦ No ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 4 ¦ No ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:11.107910
7 | tool | L1 | Activity | Activity — Procurement domain filter (PRC) | sra_activity_health | Activity — Procurement domain filter (PRC) | {'project_key': '101', 'domain_code': 'PRC'} | WARN | Expected keywords missing: ['Status'] | 0.04 |  | ## 📋 Activity Health Review — Mega PWS in 11 block of Ganjam District *Domain filter: PRC ¦ Activity filter: All* **Summary** — Total: 112 ¦ Complete: 9 ¦ In Progress: 47 ¦ Overdue / Not Mobilised: 0 ¦ Not Yet Due: 0 --- ### Activities Requiring Attention ✅ No activities are currently trending beyond their forecast completion. ### Workfront Constraint Watch **103** activities have workfront readiness below 70.0%: ¦ Activity ¦ Domain ¦ Workfront % ¦ Gap Count ¦ Critical Path ¦ ¦----------¦--------¦-------------¦-----------¦---------------¦ ¦ Material Receipt Note ¦ PRC ¦ 0.0% ¦ 9 ¦ No ¦ ¦ Purchase Request ¦ PRC ¦ 0.0% ¦ 7 ¦ No ¦ ¦ Purchase Request ¦ PRC ¦ 0.0% ¦ 2 ¦ No ¦ ¦ Dispatch ¦ PRC ¦ 0.0% ¦ 29 ¦ No ¦ ¦ Purchase Order ¦ PRC ¦ 0.0% ¦ 29 ¦ No ¦ ¦ Material Receipt Note ¦ PRC ¦ 0.0% ¦ 40 ¦ No ¦ ¦ Manufacturing Clearence ¦ PRC ¦ 0.0% ¦ 21 ¦ No ¦ ¦ Dispatch ¦ PRC ¦ 0.0% ¦ 5 ¦ No ¦ ¦ None ¦ PRC ¦ 0.0% ¦ 6 ¦ No ¦ ¦ Inspection ¦ PRC ¦ 0.0% ¦ 40 ¦ No ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:11.149925
8 | tool | L1 | Activity | Activity — Construction domain filter (CON) | sra_activity_health | Activity — Construction domain filter (CON) | {'project_key': '101', 'domain_code': 'CON'} | WARN | Expected keywords missing: ['Status'] | 0.35 |  | ## 📋 Activity Health Review — Mega PWS in 11 block of Ganjam District *Domain filter: CON ¦ Activity filter: All* **Summary** — Total: 1704 ¦ Complete: 74 ¦ In Progress: 172 ¦ Overdue / Not Mobilised: 0 ¦ Not Yet Due: 0 --- ### Activities Requiring Attention ✅ No activities are currently trending beyond their forecast completion. ### Workfront Constraint Watch **1630** activities have workfront readiness below 70.0%: ¦ Activity ¦ Domain ¦ Workfront % ¦ Gap Count ¦ Critical Path ¦ ¦----------¦--------¦-------------¦-----------¦---------------¦ ¦ None ¦ CON ¦ 0.0% ¦ 14 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ PCC ¦ CON ¦ 0.0% ¦ 1 ¦ No ¦ ¦ Reinforcement ¦ CON ¦ 0.0% ¦ 6 ¦ No ¦ ¦ Reinforcement ¦ CON ¦ 0.0% ¦ 8 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ RCC ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ Commissioning ¦ CON ¦ 0.0% ¦ 1 ¦ No ¦ ¦ RCC ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:11.498225
9 | tool | L1 | Activity | Activity — No project key | sra_activity_health | Activity — No project key | {} | WARN | Expected keywords missing: ['Status', 'Domain', 'Workfront'] | 0 |  | 📋 **Specify the project for activity health review.** (Unable to retrieve project list) |  | 2026-02-27T09:56:11.499234
10 | tool | L1 | LookAhead | Task 2W — All domains, 2-week window | sra_task_lookahead | Task 2W — All domains, 2-week window | {'project_key': '101', 'window': '2W'} | PASS | All expected content present | 3.04 |  | ## 🗓️ 2-Week Look-Ahead — Mega PWS in 11 block of Ganjam District *Scope: All Domains ¦ Activity: All* **14868** tasks fall within the 2-week start window: — Workfront Available: **343** ¦ Workfront Constrained: **14525** ### Tasks Ready to Mobilise ✅ ¦ Task ¦ Activity ¦ Domain ¦ Forecast Start ¦ Forecast Finish ¦ Float ¦ Priority Score ¦ Critical ¦ ¦------¦----------¦--------¦---------------¦-----------------¦-------¦----------------¦----------¦ ¦ Architectural Detail of Filter House & Filter Annex Building for Scheme-2 ¦ — ¦ ENG ¦ 26 Feb ¦ 22 Jan ¦ — ¦ 40.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-18CHANDIPALLI-PR (BEGUNIAPADA) to Village (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 23 Feb ¦ 23 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-4 KANTAPADA-EX (BEGUNIAPADA) to Village (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 20 Feb ¦ 14 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-19 GHODAPADA-PR (BEGUNIAPADA) to Village (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 07 Feb ¦ 14 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-58 PAILIPADA-PR (BELAGUNTHA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 05 Feb ¦ 12 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-18 VENKATRAIPALLI-EX (ASKA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 07 Jan ¦ 17 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-10 SANTARPALLI(BARIDA)-PR (KS NAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 09 Jan ¦ 09 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-1 ARJUNAPALLI-EX (KS NAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 22 Feb ¦ 22 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-131 GOBARALUNDI-PR SORODA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 11 Jan ¦ 02 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme Diagram for Gravity Distribution main from OHT-14 TABHABANIA-PR (BEGUNIAPADA) to Village (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 19 Feb ¦ 14 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme drawing for Clear water Pumping main from CWR at WTP to OHTs & IBPS-1 - (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 16 Jan ¦ 16 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-104 DINDIPALLI-PR (BHANJNAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 23 Feb ¦ 19 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-42 MANGALAPUR -EX (BELAGUNTHA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 17 Feb ¦ 17 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-92 BEDIGOBA-PR (BHANJNAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 17 Jan ¦ 17 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-25 KUMBHARI-PR (ASKA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 11 Jan ¦ 02 Feb ¦ — ¦ 0.0 ¦ ¦ ### Workfront-Constrained Tasks — Action Required ⚠️ ¦ Task ¦ Activity ¦ Domain ¦ Forecast Start ¦ Float ¦ Block Flag ¦ ¦------¦----------¦--------¦---------------¦-------¦------------¦ ¦ Architectural Detail of Chlorine Building for Scheme-1 ¦ — ¦ ENG ¦ 26 Feb ¦ — ¦ Constrained ¦ ¦ Numeration and RC Detail of Cascade aerator, Parshall flume, Distribution chamber and Flash mixer for Scheme-1 ¦ — ¦ ENG ¦ 01 Jan ¦ — ¦ Constrained ¦ ¦ P&ID Drawing for CWR cum Pump House at IBPS-1- (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 11 Jan ¦ — ¦ Constrained ¦ ¦ Overall Single Line Diagram for IBPS 12 ¦ — ¦ ENG ¦ 14 Jan ¦ — ¦ Constrained ¦ ¦ MFC ¦ MFC ¦ PRC ¦ 16 Jan ¦ — ¦ Constrained ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 16 Jan ¦ — ¦ Constrained ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 08 Feb ¦ — ¦ Constrained ¦ ¦ Design Calculation of Intermediate Sump-1 for Scheme-1 ¦ — ¦ ENG ¦ 16 Feb ¦ — ¦ Constrained ¦ ¦ Instrument list for IBPS-5 ¦ — ¦ ENG ¦ 24 Jan ¦ — ¦ Constrained ¦ ¦ Lighting Layout for Intake ¦ — ¦ ENG ¦ 20 Jan ¦ — ¦ Constrained ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:14.540890
11 | tool | L1 | LookAhead | Task 4W — All domains, 4-week window | sra_task_lookahead | Task 4W — All domains, 4-week window | {'project_key': '101', 'window': '4W'} | PASS | All expected content present | 2.88 |  | ## 🗓️ 4-Week Look-Ahead — Mega PWS in 11 block of Ganjam District *Scope: All Domains ¦ Activity: All* **14868** tasks fall within the 4-week start window: — Workfront Available: **343** ¦ Workfront Constrained: **14525** ### Tasks Ready to Mobilise ✅ ¦ Task ¦ Activity ¦ Domain ¦ Forecast Start ¦ Forecast Finish ¦ Float ¦ Priority Score ¦ Critical ¦ ¦------¦----------¦--------¦---------------¦-----------------¦-------¦----------------¦----------¦ ¦ Architectural Detail of Filter House & Filter Annex Building for Scheme-2 ¦ — ¦ ENG ¦ 26 Feb ¦ 22 Jan ¦ — ¦ 40.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-18CHANDIPALLI-PR (BEGUNIAPADA) to Village (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 23 Feb ¦ 23 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-4 KANTAPADA-EX (BEGUNIAPADA) to Village (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 20 Feb ¦ 14 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-19 GHODAPADA-PR (BEGUNIAPADA) to Village (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 07 Feb ¦ 14 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-58 PAILIPADA-PR (BELAGUNTHA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 05 Feb ¦ 12 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-18 VENKATRAIPALLI-EX (ASKA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 07 Jan ¦ 17 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-10 SANTARPALLI(BARIDA)-PR (KS NAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 09 Jan ¦ 09 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-1 ARJUNAPALLI-EX (KS NAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 22 Feb ¦ 22 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-131 GOBARALUNDI-PR SORODA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 11 Jan ¦ 02 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme Diagram for Gravity Distribution main from OHT-14 TABHABANIA-PR (BEGUNIAPADA) to Village (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 19 Feb ¦ 14 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme drawing for Clear water Pumping main from CWR at WTP to OHTs & IBPS-1 - (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 16 Jan ¦ 16 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-104 DINDIPALLI-PR (BHANJNAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 23 Feb ¦ 19 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-42 MANGALAPUR -EX (BELAGUNTHA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 17 Feb ¦ 17 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-92 BEDIGOBA-PR (BHANJNAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 17 Jan ¦ 17 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-25 KUMBHARI-PR (ASKA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 11 Jan ¦ 02 Feb ¦ — ¦ 0.0 ¦ ¦ ### Workfront-Constrained Tasks — Action Required ⚠️ ¦ Task ¦ Activity ¦ Domain ¦ Forecast Start ¦ Float ¦ Block Flag ¦ ¦------¦----------¦--------¦---------------¦-------¦------------¦ ¦ Architectural Detail of Chlorine Building for Scheme-1 ¦ — ¦ ENG ¦ 26 Feb ¦ — ¦ Constrained ¦ ¦ Numeration and RC Detail of Cascade aerator, Parshall flume, Distribution chamber and Flash mixer for Scheme-1 ¦ — ¦ ENG ¦ 01 Jan ¦ — ¦ Constrained ¦ ¦ P&ID Drawing for CWR cum Pump House at IBPS-1- (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 11 Jan ¦ — ¦ Constrained ¦ ¦ Overall Single Line Diagram for IBPS 12 ¦ — ¦ ENG ¦ 14 Jan ¦ — ¦ Constrained ¦ ¦ MFC ¦ MFC ¦ PRC ¦ 16 Jan ¦ — ¦ Constrained ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 16 Jan ¦ — ¦ Constrained ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 08 Feb ¦ — ¦ Constrained ¦ ¦ Design Calculation of Intermediate Sump-1 for Scheme-1 ¦ — ¦ ENG ¦ 16 Feb ¦ — ¦ Constrained ¦ ¦ Instrument list for IBPS-5 ¦ — ¦ ENG ¦ 24 Jan ¦ — ¦ Constrained ¦ ¦ Lighting Layout for Intake ¦ — ¦ ENG ¦ 20 Jan ¦ — ¦ Constrained ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:17.422127
12 | tool | L1 | LookAhead | Task 2W — Construction domain only | sra_task_lookahead | Task 2W — Construction domain only | {'project_key': '101', 'window': '2W', 'domain_code': 'CON'} | PASS | All expected content present | 2.95 |  | ## 🗓️ 2-Week Look-Ahead — Mega PWS in 11 block of Ganjam District *Scope: CON ¦ Activity: All* **10991** tasks fall within the 2-week start window: — Workfront Available: **0** ¦ Workfront Constrained: **10991** ### Tasks Ready to Mobilise ✅ No workfront-available tasks in the look-ahead window. ### Workfront-Constrained Tasks — Action Required ⚠️ ¦ Task ¦ Activity ¦ Domain ¦ Forecast Start ¦ Float ¦ Block Flag ¦ ¦------¦----------¦--------¦---------------¦-------¦------------¦ ¦ Plastering ESR tank portion ¦ Plastering ¦ CON ¦ 01 Jan ¦ — ¦ Constrained ¦ ¦ Shuttering- upto FGL ¦ Shuttering ¦ CON ¦ 22 Jan ¦ — ¦ Constrained ¦ ¦ Disposal of excess earth ¦ — ¦ CON ¦ 22 Jan ¦ — ¦ Constrained ¦ ¦ Plastering ¦ Plastering ¦ CON ¦ 01 Jan ¦ — ¦ Constrained ¦ ¦ Stainless steel Ladder ¦ — ¦ CON ¦ 01 Jan ¦ — ¦ Constrained ¦ ¦ Shuttering - upto bottom slab ¦ — ¦ CON ¦ — ¦ — ¦ Constrained ¦ ¦ SS handrail ¦ — ¦ CON ¦ 22 Jan ¦ — ¦ Constrained ¦ ¦ Commissioning ¦ Commissioning ¦ CON ¦ 17 Feb ¦ — ¦ Constrained ¦ ¦ Hard barrication ¦ — ¦ CON ¦ — ¦ — ¦ Constrained ¦ ¦ Earthwork in Excavation in ordinary soil 1.5m - 3m ¦ — ¦ CON ¦ 22 Jan ¦ — ¦ Constrained ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:20.369763
13 | tool | L1 | LookAhead | Task 4W — Engineering domain only | sra_task_lookahead | Task 4W — Engineering domain only | {'project_key': '101', 'window': '4W', 'domain_code': 'ENG'} | PASS | All expected content present | 2.84 |  | ## 🗓️ 4-Week Look-Ahead — Mega PWS in 11 block of Ganjam District *Scope: ENG ¦ Activity: All* **2694** tasks fall within the 4-week start window: — Workfront Available: **343** ¦ Workfront Constrained: **2351** ### Tasks Ready to Mobilise ✅ ¦ Task ¦ Activity ¦ Domain ¦ Forecast Start ¦ Forecast Finish ¦ Float ¦ Priority Score ¦ Critical ¦ ¦------¦----------¦--------¦---------------¦-----------------¦-------¦----------------¦----------¦ ¦ Architectural Detail of Filter House & Filter Annex Building for Scheme-2 ¦ — ¦ ENG ¦ 26 Feb ¦ 22 Jan ¦ — ¦ 40.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-18CHANDIPALLI-PR (BEGUNIAPADA) to Village (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 23 Feb ¦ 23 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-4 KANTAPADA-EX (BEGUNIAPADA) to Village (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 20 Feb ¦ 14 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-19 GHODAPADA-PR (BEGUNIAPADA) to Village (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 07 Feb ¦ 14 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-58 PAILIPADA-PR (BELAGUNTHA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 05 Feb ¦ 12 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-18 VENKATRAIPALLI-EX (ASKA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 07 Jan ¦ 17 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-10 SANTARPALLI(BARIDA)-PR (KS NAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 09 Jan ¦ 09 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-1 ARJUNAPALLI-EX (KS NAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 22 Feb ¦ 22 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-131 GOBARALUNDI-PR SORODA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 11 Jan ¦ 02 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme Diagram for Gravity Distribution main from OHT-14 TABHABANIA-PR (BEGUNIAPADA) to Village (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 19 Feb ¦ 14 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme drawing for Clear water Pumping main from CWR at WTP to OHTs & IBPS-1 - (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 16 Jan ¦ 16 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-104 DINDIPALLI-PR (BHANJNAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 23 Feb ¦ 19 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-42 MANGALAPUR -EX (BELAGUNTHA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 17 Feb ¦ 17 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-92 BEDIGOBA-PR (BHANJNAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 17 Jan ¦ 17 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-25 KUMBHARI-PR (ASKA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 11 Jan ¦ 02 Feb ¦ — ¦ 0.0 ¦ ¦ ### Workfront-Constrained Tasks — Action Required ⚠️ ¦ Task ¦ Activity ¦ Domain ¦ Forecast Start ¦ Float ¦ Block Flag ¦ ¦------¦----------¦--------¦---------------¦-------¦------------¦ ¦ Architectural Detail of Chlorine Building for Scheme-1 ¦ — ¦ ENG ¦ 26 Feb ¦ — ¦ Constrained ¦ ¦ Numeration and RC Detail of Cascade aerator, Parshall flume, Distribution chamber and Flash mixer for Scheme-1 ¦ — ¦ ENG ¦ 01 Jan ¦ — ¦ Constrained ¦ ¦ P&ID Drawing for CWR cum Pump House at IBPS-1- (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 11 Jan ¦ — ¦ Constrained ¦ ¦ Overall Single Line Diagram for IBPS 12 ¦ — ¦ ENG ¦ 14 Jan ¦ — ¦ Constrained ¦ ¦ Design Calculation of Intermediate Sump-1 for Scheme-1 ¦ — ¦ ENG ¦ 16 Feb ¦ — ¦ Constrained ¦ ¦ Instrument list for IBPS-5 ¦ — ¦ ENG ¦ 24 Jan ¦ — ¦ Constrained ¦ ¦ Lighting Layout for Intake ¦ — ¦ ENG ¦ 20 Jan ¦ — ¦ Constrained ¦ ¦ 33/11 kV Switchyard Layout for IBPS 1 ¦ — ¦ ENG ¦ 14 Jan ¦ — ¦ Constrained ¦ ¦ Surge Analysis Report for Clear water Pumping main from IBPS-09 (PM-2) to OHTs Ganjam WSS (Scheme-1) ¦ — ¦ ENG ¦ 30 Jan ¦ — ¦ Constrained ¦ ¦ Control And Interlock Details for IBPS-4 ¦ — ¦ ENG ¦ 24 Jan ¦ — ¦ Constrained ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:23.210848
14 | tool | L1 | LookAhead | Task 2W — Procurement domain only | sra_task_lookahead | Task 2W — Procurement domain only | {'project_key': '101', 'window': '2W', 'domain_code': 'PRC'} | PASS | All expected content present | 2.99 |  | ## 🗓️ 2-Week Look-Ahead — Mega PWS in 11 block of Ganjam District *Scope: PRC ¦ Activity: All* **1183** tasks fall within the 2-week start window: — Workfront Available: **0** ¦ Workfront Constrained: **1183** ### Tasks Ready to Mobilise ✅ No workfront-available tasks in the look-ahead window. ### Workfront-Constrained Tasks — Action Required ⚠️ ¦ Task ¦ Activity ¦ Domain ¦ Forecast Start ¦ Float ¦ Block Flag ¦ ¦------¦----------¦--------¦---------------¦-------¦------------¦ ¦ MFC ¦ MFC ¦ PRC ¦ 16 Jan ¦ — ¦ Constrained ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 16 Jan ¦ — ¦ Constrained ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 08 Feb ¦ — ¦ Constrained ¦ ¦ MRN ¦ MRN ¦ PRC ¦ 27 Feb ¦ — ¦ Constrained ¦ ¦ PR ¦ PR ¦ PRC ¦ 22 Jan ¦ — ¦ Constrained ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 16 Jan ¦ — ¦ Constrained ¦ ¦ PO ¦ PO ¦ PRC ¦ 16 Jan ¦ — ¦ Constrained ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 16 Jan ¦ — ¦ Constrained ¦ ¦ PR ¦ PR ¦ PRC ¦ 02 Mar ¦ — ¦ Constrained ¦ ¦ PO ¦ PO ¦ PRC ¦ 16 Jan ¦ — ¦ Constrained ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:26.203806
15 | tool | L1 | LookAhead | Task 2W — No project key | sra_task_lookahead | Task 2W — No project key | {} | WARN | Expected keywords missing: ['Task', 'Forecast'] | 0 |  | 📋 **Specify the project for the look-ahead window.** (Unable to retrieve project list) |  | 2026-02-27T09:56:26.205261

## LAYER_2_Intel
RUN ID | MODE | LAYER | CATEGORY | TEST NAME | TOOL NAME | INPUT SUMMARY | KWARGS | STATUS | VALIDATION NOTE | DURATION SEC | ERROR | TOOL OUTPUT | INSIGHT | TIMESTAMP
16 | tool | L2 | CritPath | Critical Path — Full project CP analysis | sra_critical_path | Critical Path — Full project CP analysis | {'project_key': '101'} | PASS | All expected content present | 2.97 |  | ## 🔴 Critical Path Analysis — Mega PWS in 11 block of Ganjam District **CP Task Count**: 0 ¦ **Total Tasks**: 14868 --- ### Float Distribution Summary ¦ Float Band ¦ Task Count ¦ % of Programme ¦ ¦-----------¦-----------¦----------------¦ ¦ 🔴 Negative Float ¦ 0 ¦ 0.0% ¦ ¦ 🔴 Zero Float (Critical) ¦ 0 ¦ 0.0% ¦ ¦ 🟡 Near-Critical (≤5d) ¦ 0 ¦ 0.0% ¦ ¦ 🟢 Healthy Float ¦ 0 ¦ 0.0% ¦ ¦ **Project Min Float** ¦ — ¦ **0d** ¦ ¦ **Average Float** ¦ — ¦ **0d** ¦ ### Controlling Critical Path Tasks (Top 15) No critical path tasks identified under current float parameters. --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:29.171490
17 | tool | L2 | CritPath | Critical Path — No project key | sra_critical_path | Critical Path — No project key | {} | WARN | Expected keywords missing: ['Float', 'CP'] | 0 |  | 📋 **Specify the project for critical path analysis.** (Unable to retrieve project list) |  | 2026-02-27T09:56:29.172490
18 | tool | L2 | CritPath | Critical Path — Non-existent project | sra_critical_path | Critical Path — Non-existent project | {'project_key': '9999'} | WARN | Soft error in output: 'No schedule data found' | 0.01 |  | No schedule data found for project key **9999**. |  | 2026-02-27T09:56:29.181159
19 | tool | L2 | Float | Float — Full programme float analysis | sra_float_analysis | Float — Full programme float analysis | {'project_key': '101'} | PASS | All expected content present | 0.42 |  | ## ⏳ Float Analysis & Near-Critical Watch — Mega PWS in 11 block of Ganjam District **Programme Float Health**: — ¦ **At-Risk Float**: 0.0% ¦ **Min Float**: 0d --- ### Near-Critical Activity Watch (Float ≤ 5 days) ✅ No activities are within the 5-day near-critical threshold. ### Float Erosion Watch ✅ No float erosion flags are currently active across the selected scope. ⚠️ **54 activities have breached the Critical Activity Density (CAD) threshold** — these require schedule management escalation. --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:29.600963
20 | tool | L2 | Float | Float — Construction domain float watch | sra_float_analysis | Float — Construction domain float watch | {'project_key': '101', 'domain_code': 'CON'} | PASS | All expected content present | 0.5 |  | ## ⏳ Float Analysis & Near-Critical Watch — Mega PWS in 11 block of Ganjam District **Programme Float Health**: — ¦ **At-Risk Float**: 0.0% ¦ **Min Float**: 0d --- ### Near-Critical Activity Watch (Float ≤ 5 days) ✅ No activities are within the 5-day near-critical threshold. ### Float Erosion Watch ✅ No float erosion flags are currently active across the selected scope. --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:30.102553
21 | tool | L2 | Float | Float — Engineering domain float watch | sra_float_analysis | Float — Engineering domain float watch | {'project_key': '101', 'domain_code': 'ENG'} | PASS | All expected content present | 0.44 |  | ## ⏳ Float Analysis & Near-Critical Watch — Mega PWS in 11 block of Ganjam District **Programme Float Health**: — ¦ **At-Risk Float**: 0.0% ¦ **Min Float**: 0d --- ### Near-Critical Activity Watch (Float ≤ 5 days) ✅ No activities are within the 5-day near-critical threshold. ### Float Erosion Watch ✅ No float erosion flags are currently active across the selected scope. ⚠️ **19 activities have breached the Critical Activity Density (CAD) threshold** — these require schedule management escalation. --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:30.540142
22 | tool | L2 | Float | Float — Procurement domain float watch | sra_float_analysis | Float — Procurement domain float watch | {'project_key': '101', 'domain_code': 'PRC'} | PASS | All expected content present | 0.4 |  | ## ⏳ Float Analysis & Near-Critical Watch — Mega PWS in 11 block of Ganjam District **Programme Float Health**: — ¦ **At-Risk Float**: 0.0% ¦ **Min Float**: 0d --- ### Near-Critical Activity Watch (Float ≤ 5 days) ✅ No activities are within the 5-day near-critical threshold. ### Float Erosion Watch ✅ No float erosion flags are currently active across the selected scope. ⚠️ **35 activities have breached the Critical Activity Density (CAD) threshold** — these require schedule management escalation. --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:30.944182
23 | tool | L2 | Float | Float — No project key | sra_float_analysis | Float — No project key | {} | WARN | Expected keywords missing: ['Near-Critical', 'Erosion'] | 0 |  | 📋 **Specify the project for float analysis.** (Unable to retrieve project list) |  | 2026-02-27T09:56:30.945182
24 | tool | L2 | Rate | Productivity — Full rate gap analysis | sra_productivity_rate | Productivity — Full rate gap analysis | {'project_key': '101'} | PASS | All expected content present | 0.41 |  | ## ⚡ Productivity & Rate Analysis — Mega PWS in 11 block of Ganjam District *Scope: All Domains ¦ Activity: All* **Executable Progress (Overall)**: 0.2% ¦ **E**: 0.0% **P**: 3.5% **C**: 0.1% --- ### Execution Rate Gap — Activities Below Required Rate *A rate shortfall is a leading indicator of schedule slippage — even activities marked In Progress can drive future delays if the production rate is below what the plan demands.* **1714** activities are tracking below the required progress rate: ¦ Activity ¦ Domain ¦ Planned % ¦ Achieved % ¦ Variance ¦ Required Rate/Day ¦ Earned Qty ¦ Planned Qty ¦ ¦----------¦--------¦-----------¦------------¦----------¦-------------------¦-----------¦-------------¦ ¦ None ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.61728 ¦ 0.0 ¦ 74.9 ¦ ¦ PCC ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ -3.22581 ¦ 0.0 ¦ 352.6 ¦ ¦ Reinforcement ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 7.69231 ¦ 0.0 ¦ 2935.0 ¦ ¦ Reinforcement ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 3.125 ¦ 0.0 ¦ 1800.0 ¦ ¦ Shuttering ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.44843 ¦ 0.0 ¦ 16029.2 ¦ ¦ RCC ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.45662 ¦ 0.0 ¦ 1320.0 ¦ ¦ Shuttering ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ -3.84615 ¦ 0.0 ¦ 2033.9 ¦ ¦ Commissioning ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.5291 ¦ 0.0 ¦ 82.0 ¦ ¦ RCC ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 1.0101 ¦ 0.0 ¦ 151.7 ¦ ¦ Reinforcement ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 5.26316 ¦ 0.0 ¦ 151.1 ¦ ¦ Plastering ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.53476 ¦ 0.0 ¦ 22479.5 ¦ ¦ Plastering ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.4065 ¦ 0.0 ¦ 25476.7 ¦ ¦ Reinforcement ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ -4.34783 ¦ 0.0 ¦ 72.1 ¦ ¦ PCC ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 11.11111 ¦ 0.0 ¦ 102.7 ¦ ¦ Shuttering ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.45045 ¦ 0.0 ¦ 106864.3 ¦ ¦ Reinforcement ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.65359 ¦ 0.0 ¦ 51.9 ¦ ¦ Material Receipt Note ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.50761 ¦ 0.0 ¦ 6525.0 ¦ ¦ None ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.72993 ¦ 0.0 ¦ 38993.5 ¦ ¦ PCC ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ -3.44828 ¦ 0.0 ¦ 77.7 ¦ ¦ None ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ -2.94118 ¦ 0.0 ¦ 1230.0 ¦ ### Top Contributors to Project Progress ¦ Activity ¦ Domain ¦ Contribution % ¦ SPI ¦ Status ¦ ¦----------¦--------¦----------------¦-----¦--------¦ ¦ Laying & Jointing ¦ CON ¦ 3.1% ¦ 0.37 ¦ In Progress ¦ ¦ Laying & Jointing ¦ CON ¦ 2.1% ¦ 0.00 ¦ Pending ¦ ¦ Laying & Jointing ¦ CON ¦ 1.6% ¦ 0.76 ¦ In Progress ¦ ¦ Purchase Order ¦ PRC ¦ 1.0% ¦ 0.28 ¦ In Progress ¦ ¦ None ¦ CON ¦ 0.9% ¦ 0.21 ¦ In Progress ¦ ¦ Inspection ¦ PRC ¦ 0.8% ¦ 0.28 ¦ In Progress ¦ ¦ Laying & Jointing ¦ CON ¦ 0.8% ¦ 0.29 ¦ In Progress ¦ ¦ HSC Installation ¦ CON ¦ 0.7% ¦ 1.00 ¦ In Progress ¦ ¦ Laying & Jointing ¦ CON ¦ 0.6% ¦ 0.00 ¦ Pending ¦ ¦ Laying & Jointing ¦ CON ¦ 0.6% ¦ 0.41 ¦ In Progress ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:31.351198
25 | tool | L2 | Rate | Productivity — Construction rate analysis | sra_productivity_rate | Productivity — Construction rate analysis | {'project_key': '101', 'domain_code': 'CON'} | PASS | All expected content present | 0.42 |  | ## ⚡ Productivity & Rate Analysis — Mega PWS in 11 block of Ganjam District *Scope: CON ¦ Activity: All* **Executable Progress (Overall)**: 0.2% ¦ **E**: 0.0% **P**: 3.5% **C**: 0.1% --- ### Execution Rate Gap — Activities Below Required Rate *A rate shortfall is a leading indicator of schedule slippage — even activities marked In Progress can drive future delays if the production rate is below what the plan demands.* **1612** activities are tracking below the required progress rate: ¦ Activity ¦ Domain ¦ Planned % ¦ Achieved % ¦ Variance ¦ Required Rate/Day ¦ Earned Qty ¦ Planned Qty ¦ ¦----------¦--------¦-----------¦------------¦----------¦-------------------¦-----------¦-------------¦ ¦ None ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.61728 ¦ 0.0 ¦ 74.9 ¦ ¦ PCC ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ -3.22581 ¦ 0.0 ¦ 352.6 ¦ ¦ Reinforcement ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 7.69231 ¦ 0.0 ¦ 2935.0 ¦ ¦ Reinforcement ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 3.125 ¦ 0.0 ¦ 1800.0 ¦ ¦ Shuttering ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.44843 ¦ 0.0 ¦ 16029.2 ¦ ¦ RCC ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.45662 ¦ 0.0 ¦ 1320.0 ¦ ¦ Shuttering ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ -3.84615 ¦ 0.0 ¦ 2033.9 ¦ ¦ Commissioning ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.5291 ¦ 0.0 ¦ 82.0 ¦ ¦ RCC ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 1.0101 ¦ 0.0 ¦ 151.7 ¦ ¦ Reinforcement ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 5.26316 ¦ 0.0 ¦ 151.1 ¦ ¦ Plastering ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.53476 ¦ 0.0 ¦ 22479.5 ¦ ¦ Plastering ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.4065 ¦ 0.0 ¦ 25476.7 ¦ ¦ Reinforcement ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ -4.34783 ¦ 0.0 ¦ 72.1 ¦ ¦ PCC ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 11.11111 ¦ 0.0 ¦ 102.7 ¦ ¦ Shuttering ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.45045 ¦ 0.0 ¦ 106864.3 ¦ ¦ Reinforcement ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.65359 ¦ 0.0 ¦ 51.9 ¦ ¦ None ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.72993 ¦ 0.0 ¦ 38993.5 ¦ ¦ PCC ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ -3.44828 ¦ 0.0 ¦ 77.7 ¦ ¦ None ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ -2.94118 ¦ 0.0 ¦ 1230.0 ¦ ¦ Plastering ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 1.16279 ¦ 0.0 ¦ 1838.3 ¦ ### Top Contributors to Project Progress ¦ Activity ¦ Domain ¦ Contribution % ¦ SPI ¦ Status ¦ ¦----------¦--------¦----------------¦-----¦--------¦ ¦ Laying & Jointing ¦ CON ¦ 3.1% ¦ 0.37 ¦ In Progress ¦ ¦ Laying & Jointing ¦ CON ¦ 2.1% ¦ 0.00 ¦ Pending ¦ ¦ Laying & Jointing ¦ CON ¦ 1.6% ¦ 0.76 ¦ In Progress ¦ ¦ None ¦ CON ¦ 0.9% ¦ 0.21 ¦ In Progress ¦ ¦ Laying & Jointing ¦ CON ¦ 0.8% ¦ 0.29 ¦ In Progress ¦ ¦ HSC Installation ¦ CON ¦ 0.7% ¦ 1.00 ¦ In Progress ¦ ¦ Laying & Jointing ¦ CON ¦ 0.6% ¦ 0.00 ¦ Pending ¦ ¦ Laying & Jointing ¦ CON ¦ 0.6% ¦ 0.41 ¦ In Progress ¦ ¦ None ¦ CON ¦ 0.6% ¦ 0.00 ¦ Pending ¦ ¦ None ¦ CON ¦ 0.5% ¦ 0.48 ¦ In Progress ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:31.773396
26 | tool | L2 | Rate | Productivity — Engineering rate analysis | sra_productivity_rate | Productivity — Engineering rate analysis | {'project_key': '101', 'domain_code': 'ENG'} | WARN | Expected keywords missing: ['Earned', 'Planned'] | 0.43 |  | ## ⚡ Productivity & Rate Analysis — Mega PWS in 11 block of Ganjam District *Scope: ENG ¦ Activity: All* **Executable Progress (Overall)**: 0.2% ¦ **E**: 0.0% **P**: 3.5% **C**: 0.1% --- ### Execution Rate Gap — Activities Below Required Rate *A rate shortfall is a leading indicator of schedule slippage — even activities marked In Progress can drive future delays if the production rate is below what the plan demands.* ✅ All active activities are tracking at or above the required progress rate. ### Top Contributors to Project Progress ¦ Activity ¦ Domain ¦ Contribution % ¦ SPI ¦ Status ¦ ¦----------¦--------¦----------------¦-----¦--------¦ ¦ None ¦ ENG ¦ 0.1% ¦ 0.85 ¦ In Progress ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 0.00 ¦ Pending ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 1.00 ¦ Complete ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 0.00 ¦ Pending ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 1.00 ¦ Complete ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 1.00 ¦ Complete ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 1.00 ¦ Complete ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 0.00 ¦ Pending ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 1.00 ¦ Complete ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 1.00 ¦ Complete ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:32.203966
27 | tool | L2 | Rate | Productivity — Procurement rate analysis | sra_productivity_rate | Productivity — Procurement rate analysis | {'project_key': '101', 'domain_code': 'PRC'} | PASS | All expected content present | 0.42 |  | ## ⚡ Productivity & Rate Analysis — Mega PWS in 11 block of Ganjam District *Scope: PRC ¦ Activity: All* **Executable Progress (Overall)**: 0.2% ¦ **E**: 0.0% **P**: 3.5% **C**: 0.1% --- ### Execution Rate Gap — Activities Below Required Rate *A rate shortfall is a leading indicator of schedule slippage — even activities marked In Progress can drive future delays if the production rate is below what the plan demands.* **102** activities are tracking below the required progress rate: ¦ Activity ¦ Domain ¦ Planned % ¦ Achieved % ¦ Variance ¦ Required Rate/Day ¦ Earned Qty ¦ Planned Qty ¦ ¦----------¦--------¦-----------¦------------¦----------¦-------------------¦-----------¦-------------¦ ¦ Material Receipt Note ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.50761 ¦ 0.0 ¦ 6525.0 ¦ ¦ Purchase Request ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 1.04167 ¦ — ¦ 113940.6 ¦ ¦ Dispatch ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 1.04167 ¦ — ¦ 2545.9 ¦ ¦ Purchase Order ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 1.04167 ¦ — ¦ 2545.9 ¦ ¦ Material Receipt Note ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.43103 ¦ — ¦ 128268.0 ¦ ¦ None ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 1.04167 ¦ — ¦ 19680.0 ¦ ¦ Inspection ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.43103 ¦ — ¦ 128268.0 ¦ ¦ Dispatch ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.43103 ¦ — ¦ 128268.0 ¦ ¦ None ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.43103 ¦ — ¦ 128268.0 ¦ ¦ Purchase Order ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 1.04167 ¦ — ¦ 19680.0 ¦ ¦ Purchase Request ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.50761 ¦ — ¦ 6525.0 ¦ ¦ Purchase Request ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 1.04167 ¦ — ¦ 19680.0 ¦ ¦ Material Receipt Note ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 1.04167 ¦ — ¦ 41580.0 ¦ ¦ Purchase Request ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.43103 ¦ — ¦ 128268.0 ¦ ¦ Manufacturing Clearence ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.43103 ¦ — ¦ 128268.0 ¦ ¦ Inspection ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 1.04167 ¦ — ¦ 2545.9 ¦ ¦ Purchase Order ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 1.04167 ¦ — ¦ 113940.6 ¦ ¦ None ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.43103 ¦ — ¦ 128268.0 ¦ ¦ Dispatch ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 1.04167 ¦ — ¦ 19680.0 ¦ ¦ Inspection ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.50761 ¦ — ¦ 6525.0 ¦ ### Top Contributors to Project Progress ¦ Activity ¦ Domain ¦ Contribution % ¦ SPI ¦ Status ¦ ¦----------¦--------¦----------------¦-----¦--------¦ ¦ Purchase Order ¦ PRC ¦ 1.0% ¦ 0.28 ¦ In Progress ¦ ¦ Inspection ¦ PRC ¦ 0.8% ¦ 0.28 ¦ In Progress ¦ ¦ None ¦ PRC ¦ 0.6% ¦ 0.28 ¦ In Progress ¦ ¦ Manufacturing Clearence ¦ PRC ¦ 0.6% ¦ 0.28 ¦ In Progress ¦ ¦ Material Receipt Note ¦ PRC ¦ 0.4% ¦ 0.28 ¦ In Progress ¦ ¦ Dispatch ¦ PRC ¦ 0.4% ¦ 0.28 ¦ In Progress ¦ ¦ Purchase Request ¦ PRC ¦ 0.2% ¦ 0.63 ¦ In Progress ¦ ¦ Purchase Order ¦ PRC ¦ 0.1% ¦ 0.70 ¦ In Progress ¦ ¦ Purchase Order ¦ PRC ¦ 0.1% ¦ 1.00 ¦ Complete ¦ ¦ Purchase Order ¦ PRC ¦ 0.1% ¦ 1.00 ¦ Complete ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:32.625037
28 | tool | L2 | Rate | Productivity — No project key | sra_productivity_rate | Productivity — No project key | {} | WARN | Expected keywords missing: ['Progress', 'Earned', 'Planned'] | 0 |  | 📋 **Specify the project for productivity rate analysis.** (Unable to retrieve project list) |  | 2026-02-27T09:56:32.625037

## LAYER_3_Integrity
RUN ID | MODE | LAYER | CATEGORY | TEST NAME | TOOL NAME | INPUT SUMMARY | KWARGS | STATUS | VALIDATION NOTE | DURATION SEC | ERROR | TOOL OUTPUT | INSIGHT | TIMESTAMP
29 | tool | L3 | Baseline | Baseline — JCR/PMS dates, drift analysis | sra_baseline_management | Baseline — JCR/PMS dates, drift analysis | {'project_key': '101'} | PASS | All expected content present | 0.42 |  | ## 📐 Baseline Management — Mega PWS in 11 block of Ganjam District ### Approved Schedule Reference Points ¦ Baseline Marker ¦ Date ¦ Notes ¦ ¦----------------¦------¦-------¦ ¦ **Original Baseline Start** ¦ 01 Jan 1970 ¦ JCR-approved programme start ¦ ¦ **Original Baseline Finish** ¦ 31 Jan 1970 ¦ JCR-approved completion ¦ ¦ **JCR Approved Date** ¦ 01 Jan 1970 ¦ Joint Construction Review ¦ ¦ **PMS Approved Date** ¦ 01 Jan 1970 ¦ Project Management Schedule ¦ ¦ **Rescheduled Baseline** ¦ 21 Jan 1970 ¦ Current approved revision ¦ ¦ **Contractual Completion** ¦ 01 Jan 1970 ¦ Client contract date ¦ ¦ **Forecast Completion** ¦ 24 Jan 1970 ¦ Current projection ¦ ### Baseline Drift Summary ¦ Drift Metric ¦ Value ¦ Assessment ¦ ¦-------------¦-------¦------------¦ ¦ Baseline vs Rescheduled Slip ¦ -14 ¦ Approved revision from original ¦ ¦ Current vs Rescheduled Slip ¦ 555 ¦ Forecast drift from revision ¦ ¦ Overall Slip Days ¦ 541d ¦ Baseline to forecast ¦ ¦ Schedule Variance ¦ -541d ¦ Earned vs planned ¦ ¦ **Baseline Integrity** ¦ **Significant Drift ? Review Required** ¦ ⬜ ¦ ### Activities with Baseline Drift ✅ All activities are tracking within their approved baseline parameters. --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:33.046356
30 | tool | L3 | Baseline | Baseline — No project key | sra_baseline_management | Baseline — No project key | {} | WARN | Expected keywords missing: ['Drift', 'JCR', 'Slip'] | 0 |  | 📋 **Specify the project for baseline management review.** (Unable to retrieve project list) |  | 2026-02-27T09:56:33.046356
31 | tool | L3 | Baseline | Baseline — Non-existent project | sra_baseline_management | Baseline — Non-existent project | {'project_key': '9999'} | WARN | Soft error in output: 'No schedule data found' | 0.01 |  | No schedule data found for project key **9999**. |  | 2026-02-27T09:56:33.061292
32 | tool | L3 | Quality | Quality — Data freshness + LAC compliance (full) | sra_schedule_quality | Quality — Data freshness + LAC compliance (full) | {'project_key': '101'} | PASS | All expected content present | 0.01 |  | ## 🔎 Schedule Quality & Integrity — Mega PWS in 11 block of Ganjam District ### Data Freshness ¦ Indicator ¦ Value ¦ ¦-----------¦-------¦ ¦ Dashboard As-On Date ¦ 31 Jan 1970 ¦ ¦ Data Age ¦ 3d ¦ ¦ Freshness Status ¦ Recent ? Within Week ¦ ### Look-Ahead Compliance (LAC) *LAC measures the percentage of look-ahead commitments that were executed on time. A reading below 80% indicates a disconnect between short-term planning and site execution.* ¦ Domain ¦ LAC (Week) ¦ LAC (Month) ¦ Overdue Rules ¦ At-Risk 7d ¦ At-Risk 30d ¦ Pending ¦ ¦--------¦------------¦-------------¦---------------¦-----------¦------------¦--------¦ ¦ 🔴 **Construction** ¦ 0.0% ¦ 0.0% ¦ 1 ¦ 1 ¦ 1 ¦ 1 ¦ ¦ 🔴 **Procurement** ¦ 0.0% ¦ 0.0% ¦ 1 ¦ 0 ¦ 0 ¦ 0 ¦ ### Activity Completion Health ¦ Status ¦ Count ¦ Rate ¦ ¦--------¦-------¦------¦ ¦ Total Activities ¦ 14868 ¦ — ¦ ¦ Complete ¦ 2348 ¦ 15.8% ¦ ¦ In Progress ¦ 1878 ¦ — ¦ ¦ Overdue / Not Mobilised ¦ 1323 ¦ 8.9% ¦ ¦ Not Yet Due ¦ — ¦ — ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:33.075426
33 | tool | L3 | Quality | Quality — No project key | sra_schedule_quality | Quality — No project key | {} | WARN | Expected keywords missing: ['LAC', 'Compliance', 'Data Freshness'] | 0 |  | 📋 **Specify the project for schedule quality review.** (Unable to retrieve project list) |  | 2026-02-27T09:56:33.077427
34 | tool | L3 | Quality | Quality — Non-existent project | sra_schedule_quality | Quality — Non-existent project | {'project_key': '9999'} | WARN | Soft error in output: 'No schedule data found' | 0.01 |  | No schedule data found for project key **9999**. |  | 2026-02-27T09:56:33.091672

## LAYER_4_Risk
RUN ID | MODE | LAYER | CATEGORY | TEST NAME | TOOL NAME | INPUT SUMMARY | KWARGS | STATUS | VALIDATION NOTE | DURATION SEC | ERROR | TOOL OUTPUT | INSIGHT | TIMESTAMP
35 | tool | L4 | Delay | Delay — Full delay & risk analysis | sra_drill_delay | Delay — Full delay & risk analysis | {'project_key': '101'} | PASS | All expected content present | 0.47 |  | ## 🔍 Delay & Risk Analysis — Mega PWS in 11 block of Ganjam District **Location**: Ganjam, Odisha. ¦ **Forecast Delay (Overall)**: 463d **Delay by Domain** — E: 390d P: 476d C: 463d 🔴 **Delay Hotspot Domain**: Procurement ¦ **Concentration Domain**: Procurement ⚠️ **Delay Risk Classification**: High ? Escalate --- ### Top Activities Contributing to Schedule Slippage **1980** activities are tracking beyond their forecast completion (0 on critical path): ¦ Activity ¦ Domain ¦ Status ¦ Delay (d) ¦ Critical ¦ Workfront ¦ Delay Source ¦ Severity ¦ ¦----------¦--------¦--------¦-----------¦----------¦-----------¦--------------¦----------¦ ¦ None ¦ ENG ¦ Complete ¦ 60d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ None ¦ ENG ¦ Complete ¦ 60d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Dispatch ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Material Receipt Note ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Plastering ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ None ¦ ENG ¦ Complete ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Inspection ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ None ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ RCC ¦ CON ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Shuttering ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Laying & Jointing ¦ CON ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ None ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ RCC ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Manufacturing Clearence ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Reinforcement ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ### Workfront & Access Constraints **1828** active activities have workfront readiness below 70.0% — unresolved constraints are a primary driver of execution shortfall: ¦ Activity ¦ Domain ¦ Readiness % ¦ Gap Count ¦ Critical ¦ ¦----------¦--------¦-------------¦-----------¦----------¦ ¦ None ¦ CON ¦ 0.0% ¦ 14 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ PCC ¦ CON ¦ 0.0% ¦ 1 ¦ No ¦ ¦ Reinforcement ¦ CON ¦ 0.0% ¦ 6 ¦ No ¦ ¦ Reinforcement ¦ CON ¦ 0.0% ¦ 8 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ RCC ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ Commissioning ¦ CON ¦ 0.0% ¦ 1 ¦ No ¦ ¦ RCC ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ### Summary Statistics - Total Activities: **2106** - Activities with Forecast Slippage: **1980** - Critical Path Activities Slipping: **0** - Average Activity Delay: **23.9d** - Workfront-Constrained Activities: **1828** --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:33.562595
36 | tool | L4 | Delay | Delay — With start/end date window | sra_drill_delay | Delay — With start/end date window | {'project_key': '101', 'start_date': '2025-01-01', 'end_date': '2025-06-30'} | PASS | All expected content present | 0.43 |  | ## 🔍 Delay & Risk Analysis — Mega PWS in 11 block of Ganjam District **Location**: Ganjam, Odisha. ¦ **Forecast Delay (Overall)**: 463d **Delay by Domain** — E: 390d P: 476d C: 463d 🔴 **Delay Hotspot Domain**: Procurement ¦ **Concentration Domain**: Procurement ⚠️ **Delay Risk Classification**: High ? Escalate --- ### Top Activities Contributing to Schedule Slippage **1980** activities are tracking beyond their forecast completion (0 on critical path): ¦ Activity ¦ Domain ¦ Status ¦ Delay (d) ¦ Critical ¦ Workfront ¦ Delay Source ¦ Severity ¦ ¦----------¦--------¦--------¦-----------¦----------¦-----------¦--------------¦----------¦ ¦ None ¦ ENG ¦ Complete ¦ 60d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ None ¦ ENG ¦ Complete ¦ 60d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Dispatch ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Material Receipt Note ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Plastering ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ None ¦ ENG ¦ Complete ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Inspection ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ None ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ RCC ¦ CON ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Shuttering ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Laying & Jointing ¦ CON ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ None ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ RCC ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Manufacturing Clearence ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Reinforcement ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ### Workfront & Access Constraints **1828** active activities have workfront readiness below 70.0% — unresolved constraints are a primary driver of execution shortfall: ¦ Activity ¦ Domain ¦ Readiness % ¦ Gap Count ¦ Critical ¦ ¦----------¦--------¦-------------¦-----------¦----------¦ ¦ None ¦ CON ¦ 0.0% ¦ 14 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ PCC ¦ CON ¦ 0.0% ¦ 1 ¦ No ¦ ¦ Reinforcement ¦ CON ¦ 0.0% ¦ 6 ¦ No ¦ ¦ Reinforcement ¦ CON ¦ 0.0% ¦ 8 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ RCC ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ Commissioning ¦ CON ¦ 0.0% ¦ 1 ¦ No ¦ ¦ RCC ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ### Summary Statistics - Total Activities: **2106** - Activities with Forecast Slippage: **1980** - Critical Path Activities Slipping: **0** - Average Activity Delay: **23.9d** - Workfront-Constrained Activities: **1828** --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:33.992756
37 | tool | L4 | Delay | Delay — Q3 2025 date window | sra_drill_delay | Delay — Q3 2025 date window | {'project_key': '101', 'start_date': '2025-07-01', 'end_date': '2025-09-30'} | PASS | All expected content present | 0.41 |  | ## 🔍 Delay & Risk Analysis — Mega PWS in 11 block of Ganjam District **Location**: Ganjam, Odisha. ¦ **Forecast Delay (Overall)**: 463d **Delay by Domain** — E: 390d P: 476d C: 463d 🔴 **Delay Hotspot Domain**: Procurement ¦ **Concentration Domain**: Procurement ⚠️ **Delay Risk Classification**: High ? Escalate --- ### Top Activities Contributing to Schedule Slippage **1980** activities are tracking beyond their forecast completion (0 on critical path): ¦ Activity ¦ Domain ¦ Status ¦ Delay (d) ¦ Critical ¦ Workfront ¦ Delay Source ¦ Severity ¦ ¦----------¦--------¦--------¦-----------¦----------¦-----------¦--------------¦----------¦ ¦ None ¦ ENG ¦ Complete ¦ 60d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ None ¦ ENG ¦ Complete ¦ 60d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Dispatch ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Material Receipt Note ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Plastering ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ None ¦ ENG ¦ Complete ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Inspection ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ None ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ RCC ¦ CON ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Shuttering ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Laying & Jointing ¦ CON ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ None ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ RCC ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Manufacturing Clearence ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Reinforcement ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ### Workfront & Access Constraints **1828** active activities have workfront readiness below 70.0% — unresolved constraints are a primary driver of execution shortfall: ¦ Activity ¦ Domain ¦ Readiness % ¦ Gap Count ¦ Critical ¦ ¦----------¦--------¦-------------¦-----------¦----------¦ ¦ None ¦ CON ¦ 0.0% ¦ 14 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ PCC ¦ CON ¦ 0.0% ¦ 1 ¦ No ¦ ¦ Reinforcement ¦ CON ¦ 0.0% ¦ 6 ¦ No ¦ ¦ Reinforcement ¦ CON ¦ 0.0% ¦ 8 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ RCC ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ Commissioning ¦ CON ¦ 0.0% ¦ 1 ¦ No ¦ ¦ RCC ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ### Summary Statistics - Total Activities: **2106** - Activities with Forecast Slippage: **1980** - Critical Path Activities Slipping: **0** - Average Activity Delay: **23.9d** - Workfront-Constrained Activities: **1828** --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:34.405055
38 | tool | L4 | Delay | Delay — No project key | sra_drill_delay | Delay — No project key | {} | WARN | Expected keywords missing: ['Hotspot', 'Workfront'] | 0 |  | 📋 **Please specify the project for delay analysis.** Available projects: (Unable to retrieve project list) 💡 Example: *Analyse delay exposure for project 101* |  | 2026-02-27T09:56:34.406053
39 | tool | L4 | Delay | Delay — Non-existent project | sra_drill_delay | Delay — Non-existent project | {'project_key': '9999'} | WARN | Soft error in output: 'No schedule data found' | 0.01 |  | No schedule data found for project key **9999**. |  | 2026-02-27T09:56:34.414001
40 | tool | L4 | Procurement | PRC — Procurement rule alignment (full) | sra_procurement_alignment | PRC — Procurement rule alignment (full) | {'project_key': '101'} | PASS | All expected content present | 0.66 |  | ## 📦 Procurement & Material Schedule Alignment — Mega PWS in 11 block of Ganjam District ### Procurement LAC Compliance ¦ Metric ¦ Week ¦ Month ¦ RAG ¦ ¦--------¦------¦-------¦-----¦ ¦ 🔴 PRC LAC Compliance ¦ 0.0% ¦ 0.0% ¦ Red ¦ ### Procurement Rule Status ¦ Rule Category ¦ Count ¦ ¦--------------¦-------¦ ¦ Overdue Rules ¦ 🔴 1 ¦ ¦ At Risk (7-day window) ¦ 🟡 0 ¦ ¦ At Risk (30-day window) ¦ 🟡 0 ¦ ¦ Pending ¦ 0 ¦ ¦ Completed ¦ 0 ¦ ### Activity-Level Procurement Risk **5** activities have procurement rules at risk of non-compliance: ¦ Activity ¦ Domain ¦ Total Rules ¦ Overdue ¦ At Risk 7d ¦ At Risk 30d ¦ LAC Week ¦ ¦----------¦--------¦-------------¦---------¦------------¦------------¦----------¦ ¦ Dispatch ¦ PRC ¦ 1 ¦ 🔴 1 ¦ 🟡 0 ¦ 0 ¦ 0.0% ¦ ¦ None ¦ PRC ¦ 1 ¦ 🔴 1 ¦ 🟡 0 ¦ 0 ¦ 0.0% ¦ ¦ Inspection ¦ PRC ¦ 1 ¦ 🔴 1 ¦ 🟡 0 ¦ 0 ¦ 0.0% ¦ ¦ Manufacturing Clearence ¦ PRC ¦ 1 ¦ 🔴 1 ¦ 🟡 0 ¦ 0 ¦ 0.0% ¦ ¦ Purchase Order ¦ PRC ¦ 1 ¦ 🔴 1 ¦ 🟡 0 ¦ 0 ¦ 0.0% ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:35.077525
41 | tool | L4 | Procurement | PRC — No project key | sra_procurement_alignment | PRC — No project key | {} | WARN | Expected keywords missing: ['PRC', 'LAC'] | 0 |  | 📋 **Specify the project for procurement alignment review.** (Unable to retrieve project list) |  | 2026-02-27T09:56:35.078523
42 | tool | L4 | Procurement | PRC — Non-existent project | sra_procurement_alignment | PRC — Non-existent project | {'project_key': '9999'} | WARN | Soft error in output: 'No schedule data found' | 0.01 |  | No schedule data found for project key **9999**. |  | 2026-02-27T09:56:35.090693
43 | tool | L4 | EOT | EOT — Exposure and contractual buffer analysis | sra_eot_exposure | EOT — Exposure and contractual buffer analysis | {'project_key': '101'} | PASS | All expected content present | 0.01 |  | ## ⚖️ EOT Exposure & Contractual Buffer — Mega PWS in 11 block of Ganjam District ¦ Contractual Metric ¦ Value ¦ Assessment ¦ ¦-------------------¦-------¦------------¦ ¦ Contractual Completion Date ¦ 01 Jan 1970 ¦ Client contract ¦ ¦ Forecast Completion Date ¦ 24 Jan 1970 ¦ Current projection ¦ ¦ Days to Contractual End ¦ -240d ¦ Remaining contractual window ¦ ¦ Days to Forecast End ¦ 515d ¦ Remaining programme window ¦ ¦ **EOT Exposure** ¦ **463d** ¦ 🔴 Delay beyond contractual end ¦ ¦ EOT Buffer ¦ -755d ¦ Approved buffer before breach ¦ ¦ **EOT RAG Status** ¦ **Red** ¦ 🔴 ¦ ¦ EOT Eligibility ¦ EOT Likely ? Forecast Exceeds Contract ¦ Contractual entitlement assessment ¦ ### Schedule Recovery Requirement ¦ Recovery Metric ¦ Value ¦ ¦----------------¦-------¦ ¦ Schedule Recovery Required ¦ 755d ¦ ¦ Recovery SPI Required ¦ -3.034 ¦ ¦ Recovery Plan Status ¦ Formal Recovery Plan Required ¦ ¦ Compression Headroom ¦ 0.0% ¦ ⚠️ **The project is currently tracking 463 days beyond the contractual completion date.** An EOT submission may be warranted — review entitlement basis. --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:35.103231
44 | tool | L4 | EOT | EOT — No project key | sra_eot_exposure | EOT — No project key | {} | WARN | Expected keywords missing: ['Contractual', 'Buffer'] | 0 |  | 📋 **Specify the project for EOT exposure assessment.** (Unable to retrieve project list) |  | 2026-02-27T09:56:35.104231
45 | tool | L4 | EOT | EOT — Non-existent project | sra_eot_exposure | EOT — Non-existent project | {'project_key': '9999'} | WARN | Soft error in output: 'No schedule data found' | 0.01 |  | No schedule data found for project key **9999**. |  | 2026-02-27T09:56:35.112823

## LAYER_5_Action
RUN ID | MODE | LAYER | CATEGORY | TEST NAME | TOOL NAME | INPUT SUMMARY | KWARGS | STATUS | VALIDATION NOTE | DURATION SEC | ERROR | TOOL OUTPUT | INSIGHT | TIMESTAMP
46 | tool | L5 | Recovery | Recovery — Generic options (no resource type) | sra_recovery_advise | Recovery — Generic options (no resource type) | {'project_key': '101'} | PASS | All expected content present | 0.42 |  | ## 🔧 Recovery Planning — Mega PWS in 11 block of Ganjam District ### Current Programme Position ¦ Metric ¦ Value ¦ ¦--------¦-------¦ ¦ PEI ¦ 1.606 ¦ ¦ SPI ¦ 0.228 ¦ ¦ Forecast Delay ¦ 463d ¦ ¦ Recovery Required ¦ 755d ¦ ¦ Workfront Readiness ¦ 0% ¦ ¦ Compression Headroom ¦ 0.0% ¦ ¦ Recovery Plan Status ¦ Formal Recovery Plan Required ¦ --- ### Recovery Strategy Options **Option 1 — Resource Augmentation** 👷 - Deploy additional crews to critical path and near-critical activities - Applicable where workfront is available and site capacity permits - Estimated programme recovery: 3–5 days per fortnight of augmentation - Risk level: Medium — quality assurance protocols must be maintained **Option 2 — Schedule Compression (Crashing)** ⏱️ - Introduce extended working hours or additional shifts on critical path activities - Compression headroom available: 0.0% - Estimated programme recovery: 5–8 days - Risk level: Medium — premium cost increase of approximately 12–18% **Option 3 — Fast-Tracking** 🚀 - Introduce concurrent execution of activities currently sequenced in series - Applicable where logical dependencies permit parallel working - Estimated programme recovery: 4–7 days - Risk level: High — increased coordination and interface management required **Option 4 — Resequencing & Scope Deferral** 📋 - Advance high-priority critical path deliverables; defer non-critical scope - Requires stakeholder alignment and change management approval - Estimated programme recovery: 2–4 days - Risk level: Low-Medium — contract implications to be assessed **Option 5 — Workfront Constraint Resolution** 🚧 - Only 0% of activities have confirmed workfront availability - 2101 activities are constrained by material delivery, RoW, or access clearance - Resolving constraints unlocks execution capacity and is the highest-leverage intervention - Coordinate with procurement, land, and logistics teams immediately - Estimated programme recovery: 5–12 days depending on constraint type - Risk level: Low — this is process-driven, not cost-driven --- 💬 *Select an option to simulate its schedule impact, or request that a recovery action be logged for the site planning team.* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:35.528137
47 | tool | L5 | Recovery | Recovery — Labor-targeted recovery advice | sra_recovery_advise | Recovery — Labor-targeted recovery advice | {'project_key': '101', 'resource_type': 'labor'} | PASS | All expected content present | 0.41 |  | ## 🔧 Recovery Planning — Mega PWS in 11 block of Ganjam District ### Current Programme Position ¦ Metric ¦ Value ¦ ¦--------¦-------¦ ¦ PEI ¦ 1.606 ¦ ¦ SPI ¦ 0.228 ¦ ¦ Forecast Delay ¦ 463d ¦ ¦ Recovery Required ¦ 755d ¦ ¦ Workfront Readiness ¦ 0% ¦ ¦ Compression Headroom ¦ 0.0% ¦ ¦ Recovery Plan Status ¦ Formal Recovery Plan Required ¦ --- ### Recovery Strategy Options **Option 1 — Resource Augmentation** 👷 - Deploy additional crews to critical path and near-critical activities - Targeted resource type: labor - Applicable where workfront is available and site capacity permits - Estimated programme recovery: 3–5 days per fortnight of augmentation - Risk level: Medium — quality assurance protocols must be maintained **Option 2 — Schedule Compression (Crashing)** ⏱️ - Introduce extended working hours or additional shifts on critical path activities - Compression headroom available: 0.0% - Estimated programme recovery: 5–8 days - Risk level: Medium — premium cost increase of approximately 12–18% **Option 3 — Fast-Tracking** 🚀 - Introduce concurrent execution of activities currently sequenced in series - Applicable where logical dependencies permit parallel working - Estimated programme recovery: 4–7 days - Risk level: High — increased coordination and interface management required **Option 4 — Resequencing & Scope Deferral** 📋 - Advance high-priority critical path deliverables; defer non-critical scope - Requires stakeholder alignment and change management approval - Estimated programme recovery: 2–4 days - Risk level: Low-Medium — contract implications to be assessed **Option 5 — Workfront Constraint Resolution** 🚧 - Only 0% of activities have confirmed workfront availability - 2101 activities are constrained by material delivery, RoW, or access clearance - Resolving constraints unlocks execution capacity and is the highest-leverage intervention - Coordinate with procurement, land, and logistics teams immediately - Estimated programme recovery: 5–12 days depending on constraint type - Risk level: Low — this is process-driven, not cost-driven --- 💬 *Select an option to simulate its schedule impact, or request that a recovery action be logged for the site planning team.* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:35.941051
48 | tool | L5 | Recovery | Recovery — Equipment-targeted recovery advice | sra_recovery_advise | Recovery — Equipment-targeted recovery advice | {'project_key': '101', 'resource_type': 'equipment'} | PASS | All expected content present | 0.53 |  | ## 🔧 Recovery Planning — Mega PWS in 11 block of Ganjam District ### Current Programme Position ¦ Metric ¦ Value ¦ ¦--------¦-------¦ ¦ PEI ¦ 1.606 ¦ ¦ SPI ¦ 0.228 ¦ ¦ Forecast Delay ¦ 463d ¦ ¦ Recovery Required ¦ 755d ¦ ¦ Workfront Readiness ¦ 0% ¦ ¦ Compression Headroom ¦ 0.0% ¦ ¦ Recovery Plan Status ¦ Formal Recovery Plan Required ¦ --- ### Recovery Strategy Options **Option 1 — Resource Augmentation** 👷 - Deploy additional crews to critical path and near-critical activities - Targeted resource type: equipment - Applicable where workfront is available and site capacity permits - Estimated programme recovery: 3–5 days per fortnight of augmentation - Risk level: Medium — quality assurance protocols must be maintained **Option 2 — Schedule Compression (Crashing)** ⏱️ - Introduce extended working hours or additional shifts on critical path activities - Compression headroom available: 0.0% - Estimated programme recovery: 5–8 days - Risk level: Medium — premium cost increase of approximately 12–18% **Option 3 — Fast-Tracking** 🚀 - Introduce concurrent execution of activities currently sequenced in series - Applicable where logical dependencies permit parallel working - Estimated programme recovery: 4–7 days - Risk level: High — increased coordination and interface management required **Option 4 — Resequencing & Scope Deferral** 📋 - Advance high-priority critical path deliverables; defer non-critical scope - Requires stakeholder alignment and change management approval - Estimated programme recovery: 2–4 days - Risk level: Low-Medium — contract implications to be assessed **Option 5 — Workfront Constraint Resolution** 🚧 - Only 0% of activities have confirmed workfront availability - 2101 activities are constrained by material delivery, RoW, or access clearance - Resolving constraints unlocks execution capacity and is the highest-leverage intervention - Coordinate with procurement, land, and logistics teams immediately - Estimated programme recovery: 5–12 days depending on constraint type - Risk level: Low — this is process-driven, not cost-driven --- 💬 *Select an option to simulate its schedule impact, or request that a recovery action be logged for the site planning team.* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:36.468812
49 | tool | L5 | Recovery | Recovery — Material-targeted recovery advice | sra_recovery_advise | Recovery — Material-targeted recovery advice | {'project_key': '101', 'resource_type': 'material'} | PASS | All expected content present | 0.41 |  | ## 🔧 Recovery Planning — Mega PWS in 11 block of Ganjam District ### Current Programme Position ¦ Metric ¦ Value ¦ ¦--------¦-------¦ ¦ PEI ¦ 1.606 ¦ ¦ SPI ¦ 0.228 ¦ ¦ Forecast Delay ¦ 463d ¦ ¦ Recovery Required ¦ 755d ¦ ¦ Workfront Readiness ¦ 0% ¦ ¦ Compression Headroom ¦ 0.0% ¦ ¦ Recovery Plan Status ¦ Formal Recovery Plan Required ¦ --- ### Recovery Strategy Options **Option 1 — Resource Augmentation** 👷 - Deploy additional crews to critical path and near-critical activities - Targeted resource type: material - Applicable where workfront is available and site capacity permits - Estimated programme recovery: 3–5 days per fortnight of augmentation - Risk level: Medium — quality assurance protocols must be maintained **Option 2 — Schedule Compression (Crashing)** ⏱️ - Introduce extended working hours or additional shifts on critical path activities - Compression headroom available: 0.0% - Estimated programme recovery: 5–8 days - Risk level: Medium — premium cost increase of approximately 12–18% **Option 3 — Fast-Tracking** 🚀 - Introduce concurrent execution of activities currently sequenced in series - Applicable where logical dependencies permit parallel working - Estimated programme recovery: 4–7 days - Risk level: High — increased coordination and interface management required **Option 4 — Resequencing & Scope Deferral** 📋 - Advance high-priority critical path deliverables; defer non-critical scope - Requires stakeholder alignment and change management approval - Estimated programme recovery: 2–4 days - Risk level: Low-Medium — contract implications to be assessed **Option 5 — Workfront Constraint Resolution** 🚧 - Only 0% of activities have confirmed workfront availability - 2101 activities are constrained by material delivery, RoW, or access clearance - Resolving constraints unlocks execution capacity and is the highest-leverage intervention - Coordinate with procurement, land, and logistics teams immediately - Estimated programme recovery: 5–12 days depending on constraint type - Risk level: Low — this is process-driven, not cost-driven --- 💬 *Select an option to simulate its schedule impact, or request that a recovery action be logged for the site planning team.* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:36.882528
50 | tool | L5 | Recovery | Recovery — Activity-focused (activity_id provided) | sra_recovery_advise | Recovery — Activity-focused (activity_id provided) | {'project_key': '101', 'resource_type': 'labor', 'activity_id': 'ACT-001'} | PASS | All expected content present | 0.4 |  | ## 🔧 Recovery Planning — Mega PWS in 11 block of Ganjam District ### Current Programme Position ¦ Metric ¦ Value ¦ ¦--------¦-------¦ ¦ PEI ¦ 1.606 ¦ ¦ SPI ¦ 0.228 ¦ ¦ Forecast Delay ¦ 463d ¦ ¦ Recovery Required ¦ 755d ¦ ¦ Workfront Readiness ¦ 0% ¦ ¦ Compression Headroom ¦ 0.0% ¦ ¦ Recovery Plan Status ¦ Formal Recovery Plan Required ¦ --- ### Recovery Strategy Options **Option 1 — Resource Augmentation** 👷 - Deploy additional crews to critical path and near-critical activities - Targeted resource type: labor - Applicable where workfront is available and site capacity permits - Estimated programme recovery: 3–5 days per fortnight of augmentation - Risk level: Medium — quality assurance protocols must be maintained **Option 2 — Schedule Compression (Crashing)** ⏱️ - Introduce extended working hours or additional shifts on critical path activities - Compression headroom available: 0.0% - Estimated programme recovery: 5–8 days - Risk level: Medium — premium cost increase of approximately 12–18% **Option 3 — Fast-Tracking** 🚀 - Introduce concurrent execution of activities currently sequenced in series - Recommended focal point: activity ACT-001 - Applicable where logical dependencies permit parallel working - Estimated programme recovery: 4–7 days - Risk level: High — increased coordination and interface management required **Option 4 — Resequencing & Scope Deferral** 📋 - Advance high-priority critical path deliverables; defer non-critical scope - Requires stakeholder alignment and change management approval - Estimated programme recovery: 2–4 days - Risk level: Low-Medium — contract implications to be assessed **Option 5 — Workfront Constraint Resolution** 🚧 - Only 0% of activities have confirmed workfront availability - 2101 activities are constrained by material delivery, RoW, or access clearance - Resolving constraints unlocks execution capacity and is the highest-leverage intervention - Coordinate with procurement, land, and logistics teams immediately - Estimated programme recovery: 5–12 days depending on constraint type - Risk level: Low — this is process-driven, not cost-driven --- 💬 *Select an option to simulate its schedule impact, or request that a recovery action be logged for the site planning team.* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:37.279574
51 | tool | L5 | Recovery | Recovery — No project key | sra_recovery_advise | Recovery — No project key | {} | WARN | Expected keywords missing: ['Workfront'] | 0 |  | 📋 **Specify the project for recovery planning.** (Unable to retrieve project list) 💡 Example: *What are the recovery options for project 101?* |  | 2026-02-27T09:56:37.280572
52 | tool | L5 | Simulate | Simulate — 2 shuttering gangs | sra_simulate | Simulate — 2 shuttering gangs | {'project_key': '101', 'resource_type': 'shuttering_gang', 'value_amount': 2} | PASS | All expected content present | 0.01 |  | ## 📊 Scenario Analysis — Mega PWS in 11 block of Ganjam District **Scenario**: Deploy 2 × shuttering_gang --- ### Projected Programme Impact ¦ Metric ¦ Current ¦ Projected ¦ Change ¦ ¦--------¦---------¦-----------¦--------¦ ¦ Forecast Delay ¦ 463d ¦ 325d ¦ **−138d** ¦ ¦ SPI ¦ 0.228 ¦ 0.258 ¦ +0.030 ¦ ¦ Productivity Rate ¦ Baseline ¦ +30.0% ¦ ✅ Enhanced ¦ ### Cost Impact - **Incremental Cost Estimate**: ₹50,000 - **Cost per Day Recovered**: ₹362 ### Risk & Implementation Considerations - Coordination overhead with newly mobilised teams; site induction and productivity ramp-up period applies. - Confirm impact on concurrent activities and interface obligations before deployment - Review against EOT entitlement basis if acceleration cost is to be claimed --- 💬 *Shall I log this scenario as an approved recovery action for the planning team?* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:37.289090
53 | tool | L5 | Simulate | Simulate — 5 additional labor (manpower) | sra_simulate | Simulate — 5 additional labor (manpower) | {'project_key': '101', 'resource_type': 'labor', 'value_amount': 5} | PASS | All expected content present | 0.01 |  | ## 📊 Scenario Analysis — Mega PWS in 11 block of Ganjam District **Scenario**: Deploy 5 × labor --- ### Projected Programme Impact ¦ Metric ¦ Current ¦ Projected ¦ Change ¦ ¦--------¦---------¦-----------¦--------¦ ¦ Forecast Delay ¦ 463d ¦ 348d ¦ **−115d** ¦ ¦ SPI ¦ 0.228 ¦ 0.253 ¦ +0.025 ¦ ¦ Productivity Rate ¦ Baseline ¦ +25.0% ¦ ✅ Enhanced ¦ ### Cost Impact - **Incremental Cost Estimate**: ₹25,000 - **Cost per Day Recovered**: ₹217 ### Risk & Implementation Considerations - Workforce absorption capacity and supervisory ratio should be validated before deployment. - Confirm impact on concurrent activities and interface obligations before deployment - Review against EOT entitlement basis if acceleration cost is to be claimed --- 💬 *Shall I log this scenario as an approved recovery action for the planning team?* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:37.302088
54 | tool | L5 | Simulate | Simulate — 1 excavator deployment | sra_simulate | Simulate — 1 excavator deployment | {'project_key': '101', 'resource_type': 'equipment', 'value_amount': 1} | PASS | All expected content present | 0.01 |  | ## 📊 Scenario Analysis — Mega PWS in 11 block of Ganjam District **Scenario**: Deploy 1 × equipment --- ### Projected Programme Impact ¦ Metric ¦ Current ¦ Projected ¦ Change ¦ ¦--------¦---------¦-----------¦--------¦ ¦ Forecast Delay ¦ 463d ¦ 371d ¦ **−92d** ¦ ¦ SPI ¦ 0.228 ¦ 0.248 ¦ +0.020 ¦ ¦ Productivity Rate ¦ Baseline ¦ +20.0% ¦ ✅ Enhanced ¦ ### Cost Impact - **Incremental Cost Estimate**: ₹50,000 - **Cost per Day Recovered**: ₹543 ### Risk & Implementation Considerations - Equipment mobilisation lead time and site access must be confirmed prior to deployment. - Confirm impact on concurrent activities and interface obligations before deployment - Review against EOT entitlement basis if acceleration cost is to be claimed --- 💬 *Shall I log this scenario as an approved recovery action for the planning team?* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:37.311854
55 | tool | L5 | Simulate | Simulate — Sunday overtime working | sra_simulate | Simulate — Sunday overtime working | {'project_key': '101', 'resource_type': 'overtime', 'value_amount': 1, 'date_range': 'this Sunday'} | PASS | All expected content present | 0.01 |  | ## 📊 Scenario Analysis — Mega PWS in 11 block of Ganjam District **Scenario**: Deploy 1 × overtime (this Sunday) --- ### Projected Programme Impact ¦ Metric ¦ Current ¦ Projected ¦ Change ¦ ¦--------¦---------¦-----------¦--------¦ ¦ Forecast Delay ¦ 463d ¦ 408d ¦ **−55d** ¦ ¦ SPI ¦ 0.228 ¦ 0.240 ¦ +0.012 ¦ ¦ Productivity Rate ¦ Baseline ¦ +12.0% ¦ ✅ Enhanced ¦ ### Cost Impact - **Incremental Cost Estimate**: ₹15,000 - **Cost per Day Recovered**: ₹273 ### Risk & Implementation Considerations - Fatigue management protocols apply; overtime premium rates and quality oversight must be maintained. - Confirm impact on concurrent activities and interface obligations before deployment - Review against EOT entitlement basis if acceleration cost is to be claimed --- 💬 *Shall I log this scenario as an approved recovery action for the planning team?* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:37.319532
56 | tool | L5 | Simulate | Simulate — Extended hours with date range | sra_simulate | Simulate — Extended hours with date range | {'project_key': '101', 'resource_type': 'extended_hours', 'value_amount': 8, 'date_range': '2025-07-15 to 2025-07-20'} | PASS | All expected content present | 0.01 |  | ## 📊 Scenario Analysis — Mega PWS in 11 block of Ganjam District **Scenario**: Deploy 8 × extended_hours (2025-07-15 to 2025-07-20) --- ### Projected Programme Impact ¦ Metric ¦ Current ¦ Projected ¦ Change ¦ ¦--------¦---------¦-----------¦--------¦ ¦ Forecast Delay ¦ 463d ¦ 408d ¦ **−55d** ¦ ¦ SPI ¦ 0.228 ¦ 0.240 ¦ +0.012 ¦ ¦ Productivity Rate ¦ Baseline ¦ +12.0% ¦ ✅ Enhanced ¦ ### Cost Impact - **Incremental Cost Estimate**: ₹15,000 - **Cost per Day Recovered**: ₹273 ### Risk & Implementation Considerations - Fatigue management protocols apply; overtime premium rates and quality oversight must be maintained. - Confirm impact on concurrent activities and interface obligations before deployment - Review against EOT entitlement basis if acceleration cost is to be claimed --- 💬 *Shall I log this scenario as an approved recovery action for the planning team?* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:37.328539
57 | tool | L5 | Simulate | Simulate — 3 formwork gangs with date | sra_simulate | Simulate — 3 formwork gangs with date | {'project_key': '101', 'resource_type': 'formwork_gang', 'value_amount': 3, 'date_range': 'next fortnight'} | PASS | All expected content present | 0.01 |  | ## 📊 Scenario Analysis — Mega PWS in 11 block of Ganjam District **Scenario**: Deploy 3 × formwork_gang (next fortnight) --- ### Projected Programme Impact ¦ Metric ¦ Current ¦ Projected ¦ Change ¦ ¦--------¦---------¦-----------¦--------¦ ¦ Forecast Delay ¦ 463d ¦ 255d ¦ **−208d** ¦ ¦ SPI ¦ 0.228 ¦ 0.273 ¦ +0.045 ¦ ¦ Productivity Rate ¦ Baseline ¦ +45.0% ¦ ✅ Enhanced ¦ ### Cost Impact - **Incremental Cost Estimate**: ₹75,000 - **Cost per Day Recovered**: ₹361 ### Risk & Implementation Considerations - Coordination overhead with newly mobilised teams; site induction and productivity ramp-up period applies. - Confirm impact on concurrent activities and interface obligations before deployment - Review against EOT entitlement basis if acceleration cost is to be claimed --- 💬 *Shall I log this scenario as an approved recovery action for the planning team?* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:37.338061
58 | tool | L5 | Simulate | Simulate — Missing resource type (should prompt) | sra_simulate | Simulate — Missing resource type (should prompt) | {'project_key': '101'} | WARN | Expected keywords missing: ['Projected', 'Programme Impact'] | 0 |  | 📋 **Additional details required to run the scenario:** **Resource Type** — e.g. shuttering_gang / labor / equipment / overtime **Quantity** — e.g. 2 (gangs), 8 (overtime hours) 💡 Example: *What if I add 2 shuttering gangs to project 101?* |  | 2026-02-27T09:56:37.339059
59 | tool | L5 | Simulate | Simulate — Missing all params (should prompt) | sra_simulate | Simulate — Missing all params (should prompt) | {} | WARN | Expected keywords missing: ['Projected', 'Programme Impact'] | 0 |  | 📋 **Additional details required to run the scenario:** **Project** — which project? (Unable to retrieve project list) **Resource Type** — e.g. shuttering_gang / labor / equipment / overtime **Quantity** — e.g. 2 (gangs), 8 (overtime hours) 💡 Example: *What if I add 2 shuttering gangs to project 101?* |  | 2026-02-27T09:56:37.340059
60 | tool | L5 | Actions | Create Action — Approve Option 1 (resource augmentation) | sra_create_action | Create Action — Approve Option 1 (resource augmentation) | {'project_key': '101', 'action_choice': 'Approve Option 1 — Resource Augmentation', 'user_id': 'site_planner'} | PASS | All expected content present | 0.01 |  | ## ✅ Recovery Action Logged **Action ID**: `ACT-101-20260227095637` --- ### Action Record ¦ Field ¦ Detail ¦ ¦-------¦--------¦ ¦ Project ¦ Mega PWS in 11 block of Ganjam District (Key: 101) ¦ ¦ Action ¦ Approve Option 1 — Resource Augmentation ¦ ¦ Assigned To ¦ site_planner ¦ ¦ Status ¦ 🟡 **Open — Pending Execution** ¦ ¦ Logged ¦ 27 Feb 2026 09:56 ¦ ### Current Programme Context - PEI: 1.606 - SPI: 0.228 - Forecast Delay: 463d - EOT Exposure: 463d 💡 *This action has been logged for tracking. The assigned team member will receive notification for follow-through.* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:37.348048
61 | tool | L5 | Actions | Create Action — Approve Option 2 (schedule compression) | sra_create_action | Create Action — Approve Option 2 (schedule compression) | {'project_key': '101', 'action_choice': 'Approve Option 2 — Schedule Compression', 'user_id': 'planning_manager'} | PASS | All expected content present | 0.01 |  | ## ✅ Recovery Action Logged **Action ID**: `ACT-101-20260227095637` --- ### Action Record ¦ Field ¦ Detail ¦ ¦-------¦--------¦ ¦ Project ¦ Mega PWS in 11 block of Ganjam District (Key: 101) ¦ ¦ Action ¦ Approve Option 2 — Schedule Compression ¦ ¦ Assigned To ¦ planning_manager ¦ ¦ Status ¦ 🟡 **Open — Pending Execution** ¦ ¦ Logged ¦ 27 Feb 2026 09:56 ¦ ### Current Programme Context - PEI: 1.606 - SPI: 0.228 - Forecast Delay: 463d - EOT Exposure: 463d 💡 *This action has been logged for tracking. The assigned team member will receive notification for follow-through.* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:37.359049
62 | tool | L5 | Actions | Create Action — Fast-track decision | sra_create_action | Create Action — Fast-track decision | {'project_key': '101', 'action_choice': 'Approve Option 3 — Fast-Tracking', 'user_id': 'project_director'} | PASS | All expected content present | 0.01 |  | ## ✅ Recovery Action Logged **Action ID**: `ACT-101-20260227095637` --- ### Action Record ¦ Field ¦ Detail ¦ ¦-------¦--------¦ ¦ Project ¦ Mega PWS in 11 block of Ganjam District (Key: 101) ¦ ¦ Action ¦ Approve Option 3 — Fast-Tracking ¦ ¦ Assigned To ¦ project_director ¦ ¦ Status ¦ 🟡 **Open — Pending Execution** ¦ ¦ Logged ¦ 27 Feb 2026 09:56 ¦ ### Current Programme Context - PEI: 1.606 - SPI: 0.228 - Forecast Delay: 463d - EOT Exposure: 463d 💡 *This action has been logged for tracking. The assigned team member will receive notification for follow-through.* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:37.369532
63 | tool | L5 | Actions | Create Action — Raise alert to site planner | sra_create_action | Create Action — Raise alert to site planner | {'project_key': '101', 'action_choice': 'Raise alert to site planner — CP breach imminent', 'user_id': 'site_planner'} | PASS | All expected content present | 0.01 |  | ## ✅ Recovery Action Logged **Action ID**: `ACT-101-20260227095637` --- ### Action Record ¦ Field ¦ Detail ¦ ¦-------¦--------¦ ¦ Project ¦ Mega PWS in 11 block of Ganjam District (Key: 101) ¦ ¦ Action ¦ Raise alert to site planner — CP breach imminent ¦ ¦ Assigned To ¦ site_planner ¦ ¦ Status ¦ 🟡 **Open — Pending Execution** ¦ ¦ Logged ¦ 27 Feb 2026 09:56 ¦ ### Alert Dispatch - Alert type: **Schedule Recovery — Immediate Action Required** - Recipient: site_planner - Priority: **High** - Channels: 📧 Email + 📱 Push notification queued ### Current Programme Context - PEI: 1.606 - SPI: 0.228 - Forecast Delay: 463d - EOT Exposure: 463d 💡 *This action has been logged for tracking. The assigned team member will receive notification for follow-through.* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:37.376527
64 | tool | L5 | Actions | Create Action — Escalate to PM (no user_id) | sra_create_action | Create Action — Escalate to PM (no user_id) | {'project_key': '101', 'action_choice': 'Escalate workfront constraints to PM'} | PASS | All expected content present | 0.01 |  | ## ✅ Recovery Action Logged **Action ID**: `ACT-101-20260227095637` --- ### Action Record ¦ Field ¦ Detail ¦ ¦-------¦--------¦ ¦ Project ¦ Mega PWS in 11 block of Ganjam District (Key: 101) ¦ ¦ Action ¦ Escalate workfront constraints to PM ¦ ¦ Assigned To ¦ Unassigned — Pending Nomination ¦ ¦ Status ¦ 🟡 **Open — Pending Execution** ¦ ¦ Logged ¦ 27 Feb 2026 09:56 ¦ ### Alert Dispatch - Alert type: **Schedule Recovery — Immediate Action Required** - Recipient: Site Planner / Planning Manager - Priority: **High** - Channels: 📧 Email + 📱 Push notification queued ### Current Programme Context - PEI: 1.606 - SPI: 0.228 - Forecast Delay: 463d - EOT Exposure: 463d 💡 *This action has been logged for tracking. The assigned team member will receive notification for follow-through.* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:37.387534
65 | tool | L5 | Actions | Create Action — Notify procurement team | sra_create_action | Create Action — Notify procurement team | {'project_key': '101', 'action_choice': 'Notify procurement team of overdue PRC rules', 'user_id': 'procurement_lead'} | PASS | All expected content present | 0.01 |  | ## ✅ Recovery Action Logged **Action ID**: `ACT-101-20260227095637` --- ### Action Record ¦ Field ¦ Detail ¦ ¦-------¦--------¦ ¦ Project ¦ Mega PWS in 11 block of Ganjam District (Key: 101) ¦ ¦ Action ¦ Notify procurement team of overdue PRC rules ¦ ¦ Assigned To ¦ procurement_lead ¦ ¦ Status ¦ 🟡 **Open — Pending Execution** ¦ ¦ Logged ¦ 27 Feb 2026 09:56 ¦ ### Alert Dispatch - Alert type: **Schedule Recovery — Immediate Action Required** - Recipient: procurement_lead - Priority: **High** - Channels: 📧 Email + 📱 Push notification queued ### Current Programme Context - PEI: 1.606 - SPI: 0.228 - Forecast Delay: 463d - EOT Exposure: 463d 💡 *This action has been logged for tracking. The assigned team member will receive notification for follow-through.* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:37.396565
66 | tool | L5 | Actions | Create Action — No action choice (should prompt) | sra_create_action | Create Action — No action choice (should prompt) | {'project_key': '101'} | WARN | Expected keywords missing: ['Action Logged', 'ACT-', 'Recovery Action'] | 0 |  | 📋 **Additional details required to log the action:** **Action** — what should be logged? (e.g. 'Approve Option 2 — Schedule Compression') 💡 Example: *Log Option 1 for project 101 and assign to site planner* |  | 2026-02-27T09:56:37.397533
67 | tool | L5 | Actions | Create Action — No inputs at all | sra_create_action | Create Action — No inputs at all | {} | WARN | Expected keywords missing: ['Action Logged', 'ACT-', 'Recovery Action'] | 0 |  | 📋 **Additional details required to log the action:** **Project** — which project? (Unable to retrieve project list) **Action** — what should be logged? (e.g. 'Approve Option 2 — Schedule Compression') 💡 Example: *Log Option 1 for project 101 and assign to site planner* |  | 2026-02-27T09:56:37.398820

## LAYER_6_Govern
RUN ID | MODE | LAYER | CATEGORY | TEST NAME | TOOL NAME | INPUT SUMMARY | KWARGS | STATUS | VALIDATION NOTE | DURATION SEC | ERROR | TOOL OUTPUT | INSIGHT | TIMESTAMP
68 | tool | L6 | Accountability | Trace — All domains, all tasks | sra_accountability_trace | Trace — All domains, all tasks | {'project_key': '101'} | PASS | All expected content present | 2.79 |  | ## 📝 Accountability & Reporting Traceability — Mega PWS in 11 block of Ganjam District *Scope: All Domains ¦ Activity: All* ### Report-Flagged Tasks (Current Period) **11899** tasks are flagged for narrative reporting this period: ¦ Task ¦ Activity ¦ Domain ¦ Health RAG ¦ Accountability ¦ Narrative Label ¦ ¦------¦----------¦--------¦------------¦----------------¦----------------¦ ¦ Plastering ESR tank portion ¦ Plastering ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ PO ¦ PO ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Background ¦ ¦ PR ¦ PR ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Background ¦ ¦ Shuttering- upto FGL ¦ Shuttering ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Disposal of excess earth ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Plastering ¦ Plastering ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Stainless steel Ladder ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Shuttering - upto bottom slab ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ SS handrail ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Commissioning ¦ Commissioning ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Hard barrication ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Earthwork in Excavation in ordinary soil 1.5m - 3m ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Reinforcement - upto bottom slab ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ RCC - Vertical Side wall upto Roof slab ¦ RCC ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Shuttering - Vertical Side wall upto half height ¦ Shuttering ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Hard barrication ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ RCC - upto 100% staging height ¦ RCC ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Reinforcement - upto GL ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ SS handrail ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Shuttering - Vertical Side wall upto half height ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ### Delay Attribution Trace **14868** tasks have delay attribution records — relevant for variance reporting and potential EOT substantiation: ¦ Task ¦ Activity ¦ Domain ¦ Delay (d) ¦ Attribution ¦ Baseline Drift ¦ ¦------¦----------¦--------¦-----------¦-------------¦----------------¦ ¦ Plastering ESR tank portion ¦ Plastering ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Numeration and RC Detail of ESR of 80KL Capacity 10m Staging height at Pangidi for Scheme-I ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Numeration and RC Detail of ESR of 230KL Capacity 12m Staging height at Chingudighai for Scheme-I ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ PO ¦ PO ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ PR ¦ PR ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Shuttering- upto FGL ¦ Shuttering ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Disposal of excess earth ¦ — ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Plastering ¦ Plastering ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Stainless steel Ladder ¦ — ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Shuttering - upto bottom slab ¦ — ¦ CON ¦ 0d ¦ No Attributable Delay ¦ Significant Slip ? Over 1 Month ¦ ¦ SS handrail ¦ — ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Commissioning ¦ Commissioning ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Hard barrication ¦ — ¦ CON ¦ 0d ¦ No Attributable Delay ¦ Significant Slip ? Over 1 Month ¦ ¦ Earthwork in Excavation in ordinary soil 1.5m - 3m ¦ — ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Reinforcement - upto bottom slab ¦ — ¦ CON ¦ 0d ¦ No Attributable Delay ¦ Significant Slip ? Over 1 Month ¦ ### Recovery Candidate Tasks - **Crash Candidates** (eligible for resource augmentation): 823 - **Fast-Track Candidates** (eligible for concurrent working): 0 ### As-Built vs Baseline Duration (Completed Tasks) ¦ Task ¦ Baseline Duration ¦ As-Built Duration ¦ Duration Variance ¦ ¦------¦------------------¦-------------------¦------------------¦ ¦ Numeration and RC Detail of ESR of 80KL Capacity 10m Staging height at Pangidi for Scheme-I ¦ 40d ¦ 319d ¦ 🔴 279d ¦ ¦ Numeration and RC Detail of ESR of 230KL Capacity 12m Staging height at Chingudighai for Scheme-I ¦ 40d ¦ 148d ¦ 🔴 108d ¦ ¦ Numeration and RC Detail of GLSR of 425KL Capacity at Barida for Scheme-II ¦ 45d ¦ 286d ¦ 🔴 241d ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-316 KENDUPADARA-PR(ASKA) to Village (Ganjam Scheme-1) ¦ 46d ¦ 46d ¦ ✅ 0d ¦ ¦ Numeration and RC Detail of ESR of 210KL Capacity 16m Staging height at Debabhumi for Scheme-I ¦ 40d ¦ 162d ¦ 🔴 122d ¦ ¦ Numeration and RC Detail of Cascade aerator, Parshall flume, Distribution chamber and Flash mixer for Scheme-1 ¦ 45d ¦ 581d ¦ 🔴 536d ¦ ¦ Reinforcement - upto 100% staging height ¦ 10d ¦ 71d ¦ 🔴 61d ¦ ¦ Numeration and RC Detail of Filter Annex Building for Scheme-1 ¦ 40d ¦ 328d ¦ 🔴 288d ¦ ¦ Design Calculation of ESR of 325KL Capacity 16m Staging height at Saurachachina for Scheme-II ¦ 45d ¦ 290d ¦ 🔴 245d ¦ ¦ Hydraulic Flow Diagram for WTP ¦ 45d ¦ 302d ¦ 🔴 257d ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:40.188603
69 | tool | L6 | Accountability | Trace — Construction domain tasks | sra_accountability_trace | Trace — Construction domain tasks | {'project_key': '101', 'domain_code': 'CON'} | PASS | All expected content present | 3 |  | ## 📝 Accountability & Reporting Traceability — Mega PWS in 11 block of Ganjam District *Scope: CON ¦ Activity: All* ### Report-Flagged Tasks (Current Period) **10223** tasks are flagged for narrative reporting this period: ¦ Task ¦ Activity ¦ Domain ¦ Health RAG ¦ Accountability ¦ Narrative Label ¦ ¦------¦----------¦--------¦------------¦----------------¦----------------¦ ¦ Plastering ESR tank portion ¦ Plastering ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Shuttering- upto FGL ¦ Shuttering ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Disposal of excess earth ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Plastering ¦ Plastering ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Stainless steel Ladder ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Shuttering - upto bottom slab ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ SS handrail ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Commissioning ¦ Commissioning ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Hard barrication ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Earthwork in Excavation in ordinary soil 1.5m - 3m ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Reinforcement - upto bottom slab ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ RCC - Vertical Side wall upto Roof slab ¦ RCC ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Shuttering - Vertical Side wall upto half height ¦ Shuttering ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Hard barrication ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ RCC - upto 100% staging height ¦ RCC ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Reinforcement - upto GL ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ SS handrail ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Shuttering - Vertical Side wall upto half height ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Commissioning ¦ Commissioning ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ RCC - Vertical Side Roof slab ¦ RCC ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ### Delay Attribution Trace **10991** tasks have delay attribution records — relevant for variance reporting and potential EOT substantiation: ¦ Task ¦ Activity ¦ Domain ¦ Delay (d) ¦ Attribution ¦ Baseline Drift ¦ ¦------¦----------¦--------¦-----------¦-------------¦----------------¦ ¦ Plastering ESR tank portion ¦ Plastering ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Shuttering- upto FGL ¦ Shuttering ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Disposal of excess earth ¦ — ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Plastering ¦ Plastering ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Stainless steel Ladder ¦ — ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Shuttering - upto bottom slab ¦ — ¦ CON ¦ 0d ¦ No Attributable Delay ¦ Significant Slip ? Over 1 Month ¦ ¦ SS handrail ¦ — ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Commissioning ¦ Commissioning ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Hard barrication ¦ — ¦ CON ¦ 0d ¦ No Attributable Delay ¦ Significant Slip ? Over 1 Month ¦ ¦ Earthwork in Excavation in ordinary soil 1.5m - 3m ¦ — ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Reinforcement - upto bottom slab ¦ — ¦ CON ¦ 0d ¦ No Attributable Delay ¦ Significant Slip ? Over 1 Month ¦ ¦ RCC - Vertical Side wall upto Roof slab ¦ RCC ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Shuttering - Vertical Side wall upto half height ¦ Shuttering ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Hard barrication ¦ — ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ RCC - upto 100% staging height ¦ RCC ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ### As-Built vs Baseline Duration (Completed Tasks) ¦ Task ¦ Baseline Duration ¦ As-Built Duration ¦ Duration Variance ¦ ¦------¦------------------¦-------------------¦------------------¦ ¦ Reinforcement - upto 100% staging height ¦ 10d ¦ 71d ¦ 🔴 61d ¦ ¦ Reinforcement - upto GL ¦ 6d ¦ 146d ¦ 🔴 140d ¦ ¦ Shuttering - upto 100% staging height ¦ 12d ¦ 28d ¦ 🔴 16d ¦ ¦ RCC - upto bottom slab ¦ 5d ¦ 77d ¦ 🔴 72d ¦ ¦ Reinforcement - Vertical Side wall upto half height ¦ 4d ¦ 3d ¦ ✅ -1d ¦ ¦ Shuttering - upto GL ¦ 16d ¦ 65d ¦ 🔴 49d ¦ ¦ RCC - upto GL ¦ 7d ¦ 62d ¦ 🔴 55d ¦ ¦ Reinforcement - upto first floor roof slab ¦ 11d ¦ 74d ¦ 🔴 63d ¦ ¦ Shuttering - upto 100% staging height ¦ 16d ¦ 79d ¦ 🔴 63d ¦ ¦ RCC - upto GL ¦ 7d ¦ 221d ¦ 🔴 214d ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:43.191685
70 | tool | L6 | Accountability | Trace — Engineering domain tasks | sra_accountability_trace | Trace — Engineering domain tasks | {'project_key': '101', 'domain_code': 'ENG'} | PASS | All expected content present | 2.91 |  | ## 📝 Accountability & Reporting Traceability — Mega PWS in 11 block of Ganjam District *Scope: ENG ¦ Activity: All* ### Report-Flagged Tasks (Current Period) **549** tasks are flagged for narrative reporting this period: ¦ Task ¦ Activity ¦ Domain ¦ Health RAG ¦ Accountability ¦ Narrative Label ¦ ¦------¦----------¦--------¦------------¦----------------¦----------------¦ ¦ Design Calculation of Switchyard at IBPS-9 for Scheme-1 ¦ — ¦ ENG ¦ 🔴 Red ¦ Engineering Team ¦ Background ¦ ¦ Architectural Detail of Chlorine Building for Scheme-1 ¦ — ¦ ENG ¦ 🟡 Amber ¦ Engineering Team ¦ Background ¦ ¦ Numeration and RC Detail of Cascade aerator, Parshall flume, Distribution chamber and Flash mixer for Scheme-1 ¦ — ¦ ENG ¦ 🟢 Green ¦ Engineering Team ¦ Background ¦ ¦ P&ID Drawing for CWR cum Pump House at IBPS-1- (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 🟡 Amber ¦ Engineering Team ¦ Background ¦ ¦ Overall Single Line Diagram for IBPS 12 ¦ — ¦ ENG ¦ 🟡 Amber ¦ Engineering Team ¦ Background ¦ ¦ Design Calculation of Intermediate Sump-1 for Scheme-1 ¦ — ¦ ENG ¦ 🟡 Amber ¦ Engineering Team ¦ Background ¦ ¦ Instrument list for IBPS-5 ¦ — ¦ ENG ¦ 🟡 Amber ¦ Engineering Team ¦ Background ¦ ¦ Lighting Layout for Intake ¦ — ¦ ENG ¦ 🔴 Red ¦ Engineering Team ¦ Critical Exception ¦ ¦ 33/11 kV Switchyard Layout for IBPS 1 ¦ — ¦ ENG ¦ 🟡 Amber ¦ Engineering Team ¦ Background ¦ ¦ Design Calculation of Switchyard at IBPS-1 for Scheme-1 ¦ — ¦ ENG ¦ 🔴 Red ¦ Engineering Team ¦ Background ¦ ¦ Surge Analysis Report for Clear water Pumping main from IBPS-09 (PM-2) to OHTs Ganjam WSS (Scheme-1) ¦ — ¦ ENG ¦ 🟡 Amber ¦ Engineering Team ¦ Background ¦ ¦ Control And Interlock Details for IBPS-4 ¦ — ¦ ENG ¦ 🟡 Amber ¦ Engineering Team ¦ Background ¦ ¦ Numeration and RC Detail of Intermediate Pump House-7 for Scheme-1 ¦ — ¦ ENG ¦ 🟡 Amber ¦ Engineering Team ¦ Background ¦ ¦ Numeration and RC Detail of ESR of 325KL Capacity 20m Staging height at Betarsingi for Scheme-I ¦ — ¦ ENG ¦ 🟡 Amber ¦ Engineering Team ¦ Background ¦ ¦ Earthing Layout for IBPS 9 ¦ — ¦ ENG ¦ 🟡 Amber ¦ Engineering Team ¦ Background ¦ ¦ Design Calculation of Valve Chambers for Scheme-2 ¦ — ¦ ENG ¦ 🔴 Red ¦ Engineering Team ¦ Critical Exception ¦ ¦ Numeration and RC Detail of Intermediate Sump-3 for Scheme-1 ¦ — ¦ ENG ¦ 🟡 Amber ¦ Engineering Team ¦ Background ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-179 AMBILLIJHARA-PR (GAN) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 🟡 Amber ¦ Engineering Team ¦ Background ¦ ¦ Instrumentation Cable schedule for IBPS-1 ¦ — ¦ ENG ¦ 🟡 Amber ¦ Engineering Team ¦ Background ¦ ¦ DG Sizing calculation Intake, WTP ¦ — ¦ ENG ¦ 🟡 Amber ¦ Engineering Team ¦ Background ¦ ### Delay Attribution Trace **2694** tasks have delay attribution records — relevant for variance reporting and potential EOT substantiation: ¦ Task ¦ Activity ¦ Domain ¦ Delay (d) ¦ Attribution ¦ Baseline Drift ¦ ¦------¦----------¦--------¦-----------¦-------------¦----------------¦ ¦ Numeration and RC Detail of ESR of 80KL Capacity 10m Staging height at Pangidi for Scheme-I ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Numeration and RC Detail of ESR of 230KL Capacity 12m Staging height at Chingudighai for Scheme-I ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Numeration and RC Detail of GLSR of 425KL Capacity at Barida for Scheme-II ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Design Calculation of Switchyard at IBPS-9 for Scheme-1 ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-316 KENDUPADARA-PR(ASKA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Architectural Detail of Chlorine Building for Scheme-1 ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Design Calculation of ESR of 60KL Capacity 10m Staging height at Khadabhaga for Scheme-I ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Numeration and RC Detail of ESR of 210KL Capacity 16m Staging height at Debabhumi for Scheme-I ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Numeration and RC Detail of Cascade aerator, Parshall flume, Distribution chamber and Flash mixer for Scheme-1 ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ P&ID Drawing for CWR cum Pump House at IBPS-1- (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-115 BALLIPADAR-EX (BUGUDA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Numeration and RC Detail of Filter Annex Building for Scheme-1 ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Architectural Detail of Filter House & Filter Annex Building for Scheme-2 ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Overall Single Line Diagram for IBPS 12 ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Design Calculation of ESR of 325KL Capacity 16m Staging height at Saurachachina for Scheme-II ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ### Recovery Candidate Tasks - **Crash Candidates** (eligible for resource augmentation): 475 - **Fast-Track Candidates** (eligible for concurrent working): 0 ### As-Built vs Baseline Duration (Completed Tasks) ¦ Task ¦ Baseline Duration ¦ As-Built Duration ¦ Duration Variance ¦ ¦------¦------------------¦-------------------¦------------------¦ ¦ Numeration and RC Detail of ESR of 80KL Capacity 10m Staging height at Pangidi for Scheme-I ¦ 40d ¦ 319d ¦ 🔴 279d ¦ ¦ Numeration and RC Detail of ESR of 230KL Capacity 12m Staging height at Chingudighai for Scheme-I ¦ 40d ¦ 148d ¦ 🔴 108d ¦ ¦ Numeration and RC Detail of GLSR of 425KL Capacity at Barida [... truncated at 6000 chars] |  | 2026-02-27T09:56:46.098911
71 | tool | L6 | Accountability | Trace — Procurement domain tasks | sra_accountability_trace | Trace — Procurement domain tasks | {'project_key': '101', 'domain_code': 'PRC'} | PASS | All expected content present | 3.42 |  | ## 📝 Accountability & Reporting Traceability — Mega PWS in 11 block of Ganjam District *Scope: PRC ¦ Activity: All* ### Report-Flagged Tasks (Current Period) **1127** tasks are flagged for narrative reporting this period: ¦ Task ¦ Activity ¦ Domain ¦ Health RAG ¦ Accountability ¦ Narrative Label ¦ ¦------¦----------¦--------¦------------¦----------------¦----------------¦ ¦ PO ¦ PO ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Background ¦ ¦ PR ¦ PR ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Background ¦ ¦ PO ¦ PO ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Background ¦ ¦ PO ¦ PO ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Background ¦ ¦ PR ¦ PR ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Background ¦ ¦ MRN ¦ MRN ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Background ¦ ¦ MFC ¦ MFC ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Critical Exception ¦ ¦ PR ¦ PR ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Background ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Critical Exception ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Critical Exception ¦ ¦ Inspection ¦ INS ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Background ¦ ¦ MRN ¦ MRN ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Critical Exception ¦ ¦ MFC ¦ MFC ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Background ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Background ¦ ¦ PR ¦ PR ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Critical Exception ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Critical Exception ¦ ¦ PO ¦ PO ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Critical Exception ¦ ¦ MFC ¦ MFC ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Background ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Critical Exception ¦ ¦ PR ¦ PR ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Critical Exception ¦ ### Delay Attribution Trace **1183** tasks have delay attribution records — relevant for variance reporting and potential EOT substantiation: ¦ Task ¦ Activity ¦ Domain ¦ Delay (d) ¦ Attribution ¦ Baseline Drift ¦ ¦------¦----------¦--------¦-----------¦-------------¦----------------¦ ¦ PO ¦ PO ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ PR ¦ PR ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ PO ¦ PO ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ PO ¦ PO ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ PR ¦ PR ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ MRN ¦ MRN ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ MFC ¦ MFC ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ PR ¦ PR ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Inspection ¦ INS ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Inspection ¦ INS ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ MRN ¦ MRN ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ MFC ¦ MFC ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ### Recovery Candidate Tasks - **Crash Candidates** (eligible for resource augmentation): 348 - **Fast-Track Candidates** (eligible for concurrent working): 0 ### As-Built vs Baseline Duration (Completed Tasks) ¦ Task ¦ Baseline Duration ¦ As-Built Duration ¦ Duration Variance ¦ ¦------¦------------------¦-------------------¦------------------¦ ¦ PO ¦ 134d ¦ 333d ¦ 🔴 199d ¦ ¦ PR ¦ 134d ¦ 344d ¦ 🔴 210d ¦ ¦ Dispatch Clearance ¦ 135d ¦ 388d ¦ 🔴 253d ¦ ¦ Dispatch Clearance ¦ 135d ¦ 409d ¦ 🔴 274d ¦ ¦ MFC ¦ 134d ¦ 118d ¦ ✅ -16d ¦ ¦ Inspection ¦ 134d ¦ 118d ¦ ✅ -16d ¦ ¦ MRN ¦ 134d ¦ 515d ¦ 🔴 381d ¦ ¦ MRN ¦ 134d ¦ 272d ¦ 🔴 138d ¦ ¦ Post Order & QAP Approval ¦ 135d ¦ 413d ¦ 🔴 278d ¦ ¦ PR ¦ 134d ¦ 391d ¦ 🔴 257d ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:49.513911
72 | tool | L6 | Accountability | Trace — No project key | sra_accountability_trace | Trace — No project key | {} | WARN | Expected keywords missing: ['Report', 'Task'] | 0 |  | 📋 **Specify the project for accountability tracing.** (Unable to retrieve project list) |  | 2026-02-27T09:56:49.514911
73 | tool | L6 | Formula | Formula — Explain SPI (with live project context) | sra_explain_formula | Formula — Explain SPI (with live project context) | {'project_key': '101', 'metric': 'SPI'} | WARN | Expected keywords missing: ['Definition'] | 0.01 |  | ## 📐 Schedule Metric Reference Guide *Live context: Mega PWS in 11 block of Ganjam District (Key: 101)* --- ### 📈 SPI — Schedule Performance Index **Formula**: `SPI = Earned Progress % / Planned Progress %` Measures whether work is being executed at the rate the programme demands. An SPI of 1.0 means the project is earning exactly what was planned. Below 1.0 indicates the execution rate is lagging — the gap compounds over time on a critical path. ¦ Value ¦ Signal ¦ Interpretation ¦ ¦-------¦--------¦----------------¦ ¦ SPI > 1.0 ¦ 🟢 Ahead of Programme ¦ Execution exceeds plan ¦ ¦ SPI = 1.0 ¦ ✅ On Programme ¦ Performance exactly as planned ¦ ¦ SPI < 1.0 ¦ 🔴 Behind Programme ¦ Execution rate below plan ¦ *Current SPI: **0.228** — Behind by 77.2%* --- 💡 *Ask about a specific metric for a live calculation against your project — e.g. 'Explain SPI for project 101'* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:49.523085
74 | tool | L6 | Formula | Formula — Explain PEI (with live project context) | sra_explain_formula | Formula — Explain PEI (with live project context) | {'project_key': '101', 'metric': 'PEI'} | WARN | Expected keywords missing: ['Definition'] | 0.01 |  | ## 📐 Schedule Metric Reference Guide *Live context: Mega PWS in 11 block of Ganjam District (Key: 101)* --- ### 📊 PEI — Project Execution Index **Formula**: `PEI = Forecast Duration / Planned Duration` Measures whether the overall programme duration is expanding beyond its original plan. A PEI above 1.0 means the project is consuming more time than the baseline allocated — a direct signal of schedule overrun risk even if individual activities appear on track. ¦ Value ¦ Signal ¦ Interpretation ¦ ¦-------¦--------¦----------------¦ ¦ PEI < 1.0 ¦ 🟢 Duration Efficient ¦ Forecast shorter than baseline ¦ ¦ PEI = 1.0 ¦ ✅ On Programme ¦ Forecast equals baseline duration ¦ ¦ PEI > 1.0 ¦ 🔴 Duration Overrun ¦ Forecast exceeds baseline ¦ *Current PEI: **1.606** — 60.6% over baseline duration* --- 💡 *Ask about a specific metric for a live calculation against your project — e.g. 'Explain SPI for project 101'* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:49.533054
75 | tool | L6 | Formula | Formula — Explain LAC compliance | sra_explain_formula | Formula — Explain LAC compliance | {'project_key': '101', 'metric': 'LAC'} | WARN | Expected keywords missing: ['Definition', 'Interpretation'] | 0.01 |  | ## 📐 Schedule Metric Reference Guide *Live context: Mega PWS in 11 block of Ganjam District (Key: 101)* --- ### 🎯 LAC — Look-Ahead Compliance **Formula**: `LAC % = (Rules Completed On Time / Total Rules Planned) × 100` LAC is the construction industry's primary execution reliability metric. It measures the percentage of short-term commitments (rules) that were fulfilled within the look-ahead window. A declining LAC is an early warning of execution discipline breakdown — it typically precedes SPI deterioration by 2–4 weeks. ¦ Value ¦ Signal ¦ ¦-------¦--------¦ ¦ ≥ 80% ¦ ✅ Strong execution reliability ¦ ¦ 60–79% ¦ 🟡 Execution gap — root cause review warranted ¦ ¦ < 60% ¦ 🔴 Systemic planning/execution disconnect — escalation required ¦ --- 💡 *Ask about a specific metric for a live calculation against your project — e.g. 'Explain SPI for project 101'* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:49.546845
76 | tool | L6 | Formula | Formula — Explain Float | sra_explain_formula | Formula — Explain Float | {'project_key': '101', 'metric': 'float'} | WARN | Expected keywords missing: ['Formula', 'Interpretation'] | 0.01 |  | ## 📐 Schedule Metric Reference Guide *Live context: Mega PWS in 11 block of Ganjam District (Key: 101)* --- ### ⏳ Total Float **Definition**: The maximum amount of time a task can be delayed without delaying the project completion date. Float is the scheduling buffer in the network. Zero float means any delay to that task directly extends the project end date (Critical Path). Negative float means the task is already causing a projected overrun. Near-critical tasks (≤5 days float) require active monitoring as they can migrate onto the critical path with a single disruption event. ¦ Float Band ¦ Classification ¦ ¦-----------¦----------------¦ ¦ < 0 ¦ 🔴 Overrun — already impacting completion ¦ ¦ = 0 ¦ 🔴 Critical Path ¦ ¦ 1–5d ¦ 🟡 Near-Critical Watch ¦ ¦ > 5d ¦ 🟢 Schedule Buffer Available ¦ --- 💡 *Ask about a specific metric for a live calculation against your project — e.g. 'Explain SPI for project 101'* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:49.559561
77 | tool | L6 | Formula | Formula — Explain EOT | sra_explain_formula | Formula — Explain EOT | {'project_key': '101', 'metric': 'EOT'} | WARN | Expected keywords missing: ['Formula', 'Interpretation'] | 0.01 |  | ## 📐 Schedule Metric Reference Guide *Live context: Mega PWS in 11 block of Ganjam District (Key: 101)* --- ### ⚖️ EOT — Extension of Time **Definition**: A contractual entitlement to extend the project completion date without penalty, typically granted when delay events arise from Employer risk or force majeure events. **EOT Exposure** represents the number of days the current forecast completion exceeds the contractual date. EOT Eligibility assesses whether the delay has a contractual basis for an extension claim. Unsubstantiated EOT exposure translates directly into Liquidated Damages (LD) liability. EOT forensic analysis requires establishing: the delay event timeline, its impact on the critical path at the time of occurrence, concurrent delay assessment, and the causal chain from event to completion date shift. --- 💡 *Ask about a specific metric for a live calculation against your project — e.g. 'Explain SPI for project 101'* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:49.570439
78 | tool | L6 | Formula | Formula — Explain ALL metrics | sra_explain_formula | Formula — Explain ALL metrics | {'project_key': '101', 'metric': 'all'} | PASS | All expected content present | 0.01 |  | ## 📐 Schedule Metric Reference Guide *Live context: Mega PWS in 11 block of Ganjam District (Key: 101)* --- ### 📈 SPI — Schedule Performance Index **Formula**: `SPI = Earned Progress % / Planned Progress %` Measures whether work is being executed at the rate the programme demands. An SPI of 1.0 means the project is earning exactly what was planned. Below 1.0 indicates the execution rate is lagging — the gap compounds over time on a critical path. ¦ Value ¦ Signal ¦ Interpretation ¦ ¦-------¦--------¦----------------¦ ¦ SPI > 1.0 ¦ 🟢 Ahead of Programme ¦ Execution exceeds plan ¦ ¦ SPI = 1.0 ¦ ✅ On Programme ¦ Performance exactly as planned ¦ ¦ SPI < 1.0 ¦ 🔴 Behind Programme ¦ Execution rate below plan ¦ *Current SPI: **0.228** — Behind by 77.2%* ### 📊 PEI — Project Execution Index **Formula**: `PEI = Forecast Duration / Planned Duration` Measures whether the overall programme duration is expanding beyond its original plan. A PEI above 1.0 means the project is consuming more time than the baseline allocated — a direct signal of schedule overrun risk even if individual activities appear on track. ¦ Value ¦ Signal ¦ Interpretation ¦ ¦-------¦--------¦----------------¦ ¦ PEI < 1.0 ¦ 🟢 Duration Efficient ¦ Forecast shorter than baseline ¦ ¦ PEI = 1.0 ¦ ✅ On Programme ¦ Forecast equals baseline duration ¦ ¦ PEI > 1.0 ¦ 🔴 Duration Overrun ¦ Forecast exceeds baseline ¦ *Current PEI: **1.606** — 60.6% over baseline duration* ### 🎯 LAC — Look-Ahead Compliance **Formula**: `LAC % = (Rules Completed On Time / Total Rules Planned) × 100` LAC is the construction industry's primary execution reliability metric. It measures the percentage of short-term commitments (rules) that were fulfilled within the look-ahead window. A declining LAC is an early warning of execution discipline breakdown — it typically precedes SPI deterioration by 2–4 weeks. ¦ Value ¦ Signal ¦ ¦-------¦--------¦ ¦ ≥ 80% ¦ ✅ Strong execution reliability ¦ ¦ 60–79% ¦ 🟡 Execution gap — root cause review warranted ¦ ¦ < 60% ¦ 🔴 Systemic planning/execution disconnect — escalation required ¦ ### ⏳ Total Float **Definition**: The maximum amount of time a task can be delayed without delaying the project completion date. Float is the scheduling buffer in the network. Zero float means any delay to that task directly extends the project end date (Critical Path). Negative float means the task is already causing a projected overrun. Near-critical tasks (≤5 days float) require active monitoring as they can migrate onto the critical path with a single disruption event. ¦ Float Band ¦ Classification ¦ ¦-----------¦----------------¦ ¦ < 0 ¦ 🔴 Overrun — already impacting completion ¦ ¦ = 0 ¦ 🔴 Critical Path ¦ ¦ 1–5d ¦ 🟡 Near-Critical Watch ¦ ¦ > 5d ¦ 🟢 Schedule Buffer Available ¦ ### ⚖️ EOT — Extension of Time **Definition**: A contractual entitlement to extend the project completion date without penalty, typically granted when delay events arise from Employer risk or force majeure events. **EOT Exposure** represents the number of days the current forecast completion exceeds the contractual date. EOT Eligibility assesses whether the delay has a contractual basis for an extension claim. Unsubstantiated EOT exposure translates directly into Liquidated Damages (LD) liability. EOT forensic analysis requires establishing: the delay event timeline, its impact on the critical path at the time of occurrence, concurrent delay assessment, and the causal chain from event to completion date shift. --- 💡 *Ask about a specific metric for a live calculation against your project — e.g. 'Explain SPI for project 101'* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:49.581691
79 | tool | L6 | Formula | Formula — No project key, SPI only | sra_explain_formula | Formula — No project key, SPI only | {'metric': 'SPI'} | WARN | Expected keywords missing: ['Definition'] | 0 |  | ## 📐 Schedule Metric Reference Guide ### 📈 SPI — Schedule Performance Index **Formula**: `SPI = Earned Progress % / Planned Progress %` Measures whether work is being executed at the rate the programme demands. An SPI of 1.0 means the project is earning exactly what was planned. Below 1.0 indicates the execution rate is lagging — the gap compounds over time on a critical path. ¦ Value ¦ Signal ¦ Interpretation ¦ ¦-------¦--------¦----------------¦ ¦ SPI > 1.0 ¦ 🟢 Ahead of Programme ¦ Execution exceeds plan ¦ ¦ SPI = 1.0 ¦ ✅ On Programme ¦ Performance exactly as planned ¦ ¦ SPI < 1.0 ¦ 🔴 Behind Programme ¦ Execution rate below plan ¦ --- 💡 *Ask about a specific metric for a live calculation against your project — e.g. 'Explain SPI for project 101'* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:49.582690
80 | tool | L6 | Formula | Formula — No inputs at all | sra_explain_formula | Formula — No inputs at all | {} | PASS | All expected content present | 0 |  | ## 📐 Schedule Metric Reference Guide ### 📈 SPI — Schedule Performance Index **Formula**: `SPI = Earned Progress % / Planned Progress %` Measures whether work is being executed at the rate the programme demands. An SPI of 1.0 means the project is earning exactly what was planned. Below 1.0 indicates the execution rate is lagging — the gap compounds over time on a critical path. ¦ Value ¦ Signal ¦ Interpretation ¦ ¦-------¦--------¦----------------¦ ¦ SPI > 1.0 ¦ 🟢 Ahead of Programme ¦ Execution exceeds plan ¦ ¦ SPI = 1.0 ¦ ✅ On Programme ¦ Performance exactly as planned ¦ ¦ SPI < 1.0 ¦ 🔴 Behind Programme ¦ Execution rate below plan ¦ ### 📊 PEI — Project Execution Index **Formula**: `PEI = Forecast Duration / Planned Duration` Measures whether the overall programme duration is expanding beyond its original plan. A PEI above 1.0 means the project is consuming more time than the baseline allocated — a direct signal of schedule overrun risk even if individual activities appear on track. ¦ Value ¦ Signal ¦ Interpretation ¦ ¦-------¦--------¦----------------¦ ¦ PEI < 1.0 ¦ 🟢 Duration Efficient ¦ Forecast shorter than baseline ¦ ¦ PEI = 1.0 ¦ ✅ On Programme ¦ Forecast equals baseline duration ¦ ¦ PEI > 1.0 ¦ 🔴 Duration Overrun ¦ Forecast exceeds baseline ¦ ### 🎯 LAC — Look-Ahead Compliance **Formula**: `LAC % = (Rules Completed On Time / Total Rules Planned) × 100` LAC is the construction industry's primary execution reliability metric. It measures the percentage of short-term commitments (rules) that were fulfilled within the look-ahead window. A declining LAC is an early warning of execution discipline breakdown — it typically precedes SPI deterioration by 2–4 weeks. ¦ Value ¦ Signal ¦ ¦-------¦--------¦ ¦ ≥ 80% ¦ ✅ Strong execution reliability ¦ ¦ 60–79% ¦ 🟡 Execution gap — root cause review warranted ¦ ¦ < 60% ¦ 🔴 Systemic planning/execution disconnect — escalation required ¦ ### ⏳ Total Float **Definition**: The maximum amount of time a task can be delayed without delaying the project completion date. Float is the scheduling buffer in the network. Zero float means any delay to that task directly extends the project end date (Critical Path). Negative float means the task is already causing a projected overrun. Near-critical tasks (≤5 days float) require active monitoring as they can migrate onto the critical path with a single disruption event. ¦ Float Band ¦ Classification ¦ ¦-----------¦----------------¦ ¦ < 0 ¦ 🔴 Overrun — already impacting completion ¦ ¦ = 0 ¦ 🔴 Critical Path ¦ ¦ 1–5d ¦ 🟡 Near-Critical Watch ¦ ¦ > 5d ¦ 🟢 Schedule Buffer Available ¦ ### ⚖️ EOT — Extension of Time **Definition**: A contractual entitlement to extend the project completion date without penalty, typically granted when delay events arise from Employer risk or force majeure events. **EOT Exposure** represents the number of days the current forecast completion exceeds the contractual date. EOT Eligibility assesses whether the delay has a contractual basis for an extension claim. Unsubstantiated EOT exposure translates directly into Liquidated Damages (LD) liability. EOT forensic analysis requires establishing: the delay event timeline, its impact on the critical path at the time of occurrence, concurrent delay assessment, and the causal chain from event to completion date shift. --- 💡 *Ask about a specific metric for a live calculation against your project — e.g. 'Explain SPI for project 101'* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:49.582690

## SQL_AGENT
RUN ID | MODE | LAYER | CATEGORY | TEST NAME | TOOL NAME | INPUT SUMMARY | KWARGS | STATUS | VALIDATION NOTE | DURATION SEC | ERROR | TOOL OUTPUT | INSIGHT | TIMESTAMP
81 | tool | L0 | SQL-NL | SQL — NL: List project summary / portfolio view | sra_sql_agent | SQL — NL: List project summary / portfolio view | {'question': 'List all projects with SPI, health score and delay', 'project_key': '101'} | WARN | Expected keywords missing: ['Activity', 'Task'] | 0.09 |  | ## ⚠️ Query Syntax Issue The database reported a syntax or access error: > column "project_key" does not exist HINT: Perhaps you meant to reference the column "tbl_01_project_summary.Project_Key". **Query attempted:** ```sql SELECT Project_Key, Project_Name, Project_Location, SPI_Overall, Project_Execution_Index, Max_Forecast_Delay_Days_Overall, EOT_Exposure_Days, Schedule_Health_RAG, Schedule_Health_Score, Data_Freshness_Label FROM tbl_01_project_summary WHERE Project_Key = 101 ORDER BY Max_Forecast_Delay_Days_Overall DESC NULLS LAST LIMIT 500 ``` Please review the column names and table references. Column names follow the `PascalCase_With_Underscores` convention. |  | 2026-02-27T09:56:49.673033
82 | tool | L0 | SQL-NL | SQL — NL: Critical tasks on CP (project scope) | sra_sql_agent | SQL — NL: Critical tasks on CP (project scope) | {'question': 'Show all critical tasks in project', 'project_key': '101'} | PASS | All expected content present | 0.14 |  | ## ⚠️ Query Syntax Issue The database reported a syntax or access error: > column "task_key" does not exist HINT: Perhaps you meant to reference the column "tbl_03_project_task.Task_Key". **Query attempted:** ```sql SELECT Task_Key, Task_Name, Activity_Code, Domain_Code, Task_Status, Total_Float_Days, Forecast_Delay_Days, Task_Health_RAG, Slip_Days FROM tbl_03_project_task WHERE Project_Key = 101 AND Is_Critical_Wrench = TRUE ORDER BY Total_Float_Days ASC LIMIT 500 ``` Please review the column names and table references. Column names follow the `PascalCase_With_Underscores` convention. |  | 2026-02-27T09:56:49.810620
83 | tool | L0 | SQL-NL | SQL — NL: Delayed tasks with risk tier | sra_sql_agent | SQL — NL: Delayed tasks with risk tier | {'question': 'Show delayed tasks with risk tier', 'project_key': '101'} | PASS | All expected content present | 0.08 |  | ## ⚠️ Query Syntax Issue The database reported a syntax or access error: > column "task_key" does not exist HINT: Perhaps you meant to reference the column "tbl_03_project_task.Task_Key". **Query attempted:** ```sql SELECT Task_Key, Task_Name, Activity_Code, Domain_Code, Task_Status, Forecast_Delay_Days, Slip_Days, Total_Float_Days, Task_Risk_Tier FROM tbl_03_project_task WHERE Project_Key = 101 AND Forecast_Delay_Days > 0 ORDER BY Forecast_Delay_Days DESC LIMIT 500 ``` Please review the column names and table references. Column names follow the `PascalCase_With_Underscores` convention. |  | 2026-02-27T09:56:49.892891
84 | tool | L0 | SQL-NL | SQL — NL: Float distribution across tasks | sra_sql_agent | SQL — NL: Float distribution across tasks | {'question': 'Float distribution for all tasks', 'project_key': '101'} | PASS | All expected content present | 0.12 |  | ## ⚠️ Query Syntax Issue The database reported a syntax or access error: > column "task_key" does not exist HINT: Perhaps you meant to reference the column "tbl_03_project_task.Task_Key". **Query attempted:** ```sql SELECT Task_Key, Task_Name, Activity_Code, Domain_Code, Total_Float_Days, Float_Health_Status, Float_RAG_Label, Is_Critical_Wrench, Float_Erosion_Flag FROM tbl_03_project_task WHERE Project_Key = 101 ORDER BY Total_Float_Days ASC LIMIT 500 ``` Please review the column names and table references. Column names follow the `PascalCase_With_Underscores` convention. |  | 2026-02-27T09:56:50.012125
85 | tool | L0 | SQL-NL | SQL — NL: 2-week look-ahead tasks | sra_sql_agent | SQL — NL: 2-week look-ahead tasks | {'question': 'Show tasks in the 2 week look ahead window', 'project_key': '101'} | PASS | All expected content present | 0.09 |  | ## ⚠️ Query Syntax Issue The database reported a syntax or access error: > column "task_key" does not exist HINT: Perhaps you meant to reference the column "tbl_03_project_task.Task_Key". **Query attempted:** ```sql SELECT Task_Key, Task_Name, Activity_Code, Domain_Code, Forecast_Start_Date, Forecast_Finish_Date, Is_WorkFront_Available, LookAhead_Priority_Score, Total_Float_Days FROM tbl_03_project_task WHERE Project_Key = 101 AND In_2W_Start_Window IS NOT NULL ORDER BY LookAhead_Priority_Score DESC LIMIT 500 ``` Please review the column names and table references. Column names follow the `PascalCase_With_Underscores` convention. |  | 2026-02-27T09:56:50.101965
86 | tool | L0 | SQL-NL | SQL — NL: Milestones and their status | sra_sql_agent | SQL — NL: Milestones and their status | {'question': 'List all milestones and their status', 'project_key': '101'} | PASS | All expected content present | 0 |  | ## 🔍 Ad-Hoc Query — Clarification Required The question **"List all milestones and their status"** falls outside the coverage of the structured schedule intelligence tools, and could not be automatically translated into a targeted database query. To proceed, please provide one of the following: 1. **A more specific question** — include the grain (task/activity/project), domain (ENG/PRC/CON), and the specific metrics or conditions you need. 2. **A raw SQL SELECT** — pass it via the `raw_sql` parameter. ### Available Tables ¦ Table ¦ Grain ¦ Key Columns ¦ ¦-------¦-------¦-------------¦ ¦ `tbl_01_project_summary` ¦ One row per project ¦ Project_Key, SPI_Overall, PEI, EOT_Exposure_Days, Schedule_Health_RAG ¦ ¦ `tbl_02_project_activity` ¦ One row per activity ¦ Activity_Code, Domain_Code, Forecast_Delay_Days, Float_Days, LAC_Pct ¦ ¦ `tbl_03_project_task` ¦ One row per task ¦ Task_Key, Activity_Code, Float_Days, Is_Critical_Wrench, Task_Health_RAG ¦ 💡 *Example: "Show all Construction tasks in project 101 with negative float" or "List activities with CON_LAC_Week_Pct below 60% for project 101"* |  | 2026-02-27T09:56:50.101965
87 | tool | L0 | SQL-NL | SQL — NL: Delayed activities with SPI | sra_sql_agent | SQL — NL: Delayed activities with SPI | {'question': 'Which activities have slipped and what is their SPI', 'project_key': '101'} | WARN | Expected keywords missing: ['Task'] | 0.08 |  | ## ⚠️ Query Syntax Issue The database reported a syntax or access error: > column "activity_code" does not exist HINT: Perhaps you meant to reference the column "tbl_02_project_activity.Activity_Code". **Query attempted:** ```sql SELECT Activity_Code, Activity_Description, Domain_Code, Activity_Status, Forecast_Delay_Days, Slip_Days, SPI_RAG_Label, Delay_Magnitude_Label, Is_Critical_Wrench FROM tbl_02_project_activity WHERE Project_Key = 101 AND Forecast_Delay_Days > 0 ORDER BY Forecast_Delay_Days DESC LIMIT 500 ``` Please review the column names and table references. Column names follow the `PascalCase_With_Underscores` convention. |  | 2026-02-27T09:56:50.177537
88 | tool | L0 | SQL-NL | SQL — NL: Workfront-constrained activities | sra_sql_agent | SQL — NL: Workfront-constrained activities | {'question': 'Activities with low workfront readiness', 'project_key': '101'} | WARN | Expected keywords missing: ['Task'] | 0.08 |  | ## ⚠️ Query Syntax Issue The database reported a syntax or access error: > column "activity_code" does not exist HINT: Perhaps you meant to reference the column "tbl_02_project_activity.Activity_Code". **Query attempted:** ```sql SELECT Activity_Code, Activity_Description, Domain_Code, Workfront_Ready_Pct, Workfront_Gap_Count, CAD_Breach_Flag, Is_Critical_Wrench, Activity_Status FROM tbl_02_project_activity WHERE Project_Key = 101 AND Workfront_Ready_Pct < 70 ORDER BY Workfront_Ready_Pct ASC LIMIT 500 ``` Please review the column names and table references. Column names follow the `PascalCase_With_Underscores` convention. |  | 2026-02-27T09:56:50.255997
89 | tool | L0 | SQL-NL | SQL — NL: LAC compliance per activity | sra_sql_agent | SQL — NL: LAC compliance per activity | {'question': 'Show LAC compliance per activity', 'project_key': '101'} | WARN | Expected keywords missing: ['Task'] | 0.14 |  | ## ⚠️ Query Syntax Issue The database reported a syntax or access error: > column "activity_code" does not exist HINT: Perhaps you meant to reference the column "tbl_02_project_activity.Activity_Code". **Query attempted:** ```sql SELECT Activity_Code, Activity_Description, Domain_Code, Activity_Status, Planned_Progress_Pct, Actual_Progress_Pct, Forecast_Delay_Days, Total_Float_Days, Activity_Health_RAG FROM tbl_02_project_activity WHERE Project_Key = 101 ORDER BY Forecast_Delay_Days DESC NULLS LAST LIMIT 500 ``` Please review the column names and table references. Column names follow the `PascalCase_With_Underscores` convention. |  | 2026-02-27T09:56:50.398189
90 | tool | L0 | SQL-NL | SQL — NL: Critical activities (CP focus) | sra_sql_agent | SQL — NL: Critical activities (CP focus) | {'question': 'Which activities are on the critical path', 'project_key': '101'} | WARN | Expected keywords missing: ['Task'] | 0.08 |  | ## ⚠️ Query Syntax Issue The database reported a syntax or access error: > column "activity_code" does not exist HINT: Perhaps you meant to reference the column "tbl_02_project_activity.Activity_Code". **Query attempted:** ```sql SELECT Activity_Code, Activity_Description, Domain_Code, Activity_Status, Planned_Progress_Pct, Actual_Progress_Pct, Forecast_Delay_Days, Total_Float_Days, Activity_Health_RAG FROM tbl_02_project_activity WHERE Project_Key = 101 ORDER BY Forecast_Delay_Days DESC NULLS LAST LIMIT 500 ``` Please review the column names and table references. Column names follow the `PascalCase_With_Underscores` convention. |  | 2026-02-27T09:56:50.476819
91 | tool | L0 | SQL-NL | SQL — NL: Procurement at-risk activities | sra_sql_agent | SQL — NL: Procurement at-risk activities | {'question': 'Procurement activities with overdue rules', 'project_key': '101'} | WARN | Expected keywords missing: ['Task'] | 0.1 |  | ## ⚠️ Query Syntax Issue The database reported a syntax or access error: > column "activity_code" does not exist HINT: Perhaps you meant to reference the column "tbl_02_project_activity.Activity_Code". **Query attempted:** ```sql SELECT Activity_Code, Activity_Description, Domain_Code, Activity_Status, Planned_Progress_Pct, Actual_Progress_Pct, Forecast_Delay_Days, Total_Float_Days, Activity_Health_RAG FROM tbl_02_project_activity WHERE Project_Key = 101 ORDER BY Forecast_Delay_Days DESC NULLS LAST LIMIT 500 ``` Please review the column names and table references. Column names follow the `PascalCase_With_Underscores` convention. |  | 2026-02-27T09:56:50.579407
92 | tool | L0 | SQL-NL | SQL — NL: EOT exposure per project | sra_sql_agent | SQL — NL: EOT exposure per project | {'question': 'EOT exposure and contractual buffer for the project', 'project_key': '101'} | WARN | Expected keywords missing: ['Activity', 'Task'] | 0.08 |  | ## ⚠️ Query Syntax Issue The database reported a syntax or access error: > column "project_key" does not exist HINT: Perhaps you meant to reference the column "tbl_01_project_summary.Project_Key". **Query attempted:** ```sql SELECT Project_Key, Project_Name, Project_Location, SPI_Overall, Project_Execution_Index, Max_Forecast_Delay_Days_Overall, EOT_Exposure_Days, Schedule_Health_RAG, Schedule_Health_Score, Data_Freshness_Label FROM tbl_01_project_summary WHERE Project_Key = 101 ORDER BY Max_Forecast_Delay_Days_Overall DESC NULLS LAST LIMIT 500 ``` Please review the column names and table references. Column names follow the `PascalCase_With_Underscores` convention. |  | 2026-02-27T09:56:50.656085
93 | tool | L0 | SQL-NL | SQL — NL: Baseline drift activities | sra_sql_agent | SQL — NL: Baseline drift activities | {'question': 'Activities with baseline drift and slip', 'project_key': '101'} | WARN | Expected keywords missing: ['Task'] | 0.08 |  | ## ⚠️ Query Syntax Issue The database reported a syntax or access error: > column "activity_code" does not exist HINT: Perhaps you meant to reference the column "tbl_02_project_activity.Activity_Code". **Query attempted:** ```sql SELECT Activity_Code, Activity_Description, Domain_Code, Activity_Status, Planned_Progress_Pct, Actual_Progress_Pct, Forecast_Delay_Days, Total_Float_Days, Activity_Health_RAG FROM tbl_02_project_activity WHERE Project_Key = 101 ORDER BY Forecast_Delay_Days DESC NULLS LAST LIMIT 500 ``` Please review the column names and table references. Column names follow the `PascalCase_With_Underscores` convention. |  | 2026-02-27T09:56:50.736180
94 | tool | L0 | SQL-NL | SQL — NL: Portfolio view (no project filter) | sra_sql_agent | SQL — NL: Portfolio view (no project filter) | {'question': 'Show all projects with health score and SPI overall'} | WARN | Expected keywords missing: ['Activity', 'Task'] | 0.08 |  | ## ⚠️ Query Syntax Issue The database reported a syntax or access error: > column "project_key" does not exist HINT: Perhaps you meant to reference the column "tbl_01_project_summary.Project_Key". **Query attempted:** ```sql SELECT Project_Key, Project_Name, Project_Location, SPI_Overall, Project_Execution_Index, Max_Forecast_Delay_Days_Overall, EOT_Exposure_Days, Schedule_Health_RAG, Schedule_Health_Score, Data_Freshness_Label FROM tbl_01_project_summary ORDER BY Max_Forecast_Delay_Days_Overall DESC NULLS LAST LIMIT 500 ``` Please review the column names and table references. Column names follow the `PascalCase_With_Underscores` convention. |  | 2026-02-27T09:56:50.815211
95 | tool | L0 | SQL-RAW | SQL RAW — Project summary: key health KPIs | sra_sql_agent | SQL RAW — Project summary: key health KPIs | {'question': 'Raw SQL: project KPIs', 'project_key': '101', 'raw_sql': 'SELECT "Project_Key", "Project_Name", "Project_Location", "SPI_Overall", "Project_Execution_Index", "Max_Forecast_Delay_Days_Overall", "EOT_Exposure_Days", "Schedule_Health_RAG", "Schedule_Health_Score", "Weakest_Domain", "Data_Freshness_Label" FROM public.tbl_01_project_summary WHERE "Project_Key" = 101 ORDER BY "Max_Forecast_Delay_Days_Overall" DESC NULLS LAST LIMIT 10'} | WARN | Expected keywords missing: ['Activity', 'Task'] | 0.09 |  | ## 📊 Ad-Hoc Schedule Query Results *Question: Raw SQL: project KPIs* *Scope: Project 101* *Rows returned: 1* --- ¦ Project_Key ¦ Project_Name ¦ Project_Location ¦ SPI_Overall ¦ Project_Execution_Index ¦ Max_Forecast_Delay_Days_Overall ¦ EOT_Exposure_Days ¦ Schedule_Health_RAG ¦ Schedule_Health_Score ¦ Weakest_Domain ¦ Data_Freshness_Label ¦ ¦-------------¦--------------¦------------------¦-------------¦-------------------------¦---------------------------------¦-------------------¦---------------------¦-----------------------¦----------------¦----------------------¦ ¦ 101 ¦ Mega PWS in 11 block of Ganjam District ¦ Ganjam, Odisha. ¦ 0.228 ¦ 1.60551 ¦ 463 ¦ 463 ¦ Red ¦ 15 ¦ Construction ¦ Recent ? Within Week ¦ --- <details><summary>📋 SQL Executed</summary> ```sql SELECT "Project_Key", "Project_Name", "Project_Location", "SPI_Overall", "Project_Execution_Index", "Max_Forecast_Delay_Days_Overall", "EOT_Exposure_Days", "Schedule_Health_RAG", "Schedule_Health_Score", "Weakest_Domain", "Data_Freshness_Label" FROM public.tbl_01_project_summary WHERE "Project_Key" = 101 ORDER BY "Max_Forecast_Delay_Days_Overall" DESC NULLS LAST LIMIT 10 ``` </details> --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:50.901962
96 | tool | L0 | SQL-RAW | SQL RAW — Top 10 delayed activities with CP flag | sra_sql_agent | SQL RAW — Top 10 delayed activities with CP flag | {'question': 'Raw SQL: top delayed activities', 'project_key': '101', 'raw_sql': 'SELECT "Activity_Code", "Activity_Description", "Domain_Code", "Activity_Status", "Forecast_Delay_Days", "Slip_Days", "Is_Critical_Wrench", "Delay_Magnitude_Label", "Delay_Source_Label", "Compound_Risk_Score" FROM public.tbl_02_project_activity WHERE "Project_Key" = 101 AND "Forecast_Delay_Days" > 0 ORDER BY "Forecast_Delay_Days" DESC LIMIT 10'} | WARN | Expected keywords missing: ['Task'] | 0.1 |  | ## 📊 Ad-Hoc Schedule Query Results *Question: Raw SQL: top delayed activities* *Scope: Project 101* *Rows returned: 0* --- The query returned no records matching the specified criteria. --- <details><summary>📋 SQL Executed</summary> ```sql SELECT "Activity_Code", "Activity_Description", "Domain_Code", "Activity_Status", "Forecast_Delay_Days", "Slip_Days", "Is_Critical_Wrench", "Delay_Magnitude_Label", "Delay_Source_Label", "Compound_Risk_Score" FROM public.tbl_02_project_activity WHERE "Project_Key" = 101 AND "Forecast_Delay_Days" > 0 ORDER BY "Forecast_Delay_Days" DESC LIMIT 10 ``` </details> --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:51.004830
97 | tool | L0 | SQL-RAW | SQL RAW — Tasks near-critical (float ≤ 5d) | sra_sql_agent | SQL RAW — Tasks near-critical (float ≤ 5d) | {'question': 'Raw SQL: near-critical tasks', 'project_key': '101', 'raw_sql': 'SELECT "Task_Key", "Task_Name", "Activity_Code", "Domain_Code", "Total_Float_Days", "Float_Health_Status", "Float_RAG_Label", "Is_Critical_Wrench", "Forecast_Delay_Days", "Task_Health_RAG" FROM public.tbl_03_project_task WHERE "Project_Key" = 101 AND "Total_Float_Days" >= 0 AND "Total_Float_Days" <= 5 ORDER BY "Total_Float_Days" ASC LIMIT 20'} | PASS | All expected content present | 0.09 |  | ## 📊 Ad-Hoc Schedule Query Results *Question: Raw SQL: near-critical tasks* *Scope: Project 101* *Rows returned: 0* --- The query returned no records matching the specified criteria. --- <details><summary>📋 SQL Executed</summary> ```sql SELECT "Task_Key", "Task_Name", "Activity_Code", "Domain_Code", "Total_Float_Days", "Float_Health_Status", "Float_RAG_Label", "Is_Critical_Wrench", "Forecast_Delay_Days", "Task_Health_RAG" FROM public.tbl_03_project_task WHERE "Project_Key" = 101 AND "Total_Float_Days" >= 0 AND "Total_Float_Days" <= 5 ORDER BY "Total_Float_Days" ASC LIMIT 20 ``` </details> --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:51.092300
98 | tool | L0 | SQL-RAW | SQL RAW — Milestones forecast vs baseline | sra_sql_agent | SQL RAW — Milestones forecast vs baseline | {'question': 'Raw SQL: milestones', 'project_key': '101', 'raw_sql': 'SELECT "Task_Key", "Task_Name", "Activity_Code", "Domain_Code", "Baseline_Finish_Date", "Forecast_Finish_Date", "Milestone_Status_Label", "Slip_Days" FROM public.tbl_03_project_task WHERE "Project_Key" = 101 AND "Is_Milestone" = TRUE ORDER BY "Forecast_Finish_Date" ASC LIMIT 20'} | PASS | All expected content present | 0.14 |  | ## 📊 Ad-Hoc Schedule Query Results *Question: Raw SQL: milestones* *Scope: Project 101* *Rows returned: 0* --- The query returned no records matching the specified criteria. --- <details><summary>📋 SQL Executed</summary> ```sql SELECT "Task_Key", "Task_Name", "Activity_Code", "Domain_Code", "Baseline_Finish_Date", "Forecast_Finish_Date", "Milestone_Status_Label", "Slip_Days" FROM public.tbl_03_project_task WHERE "Project_Key" = 101 AND "Is_Milestone" = TRUE ORDER BY "Forecast_Finish_Date" ASC LIMIT 20 ``` </details> --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:51.233980
99 | tool | L0 | SQL-RAW | SQL RAW — Procurement rule summary per activity | sra_sql_agent | SQL RAW — Procurement rule summary per activity | {'question': 'Raw SQL: procurement rules', 'project_key': '101', 'raw_sql': 'SELECT "Activity_Code", "Activity_Description", "Domain_Code", "PRC_Total_Rules", "PRC_Completed_Rules", "PRC_Overdue_Rules", "PRC_At_Risk_Rules_7Day", "PRC_At_Risk_Rules_30Day", "PRC_LAC_Week_Pct", "PRC_LAC_RAG" FROM public.tbl_02_project_activity WHERE "Project_Key" = 101 AND "PRC_Total_Rules" > 0 ORDER BY "PRC_Overdue_Rules" DESC LIMIT 15'} | WARN | Expected keywords missing: ['Task'] | 0.14 |  | ## 📊 Ad-Hoc Schedule Query Results *Question: Raw SQL: procurement rules* *Scope: Project 101* *Rows returned: 5* --- ¦ Activity_Code ¦ Activity_Description ¦ Domain_Code ¦ PRC_Total_Rules ¦ PRC_Completed_Rules ¦ PRC_Overdue_Rules ¦ PRC_At_Risk_Rules_7Day ¦ PRC_At_Risk_Rules_30Day ¦ PRC_LAC_Week_Pct ¦ PRC_LAC_RAG ¦ ¦---------------¦----------------------¦-------------¦-----------------¦---------------------¦-------------------¦------------------------¦-------------------------¦------------------¦-------------¦ ¦ Dispatch ¦ Dispatch ¦ PRC ¦ 1 ¦ 0 ¦ 1 ¦ 0 ¦ 0 ¦ 0 ¦ Red ¦ ¦ — ¦ — ¦ PRC ¦ 1 ¦ 0 ¦ 1 ¦ 0 ¦ 0 ¦ 0 ¦ Red ¦ ¦ INS ¦ Inspection ¦ PRC ¦ 1 ¦ 0 ¦ 1 ¦ 0 ¦ 0 ¦ 0 ¦ Red ¦ ¦ MFC ¦ Manufacturing Clearence ¦ PRC ¦ 1 ¦ 0 ¦ 1 ¦ 0 ¦ 0 ¦ 0 ¦ Red ¦ ¦ PO ¦ Purchase Order ¦ PRC ¦ 1 ¦ 0 ¦ 1 ¦ 0 ¦ 0 ¦ 0 ¦ Red ¦ --- <details><summary>📋 SQL Executed</summary> ```sql SELECT "Activity_Code", "Activity_Description", "Domain_Code", "PRC_Total_Rules", "PRC_Completed_Rules", "PRC_Overdue_Rules", "PRC_At_Risk_Rules_7Day", "PRC_At_Risk_Rules_30Day", "PRC_LAC_Week_Pct", "PRC_LAC_RAG" FROM public.tbl_02_project_activity WHERE "Project_Key" = 101 AND "PRC_Total_Rules" > 0 ORDER BY "PRC_Overdue_Rules" DESC LIMIT 15 ``` </details> --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:51.372834
100 | tool | L0 | SQL-RAW | SQL RAW — Construction LAC per activity | sra_sql_agent | SQL RAW — Construction LAC per activity | {'question': 'Raw SQL: construction LAC', 'project_key': '101', 'raw_sql': 'SELECT "Activity_Code", "Activity_Description", "Domain_Code", "CON_Total_Rules", "CON_Completed_Rules", "CON_Overdue_Rules", "CON_At_Risk_Rules_7Day", "CON_LAC_Week_Pct", "CON_LAC_Month_Pct", "CON_LAC_RAG" FROM public.tbl_02_project_activity WHERE "Project_Key" = 101 AND "CON_Total_Rules" > 0 ORDER BY "CON_LAC_Week_Pct" ASC LIMIT 15'} | WARN | Expected keywords missing: ['Task'] | 0.08 |  | ## 📊 Ad-Hoc Schedule Query Results *Question: Raw SQL: construction LAC* *Scope: Project 101* *Rows returned: 15* --- ¦ Activity_Code ¦ Activity_Description ¦ Domain_Code ¦ CON_Total_Rules ¦ CON_Completed_Rules ¦ CON_Overdue_Rules ¦ CON_At_Risk_Rules_7Day ¦ CON_LAC_Week_Pct ¦ CON_LAC_Month_Pct ¦ CON_LAC_RAG ¦ ¦---------------¦----------------------¦-------------¦-----------------¦---------------------¦-------------------¦------------------------¦------------------¦-------------------¦-------------¦ ¦ PCC ¦ PCC ¦ CON ¦ 1 ¦ 0 ¦ 1 ¦ 1 ¦ 0 ¦ 0 ¦ Red ¦ ¦ Shuttering ¦ Shuttering ¦ CON ¦ 1 ¦ 0 ¦ 1 ¦ 1 ¦ 0 ¦ 0 ¦ Red ¦ ¦ PCC ¦ PCC ¦ CON ¦ 1 ¦ 0 ¦ 1 ¦ 1 ¦ 0 ¦ 0 ¦ Red ¦ ¦ Reinforcement ¦ Reinforcement ¦ CON ¦ 1 ¦ 0 ¦ 1 ¦ 1 ¦ 0 ¦ 0 ¦ Red ¦ ¦ Reinforcement ¦ Reinforcement ¦ CON ¦ 1 ¦ 0 ¦ 1 ¦ 1 ¦ 0 ¦ 0 ¦ Red ¦ ¦ Shuttering ¦ Shuttering ¦ CON ¦ 1 ¦ 0 ¦ 1 ¦ 1 ¦ 0 ¦ 0 ¦ Red ¦ ¦ RCC ¦ RCC ¦ CON ¦ 1 ¦ 0 ¦ 1 ¦ 1 ¦ 0 ¦ 0 ¦ Red ¦ ¦ Shuttering ¦ Shuttering ¦ CON ¦ 1 ¦ 0 ¦ 1 ¦ 1 ¦ 0 ¦ 0 ¦ Red ¦ ¦ Commissioning ¦ Commissioning ¦ CON ¦ 1 ¦ 0 ¦ 1 ¦ 1 ¦ 0 ¦ 0 ¦ Red ¦ ¦ PCC ¦ PCC ¦ CON ¦ 1 ¦ 0 ¦ 1 ¦ 1 ¦ 0 ¦ 0 ¦ Red ¦ ¦ RCC ¦ RCC ¦ CON ¦ 1 ¦ 0 ¦ 1 ¦ 1 ¦ 0 ¦ 0 ¦ Red ¦ ¦ Road Cutting (Cum) ¦ Road Cutting (Cum) ¦ CON ¦ 1 ¦ 0 ¦ 1 ¦ 1 ¦ 0 ¦ 0 ¦ Red ¦ ¦ Reinforcement ¦ Reinforcement ¦ CON ¦ 1 ¦ 0 ¦ 1 ¦ 1 ¦ 0 ¦ 0 ¦ Red ¦ ¦ Plastering ¦ Plastering ¦ CON ¦ 1 ¦ 0 ¦ 1 ¦ 1 ¦ 0 ¦ 0 ¦ Red ¦ ¦ — ¦ — ¦ CON ¦ 1 ¦ 0 ¦ 1 ¦ 1 ¦ 0 ¦ 0 ¦ Red ¦ --- <details><summary>📋 SQL Executed</summary> ```sql SELECT "Activity_Code", "Activity_Description", "Domain_Code", "CON_Total_Rules", "CON_Completed_Rules", "CON_Overdue_Rules", "CON_At_Risk_Rules_7Day", "CON_LAC_Week_Pct", "CON_LAC_Month_Pct", "CON_LAC_RAG" FROM public.tbl_02_project_activity WHERE "Project_Key" = 101 AND "CON_Total_Rules" > 0 ORDER BY "CON_LAC_Week_Pct" ASC LIMIT 15 ``` </details> --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:51.448901
101 | tool | L0 | SQL-RAW | SQL RAW — Recovery candidates (crash + fast-track) | sra_sql_agent | SQL RAW — Recovery candidates (crash + fast-track) | {'question': 'Raw SQL: recovery candidates', 'project_key': '101', 'raw_sql': 'SELECT "Task_Key", "Task_Name", "Activity_Code", "Domain_Code", "Crash_Candidate_Flag", "FastTrack_Candidate_Flag", "Task_Acceleration_Days", "Task_Recovery_SPI_Required", "Recovery_Feasibility_Label", "Task_Health_RAG" FROM public.tbl_03_project_task WHERE "Project_Key" = 101 AND ("Crash_Candidate_Flag" = TRUE OR "FastTrack_Candidate_Flag" = TRUE) ORDER BY "Task_Acceleration_Days" DESC NULLS LAST LIMIT 15'} | PASS | All expected content present | 0.09 |  | ## 📊 Ad-Hoc Schedule Query Results *Question: Raw SQL: recovery candidates* *Scope: Project 101* *Rows returned: 15* --- ¦ Task_Key ¦ Task_Name ¦ Activity_Code ¦ Domain_Code ¦ Crash_Candidate_Flag ¦ FastTrack_Candidate_Flag ¦ Task_Acceleration_Days ¦ Task_Recovery_SPI_Required ¦ Recovery_Feasibility_Label ¦ Task_Health_RAG ¦ ¦----------¦-----------¦---------------¦-------------¦----------------------¦--------------------------¦------------------------¦----------------------------¦----------------------------¦-----------------¦ ¦ 10184992 ¦ Detailed scheme report (DSR) ¦ — ¦ ENG ¦ True ¦ False ¦ 926 ¦ — ¦ Recovery Unlikely Without Resequencing ¦ Amber ¦ ¦ 10185106 ¦ Detailed scheme report (DSR) ¦ — ¦ ENG ¦ True ¦ False ¦ 923 ¦ — ¦ Recovery Unlikely Without Resequencing ¦ Amber ¦ ¦ 1014069 ¦ Numeration and RC Detail of Switchyard at IBPS-1 for Scheme-2 ¦ — ¦ ENG ¦ True ¦ False ¦ 882 ¦ — ¦ Recovery Unlikely Without Resequencing ¦ Red ¦ ¦ 1012985 ¦ Approach Channel ¦ — ¦ ENG ¦ True ¦ False ¦ 875 ¦ — ¦ Recovery Unlikely Without Resequencing ¦ Red ¦ ¦ 10134111 ¦ Design Calculation of ESR of 125KL Capacity 14m Staging height at Baragaom for Scheme-I ¦ — ¦ ENG ¦ True ¦ False ¦ 870 ¦ — ¦ Recovery Unlikely Without Resequencing ¦ Red ¦ ¦ 10126411 ¦ Inspection ¦ INS ¦ PRC ¦ True ¦ False ¦ 869 ¦ — ¦ Recovery Unlikely Without Resequencing ¦ Red ¦ ¦ 10126410 ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ True ¦ False ¦ 869 ¦ — ¦ Recovery Unlikely Without Resequencing ¦ Red ¦ ¦ 10126409 ¦ MFC ¦ MFC ¦ PRC ¦ True ¦ False ¦ 869 ¦ — ¦ Recovery Unlikely Without Resequencing ¦ Red ¦ ¦ 10126408 ¦ Post Order & QAP Approval ¦ — ¦ PRC ¦ True ¦ False ¦ 869 ¦ — ¦ Recovery Unlikely Without Resequencing ¦ Red ¦ ¦ 1013598 ¦ Cable Design Memorandum and Typical Voltage Drop & Cable Design Calculationsfor Intake, WTP ¦ — ¦ ENG ¦ True ¦ False ¦ 865 ¦ — ¦ Recovery Unlikely Without Resequencing ¦ Red ¦ ¦ 1012371 ¦ L Section for Clear Water Pumping Main from IBPS 11 (PM-2) to OHT-(Ganjam Scheme-1) ¦ — ¦ ENG ¦ True ¦ False ¦ 863 ¦ — ¦ Recovery Unlikely Without Resequencing ¦ Red ¦ ¦ 1014048 ¦ Architectural Detail of Clear Water Pump House for Scheme-2 ¦ — ¦ ENG ¦ True ¦ False ¦ 860 ¦ — ¦ Recovery Unlikely Without Resequencing ¦ Red ¦ ¦ 1012388 ¦ Surge Analysis Report for Clear water Pumping main from IBPS-11 (PM-1) to OHTs Ganjam WSS (Scheme-1) ¦ — ¦ ENG ¦ True ¦ False ¦ 852 ¦ — ¦ Recovery Unlikely Without Resequencing ¦ Red ¦ ¦ 1014137 ¦ Numeration and RC Detail of Valve Chambers for Scheme-2 ¦ — ¦ ENG ¦ True ¦ False ¦ 851 ¦ — ¦ Recovery Unlikely Without Resequencing ¦ Red ¦ ¦ 1014134 ¦ Numeration and RC Detail of Valve Chambers for Scheme-2 ¦ — ¦ ENG ¦ True ¦ False ¦ 851 ¦ — ¦ Recovery Unlikely Without Resequencing ¦ Red ¦ --- <details><summary>📋 SQL Executed</summary> ```sql SELECT "Task_Key", "Task_Name", "Activity_Code", "Domain_Code", "Crash_Candidate_Flag", "FastTrack_Candidate_Flag", "Task_Acceleration_Days", "Task_Recovery_SPI_Required", "Recovery_Feasibility_Label", "Task_Health_RAG" FROM public.tbl_03_project_task WHERE "Project_Key" = 101 AND ("Crash_Candidate_Flag" = TRUE OR "FastTrack_Candidate_Flag" = TRUE) ORDER BY "Task_Acceleration_Days" DESC NULLS LAST LIMIT 15 ``` </details> --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:51.537933
102 | tool | L0 | SQL-RAW | SQL RAW — As-built vs baseline (completed tasks) | sra_sql_agent | SQL RAW — As-built vs baseline (completed tasks) | {'question': 'Raw SQL: as-built variance', 'project_key': '101', 'raw_sql': 'SELECT "Task_Key", "Task_Name", "Activity_Code", "Domain_Code", "Baseline_Duration_Days", "As_Built_Duration_Days", "Duration_Variance_Days", "Task_Status", "Actual_Finish_Date" FROM public.tbl_03_project_task WHERE "Project_Key" = 101 AND "Task_Status" = \'Complete\' AND "As_Built_Duration_Days" IS NOT NULL ORDER BY "Duration_Variance_Days" DESC NULLS LAST LIMIT 15'} | PASS | All expected content present | 0.09 |  | ## 📊 Ad-Hoc Schedule Query Results *Question: Raw SQL: as-built variance* *Scope: Project 101* *Rows returned: 15* --- ¦ Task_Key ¦ Task_Name ¦ Activity_Code ¦ Domain_Code ¦ Baseline_Duration_Days ¦ As_Built_Duration_Days ¦ Duration_Variance_Days ¦ Task_Status ¦ Actual_Finish_Date ¦ ¦----------¦-----------¦---------------¦-------------¦------------------------¦------------------------¦------------------------¦-------------¦--------------------¦ ¦ 10134120 ¦ Numeration and RC Detail of ESR of 500KL Capacity 12m Staging height at Chandipalli for Scheme-II ¦ — ¦ ENG ¦ 46 ¦ 742 ¦ 696 ¦ Complete ¦ 14 Feb 1970 ¦ ¦ 10134121 ¦ Numeration and RC Detail of ESR of 500KL Capacity 12m Staging height at Chandipalli for Scheme-II ¦ — ¦ ENG ¦ 46 ¦ 742 ¦ 696 ¦ Complete ¦ 14 Feb 1970 ¦ ¦ 10134119 ¦ Design Calculation of ESR of 500KL Capacity 12m Staging height at Chandipalli for Scheme-II ¦ — ¦ ENG ¦ 46 ¦ 742 ¦ 696 ¦ Complete ¦ 14 Feb 1970 ¦ ¦ 10134122 ¦ Numeration and RC Detail of ESR of 500KL Capacity 12m Staging height at Chandipalli for Scheme-II ¦ — ¦ ENG ¦ 46 ¦ 742 ¦ 696 ¦ Complete ¦ 13 Feb 1970 ¦ ¦ 1012938 ¦ Scheme diagram for Gravity Distribution main from OHT-261 HUKUMA-EX (SORODA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 46 ¦ 732 ¦ 686 ¦ Complete ¦ 28 Jan 1970 ¦ ¦ 1012937 ¦ Hydraulics Design for Gravity Distribution main from OHT-261 HUKUMA-EX (SORODA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 46 ¦ 732 ¦ 686 ¦ Complete ¦ 28 Jan 1970 ¦ ¦ 1012966 ¦ Scheme diagram for Gravity Distribution main from OHT-275 GOUDAGOTHA-EX (SORODA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 45 ¦ 687 ¦ 642 ¦ Complete ¦ 02 Feb 1970 ¦ ¦ 1012965 ¦ Hydraulics Design for Gravity Distribution main from OHT-275 GOUDAGOTHA-EX (SORODA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 45 ¦ 687 ¦ 642 ¦ Complete ¦ 03 Feb 1970 ¦ ¦ 1012446 ¦ Scheme diagram for Gravity Distribution main from OHT-15 ATHAGADAPATNA-PR (KS NAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 45 ¦ 656 ¦ 611 ¦ Complete ¦ 28 Jan 1970 ¦ ¦ 1012445 ¦ Hydraulics Design for Gravity Distribution main from OHT-15 ATHAGADAPATNA-PR (KS NAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 45 ¦ 656 ¦ 611 ¦ Complete ¦ 28 Jan 1970 ¦ ¦ 1012903 ¦ Hydraulics Design for Gravity Distribution main from OHT-244 KHURA-PR (POLASARA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 46 ¦ 648 ¦ 602 ¦ Complete ¦ 28 Jan 1970 ¦ ¦ 1012904 ¦ Scheme diagram for Gravity Distribution main from OHT-244 KHURA-PR (POLASARA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 46 ¦ 648 ¦ 602 ¦ Complete ¦ 28 Jan 1970 ¦ ¦ 1012290 ¦ Surge Analysis Report for Raw water pumping main from Intake well to RW-IBPS - (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 45 ¦ 618 ¦ 573 ¦ Complete ¦ 27 Feb 1970 ¦ ¦ 10852992 ¦ Scheme diagram for Gravity Distribution main from OHT-296 ATHAGADAPATNA-EX GLSR (KS NAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 46 ¦ 609 ¦ 563 ¦ Complete ¦ 29 Jan 1970 ¦ ¦ 10852991 ¦ Hydraulics Design for Gravity Distribution main from OHT-296 ATHAGADAPATNA-EX GLSR (KS NAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 46 ¦ 609 ¦ 563 ¦ Complete ¦ 29 Jan 1970 ¦ --- <details><summary>📋 SQL Executed</summary> ```sql SELECT "Task_Key", "Task_Name", "Activity_Code", "Domain_Code", "Baseline_Duration_Days", "As_Built_Duration_Days", "Duration_Variance_Days", "Task_Status", "Actual_Finish_Date" FROM public.tbl_03_project_task WHERE "Project_Key" = 101 AND "Task_Status" = 'Complete' AND "As_Built_Duration_Days" IS NOT NULL ORDER BY "Duration_Variance_Days" DESC NULLS LAST LIMIT 15 ``` </details> --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:51.631747
103 | tool | L0 | SQL-RAW | SQL RAW — Workfront block flag tasks in 2W window | sra_sql_agent | SQL RAW — Workfront block flag tasks in 2W window | {'question': 'Raw SQL: blocked tasks in 2W window', 'project_key': '101', 'raw_sql': 'SELECT "Task_Key", "Task_Name", "Activity_Code", "Domain_Code", "Forecast_Start_Date", "Forecast_Finish_Date", "Workfront_Block_Flag", "Is_WorkFront_Available", "Total_Float_Days", "LookAhead_Priority_Score" FROM public.tbl_03_project_task WHERE "Project_Key" = 101 AND "In_2W_Start_Window" IS NOT NULL ORDER BY "LookAhead_Priority_Score" DESC NULLS LAST LIMIT 20'} | PASS | All expected content present | 0.1 |  | ## 📊 Ad-Hoc Schedule Query Results *Question: Raw SQL: blocked tasks in 2W window* *Scope: Project 101* *Rows returned: 20* --- ¦ Task_Key ¦ Task_Name ¦ Activity_Code ¦ Domain_Code ¦ Forecast_Start_Date ¦ Forecast_Finish_Date ¦ Workfront_Block_Flag ¦ Is_WorkFront_Available ¦ Total_Float_Days ¦ LookAhead_Priority_Score ¦ ¦----------¦-----------¦---------------¦-------------¦---------------------¦----------------------¦----------------------¦------------------------¦------------------¦--------------------------¦ ¦ 10184851 ¦ PR ¦ PR ¦ PRC ¦ 22 Jan 1970 ¦ 22 Jan 1970 ¦ False ¦ False ¦ — ¦ 40 ¦ ¦ 10185379 ¦ MRN ¦ MRN ¦ PRC ¦ 16 Jan 1970 ¦ 19 Jan 1970 ¦ False ¦ False ¦ — ¦ 40 ¦ ¦ 10115574 ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 08 Feb 1970 ¦ 17 Feb 1970 ¦ False ¦ — ¦ — ¦ 40 ¦ ¦ 10115555 ¦ MRN ¦ MRN ¦ PRC ¦ 27 Feb 1970 ¦ 09 Jan 1970 ¦ False ¦ False ¦ — ¦ 40 ¦ ¦ 10184799 ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 16 Jan 1970 ¦ 14 Jan 1970 ¦ False ¦ False ¦ — ¦ 40 ¦ ¦ 10184873 ¦ PO ¦ PO ¦ PRC ¦ 16 Jan 1970 ¦ 05 Feb 1970 ¦ False ¦ False ¦ — ¦ 40 ¦ ¦ 1013115 ¦ P&ID Drawing for CWR cum Pump House at IBPS-1- (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 11 Jan 1970 ¦ 22 Jan 1970 ¦ False ¦ — ¦ — ¦ 40 ¦ ¦ 10115441 ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 16 Jan 1970 ¦ 19 Jan 1970 ¦ False ¦ False ¦ — ¦ 40 ¦ ¦ 1013782 ¦ Instrument list for IBPS-5 ¦ — ¦ ENG ¦ 24 Jan 1970 ¦ 22 Jan 1970 ¦ False ¦ — ¦ — ¦ 40 ¦ ¦ 1014165 ¦ Lighting Layout for Intake ¦ — ¦ ENG ¦ 20 Jan 1970 ¦ 22 Jan 1970 ¦ False ¦ — ¦ — ¦ 40 ¦ ¦ 10184883 ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 16 Jan 1970 ¦ 12 Feb 1970 ¦ False ¦ False ¦ — ¦ 40 ¦ ¦ 10184824 ¦ PO ¦ PO ¦ PRC ¦ 16 Jan 1970 ¦ 27 Feb 1970 ¦ False ¦ False ¦ — ¦ 40 ¦ ¦ 10115556 ¦ PR ¦ PR ¦ PRC ¦ 02 Mar 1970 ¦ 01 Mar 1970 ¦ False ¦ False ¦ — ¦ 40 ¦ ¦ 1013689 ¦ 33/11 kV Switchyard Layout for IBPS 1 ¦ — ¦ ENG ¦ 14 Jan 1970 ¦ 22 Jan 1970 ¦ False ¦ — ¦ — ¦ 40 ¦ ¦ 1013050 ¦ Architectural Detail of Chlorine Building for Scheme-1 ¦ — ¦ ENG ¦ 26 Feb 1970 ¦ 22 Jan 1970 ¦ False ¦ — ¦ — ¦ 40 ¦ ¦ 10184999 ¦ Numeration and RC Detail of Cascade aerator, Parshall flume, Distribution chamber and Flash mixer for Scheme-1 ¦ — ¦ ENG ¦ 01 Jan 1970 ¦ 22 Jan 1970 ¦ False ¦ — ¦ — ¦ 40 ¦ ¦ 1013740 ¦ Overall Single Line Diagram for IBPS 12 ¦ — ¦ ENG ¦ 14 Jan 1970 ¦ 22 Jan 1970 ¦ False ¦ — ¦ — ¦ 40 ¦ ¦ 10184910 ¦ MFC ¦ MFC ¦ PRC ¦ 16 Jan 1970 ¦ 26 Jan 1970 ¦ False ¦ False ¦ — ¦ 40 ¦ ¦ 1013102 ¦ Design Calculation of Intermediate Sump-1 for Scheme-1 ¦ — ¦ ENG ¦ 16 Feb 1970 ¦ 22 Jan 1970 ¦ False ¦ — ¦ — ¦ 40 ¦ ¦ 1012376 ¦ Surge Analysis Report for Clear water Pumping main from IBPS-09 (PM-2) to OHTs Ganjam WSS (Scheme-1) ¦ — ¦ ENG ¦ 30 Jan 1970 ¦ 22 Jan 1970 ¦ False ¦ False ¦ — ¦ 40 ¦ --- <details><summary>📋 SQL Executed</summary> ```sql SELECT "Task_Key", "Task_Name", "Activity_Code", "Domain_Code", "Forecast_Start_Date", "Forecast_Finish_Date", "Workfront_Block_Flag", "Is_WorkFront_Available", "Total_Float_Days", "LookAhead_Priority_Score" FROM public.tbl_03_project_task WHERE "Project_Key" = 101 AND "In_2W_Start_Window" IS NOT NULL ORDER BY "LookAhead_Priority_Score" DESC NULLS LAST LIMIT 20 ``` </details> --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:51.736254
104 | tool | L0 | SQL-EDGE | SQL EDGE — Blocked: INSERT statement attempt | sra_sql_agent | SQL EDGE — Blocked: INSERT statement attempt | {'question': 'Security test: INSERT attempt', 'raw_sql': 'INSERT INTO tbl_01_project_summary VALUES (1)'} | WARN | Expected keywords missing: ['Project', 'Activity', 'Task'] | 0 |  | ## 🚫 Query Not Permitted The proposed SQL statement was not executed for the following reason: > Statement contains disallowed DML/DDL keywords. Only read-only `SELECT` statements are permitted. Please revise and resubmit. |  | 2026-02-27T09:56:51.737253
105 | tool | L0 | SQL-EDGE | SQL EDGE — Blocked: DELETE statement attempt | sra_sql_agent | SQL EDGE — Blocked: DELETE statement attempt | {'question': 'Security test: DELETE attempt', 'raw_sql': 'DELETE FROM tbl_01_project_summary WHERE 1=1'} | WARN | Expected keywords missing: ['Project', 'Activity', 'Task'] | 0 |  | ## 🚫 Query Not Permitted The proposed SQL statement was not executed for the following reason: > Statement contains disallowed DML/DDL keywords. Only read-only `SELECT` statements are permitted. Please revise and resubmit. |  | 2026-02-27T09:56:51.737253
106 | tool | L0 | SQL-EDGE | SQL EDGE — Blocked: DROP TABLE attempt | sra_sql_agent | SQL EDGE — Blocked: DROP TABLE attempt | {'question': 'Security test: DROP TABLE attempt', 'raw_sql': 'DROP TABLE tbl_03_project_task'} | WARN | Expected keywords missing: ['Project', 'Activity', 'Task'] | 0 |  | ## 🚫 Query Not Permitted The proposed SQL statement was not executed for the following reason: > Statement contains disallowed DML/DDL keywords. Only read-only `SELECT` statements are permitted. Please revise and resubmit. |  | 2026-02-27T09:56:51.738251
107 | tool | L0 | SQL-EDGE | SQL EDGE — Blocked: Multiple statements (semicolon) | sra_sql_agent | SQL EDGE — Blocked: Multiple statements (semicolon) | {'question': 'Security test: multiple statements', 'raw_sql': 'SELECT 1; DROP TABLE tbl_01_project_summary'} | WARN | Expected keywords missing: ['Project', 'Activity', 'Task'] | 0 |  | ## 🚫 Query Not Permitted The proposed SQL statement was not executed for the following reason: > Statement contains disallowed DML/DDL keywords. Only read-only `SELECT` statements are permitted. Please revise and resubmit. |  | 2026-02-27T09:56:51.739252
108 | tool | L0 | SQL-EDGE | SQL EDGE — Ambiguous question (should request clarification) | sra_sql_agent | SQL EDGE — Ambiguous question (should request clarification) | {'question': 'Show me everything', 'project_key': '101'} | PASS | All expected content present | 0 |  | ## 🔍 Ad-Hoc Query — Clarification Required The question **"Show me everything"** falls outside the coverage of the structured schedule intelligence tools, and could not be automatically translated into a targeted database query. To proceed, please provide one of the following: 1. **A more specific question** — include the grain (task/activity/project), domain (ENG/PRC/CON), and the specific metrics or conditions you need. 2. **A raw SQL SELECT** — pass it via the `raw_sql` parameter. ### Available Tables ¦ Table ¦ Grain ¦ Key Columns ¦ ¦-------¦-------¦-------------¦ ¦ `tbl_01_project_summary` ¦ One row per project ¦ Project_Key, SPI_Overall, PEI, EOT_Exposure_Days, Schedule_Health_RAG ¦ ¦ `tbl_02_project_activity` ¦ One row per activity ¦ Activity_Code, Domain_Code, Forecast_Delay_Days, Float_Days, LAC_Pct ¦ ¦ `tbl_03_project_task` ¦ One row per task ¦ Task_Key, Activity_Code, Float_Days, Is_Critical_Wrench, Task_Health_RAG ¦ 💡 *Example: "Show all Construction tasks in project 101 with negative float" or "List activities with CON_LAC_Week_Pct below 60% for project 101"* |  | 2026-02-27T09:56:51.739252
109 | tool | L0 | SQL-EDGE | SQL EDGE — No question, no SQL (empty inputs) | sra_sql_agent | SQL EDGE — No question, no SQL (empty inputs) | {'question': 'general question with no direction'} | PASS | All expected content present | 0 |  | ## 🔍 Ad-Hoc Query — Clarification Required The question **"general question with no direction"** falls outside the coverage of the structured schedule intelligence tools, and could not be automatically translated into a targeted database query. To proceed, please provide one of the following: 1. **A more specific question** — include the grain (task/activity/project), domain (ENG/PRC/CON), and the specific metrics or conditions you need. 2. **A raw SQL SELECT** — pass it via the `raw_sql` parameter. ### Available Tables ¦ Table ¦ Grain ¦ Key Columns ¦ ¦-------¦-------¦-------------¦ ¦ `tbl_01_project_summary` ¦ One row per project ¦ Project_Key, SPI_Overall, PEI, EOT_Exposure_Days, Schedule_Health_RAG ¦ ¦ `tbl_02_project_activity` ¦ One row per activity ¦ Activity_Code, Domain_Code, Forecast_Delay_Days, Float_Days, LAC_Pct ¦ ¦ `tbl_03_project_task` ¦ One row per task ¦ Task_Key, Activity_Code, Float_Days, Is_Critical_Wrench, Task_Health_RAG ¦ 💡 *Example: "Show all Construction tasks in project 101 with negative float" or "List activities with CON_LAC_Week_Pct below 60% for project 101"* |  | 2026-02-27T09:56:51.740251

## AGENT_NL
RUN ID | MODE | LAYER | CATEGORY | TEST NAME | TOOL NAME | INPUT SUMMARY | KWARGS | STATUS | VALIDATION NOTE | DURATION SEC | ERROR | TOOL OUTPUT | INSIGHT | TIMESTAMP

## EDGE_CASES
RUN ID | MODE | LAYER | CATEGORY | TEST NAME | TOOL NAME | INPUT SUMMARY | KWARGS | STATUS | VALIDATION NOTE | DURATION SEC | ERROR | TOOL OUTPUT | INSIGHT | TIMESTAMP
104 | tool | L0 | SQL-EDGE | SQL EDGE — Blocked: INSERT statement attempt | sra_sql_agent | SQL EDGE — Blocked: INSERT statement attempt | {'question': 'Security test: INSERT attempt', 'raw_sql': 'INSERT INTO tbl_01_project_summary VALUES (1)'} | WARN | Expected keywords missing: ['Project', 'Activity', 'Task'] | 0 |  | ## 🚫 Query Not Permitted The proposed SQL statement was not executed for the following reason: > Statement contains disallowed DML/DDL keywords. Only read-only `SELECT` statements are permitted. Please revise and resubmit. |  | 2026-02-27T09:56:51.737253
105 | tool | L0 | SQL-EDGE | SQL EDGE — Blocked: DELETE statement attempt | sra_sql_agent | SQL EDGE — Blocked: DELETE statement attempt | {'question': 'Security test: DELETE attempt', 'raw_sql': 'DELETE FROM tbl_01_project_summary WHERE 1=1'} | WARN | Expected keywords missing: ['Project', 'Activity', 'Task'] | 0 |  | ## 🚫 Query Not Permitted The proposed SQL statement was not executed for the following reason: > Statement contains disallowed DML/DDL keywords. Only read-only `SELECT` statements are permitted. Please revise and resubmit. |  | 2026-02-27T09:56:51.737253
106 | tool | L0 | SQL-EDGE | SQL EDGE — Blocked: DROP TABLE attempt | sra_sql_agent | SQL EDGE — Blocked: DROP TABLE attempt | {'question': 'Security test: DROP TABLE attempt', 'raw_sql': 'DROP TABLE tbl_03_project_task'} | WARN | Expected keywords missing: ['Project', 'Activity', 'Task'] | 0 |  | ## 🚫 Query Not Permitted The proposed SQL statement was not executed for the following reason: > Statement contains disallowed DML/DDL keywords. Only read-only `SELECT` statements are permitted. Please revise and resubmit. |  | 2026-02-27T09:56:51.738251
107 | tool | L0 | SQL-EDGE | SQL EDGE — Blocked: Multiple statements (semicolon) | sra_sql_agent | SQL EDGE — Blocked: Multiple statements (semicolon) | {'question': 'Security test: multiple statements', 'raw_sql': 'SELECT 1; DROP TABLE tbl_01_project_summary'} | WARN | Expected keywords missing: ['Project', 'Activity', 'Task'] | 0 |  | ## 🚫 Query Not Permitted The proposed SQL statement was not executed for the following reason: > Statement contains disallowed DML/DDL keywords. Only read-only `SELECT` statements are permitted. Please revise and resubmit. |  | 2026-02-27T09:56:51.739252
108 | tool | L0 | SQL-EDGE | SQL EDGE — Ambiguous question (should request clarification) | sra_sql_agent | SQL EDGE — Ambiguous question (should request clarification) | {'question': 'Show me everything', 'project_key': '101'} | PASS | All expected content present | 0 |  | ## 🔍 Ad-Hoc Query — Clarification Required The question **"Show me everything"** falls outside the coverage of the structured schedule intelligence tools, and could not be automatically translated into a targeted database query. To proceed, please provide one of the following: 1. **A more specific question** — include the grain (task/activity/project), domain (ENG/PRC/CON), and the specific metrics or conditions you need. 2. **A raw SQL SELECT** — pass it via the `raw_sql` parameter. ### Available Tables ¦ Table ¦ Grain ¦ Key Columns ¦ ¦-------¦-------¦-------------¦ ¦ `tbl_01_project_summary` ¦ One row per project ¦ Project_Key, SPI_Overall, PEI, EOT_Exposure_Days, Schedule_Health_RAG ¦ ¦ `tbl_02_project_activity` ¦ One row per activity ¦ Activity_Code, Domain_Code, Forecast_Delay_Days, Float_Days, LAC_Pct ¦ ¦ `tbl_03_project_task` ¦ One row per task ¦ Task_Key, Activity_Code, Float_Days, Is_Critical_Wrench, Task_Health_RAG ¦ 💡 *Example: "Show all Construction tasks in project 101 with negative float" or "List activities with CON_LAC_Week_Pct below 60% for project 101"* |  | 2026-02-27T09:56:51.739252
109 | tool | L0 | SQL-EDGE | SQL EDGE — No question, no SQL (empty inputs) | sra_sql_agent | SQL EDGE — No question, no SQL (empty inputs) | {'question': 'general question with no direction'} | PASS | All expected content present | 0 |  | ## 🔍 Ad-Hoc Query — Clarification Required The question **"general question with no direction"** falls outside the coverage of the structured schedule intelligence tools, and could not be automatically translated into a targeted database query. To proceed, please provide one of the following: 1. **A more specific question** — include the grain (task/activity/project), domain (ENG/PRC/CON), and the specific metrics or conditions you need. 2. **A raw SQL SELECT** — pass it via the `raw_sql` parameter. ### Available Tables ¦ Table ¦ Grain ¦ Key Columns ¦ ¦-------¦-------¦-------------¦ ¦ `tbl_01_project_summary` ¦ One row per project ¦ Project_Key, SPI_Overall, PEI, EOT_Exposure_Days, Schedule_Health_RAG ¦ ¦ `tbl_02_project_activity` ¦ One row per activity ¦ Activity_Code, Domain_Code, Forecast_Delay_Days, Float_Days, LAC_Pct ¦ ¦ `tbl_03_project_task` ¦ One row per task ¦ Task_Key, Activity_Code, Float_Days, Is_Critical_Wrench, Task_Health_RAG ¦ 💡 *Example: "Show all Construction tasks in project 101 with negative float" or "List activities with CON_LAC_Week_Pct below 60% for project 101"* |  | 2026-02-27T09:56:51.740251
2 | tool | L1 | Health | PEI — Missing project key (should list projects) | sra_status_pei | PEI — Missing project key (should list projects) | {} | WARN | Expected keywords missing: ['SPI', 'PEI', 'Programme'] | 0 |  | 📋 **Please specify the project to assess.** Available projects: (Unable to retrieve project list) 💡 Example: *What is the schedule health of project 101?* |  | 2026-02-27T09:56:10.551490
3 | tool | L1 | Health | PEI — Invalid project key (non-numeric) | sra_status_pei | PEI — Invalid project key (non-numeric) | {'project_key': 'ABC'} | WARN | Soft error in output: 'Invalid project key' | 0 |  | Invalid project key `ABC`. Please provide a numeric value (e.g. 101). |  | 2026-02-27T09:56:10.552487
4 | tool | L1 | Health | PEI — Non-existent project key | sra_status_pei | PEI — Non-existent project key | {'project_key': '9999'} | WARN | Soft error in output: 'No schedule data found' | 0.02 |  | No schedule data found for project key **9999**. Please verify the project reference. |  | 2026-02-27T09:56:10.567709
9 | tool | L1 | Activity | Activity — No project key | sra_activity_health | Activity — No project key | {} | WARN | Expected keywords missing: ['Status', 'Domain', 'Workfront'] | 0 |  | 📋 **Specify the project for activity health review.** (Unable to retrieve project list) |  | 2026-02-27T09:56:11.499234
15 | tool | L1 | LookAhead | Task 2W — No project key | sra_task_lookahead | Task 2W — No project key | {} | WARN | Expected keywords missing: ['Task', 'Forecast'] | 0 |  | 📋 **Specify the project for the look-ahead window.** (Unable to retrieve project list) |  | 2026-02-27T09:56:26.205261
17 | tool | L2 | CritPath | Critical Path — No project key | sra_critical_path | Critical Path — No project key | {} | WARN | Expected keywords missing: ['Float', 'CP'] | 0 |  | 📋 **Specify the project for critical path analysis.** (Unable to retrieve project list) |  | 2026-02-27T09:56:29.172490
18 | tool | L2 | CritPath | Critical Path — Non-existent project | sra_critical_path | Critical Path — Non-existent project | {'project_key': '9999'} | WARN | Soft error in output: 'No schedule data found' | 0.01 |  | No schedule data found for project key **9999**. |  | 2026-02-27T09:56:29.181159
23 | tool | L2 | Float | Float — No project key | sra_float_analysis | Float — No project key | {} | WARN | Expected keywords missing: ['Near-Critical', 'Erosion'] | 0 |  | 📋 **Specify the project for float analysis.** (Unable to retrieve project list) |  | 2026-02-27T09:56:30.945182
28 | tool | L2 | Rate | Productivity — No project key | sra_productivity_rate | Productivity — No project key | {} | WARN | Expected keywords missing: ['Progress', 'Earned', 'Planned'] | 0 |  | 📋 **Specify the project for productivity rate analysis.** (Unable to retrieve project list) |  | 2026-02-27T09:56:32.625037
30 | tool | L3 | Baseline | Baseline — No project key | sra_baseline_management | Baseline — No project key | {} | WARN | Expected keywords missing: ['Drift', 'JCR', 'Slip'] | 0 |  | 📋 **Specify the project for baseline management review.** (Unable to retrieve project list) |  | 2026-02-27T09:56:33.046356
31 | tool | L3 | Baseline | Baseline — Non-existent project | sra_baseline_management | Baseline — Non-existent project | {'project_key': '9999'} | WARN | Soft error in output: 'No schedule data found' | 0.01 |  | No schedule data found for project key **9999**. |  | 2026-02-27T09:56:33.061292
33 | tool | L3 | Quality | Quality — No project key | sra_schedule_quality | Quality — No project key | {} | WARN | Expected keywords missing: ['LAC', 'Compliance', 'Data Freshness'] | 0 |  | 📋 **Specify the project for schedule quality review.** (Unable to retrieve project list) |  | 2026-02-27T09:56:33.077427
34 | tool | L3 | Quality | Quality — Non-existent project | sra_schedule_quality | Quality — Non-existent project | {'project_key': '9999'} | WARN | Soft error in output: 'No schedule data found' | 0.01 |  | No schedule data found for project key **9999**. |  | 2026-02-27T09:56:33.091672
38 | tool | L4 | Delay | Delay — No project key | sra_drill_delay | Delay — No project key | {} | WARN | Expected keywords missing: ['Hotspot', 'Workfront'] | 0 |  | 📋 **Please specify the project for delay analysis.** Available projects: (Unable to retrieve project list) 💡 Example: *Analyse delay exposure for project 101* |  | 2026-02-27T09:56:34.406053
39 | tool | L4 | Delay | Delay — Non-existent project | sra_drill_delay | Delay — Non-existent project | {'project_key': '9999'} | WARN | Soft error in output: 'No schedule data found' | 0.01 |  | No schedule data found for project key **9999**. |  | 2026-02-27T09:56:34.414001
41 | tool | L4 | Procurement | PRC — No project key | sra_procurement_alignment | PRC — No project key | {} | WARN | Expected keywords missing: ['PRC', 'LAC'] | 0 |  | 📋 **Specify the project for procurement alignment review.** (Unable to retrieve project list) |  | 2026-02-27T09:56:35.078523
42 | tool | L4 | Procurement | PRC — Non-existent project | sra_procurement_alignment | PRC — Non-existent project | {'project_key': '9999'} | WARN | Soft error in output: 'No schedule data found' | 0.01 |  | No schedule data found for project key **9999**. |  | 2026-02-27T09:56:35.090693
44 | tool | L4 | EOT | EOT — No project key | sra_eot_exposure | EOT — No project key | {} | WARN | Expected keywords missing: ['Contractual', 'Buffer'] | 0 |  | 📋 **Specify the project for EOT exposure assessment.** (Unable to retrieve project list) |  | 2026-02-27T09:56:35.104231
45 | tool | L4 | EOT | EOT — Non-existent project | sra_eot_exposure | EOT — Non-existent project | {'project_key': '9999'} | WARN | Soft error in output: 'No schedule data found' | 0.01 |  | No schedule data found for project key **9999**. |  | 2026-02-27T09:56:35.112823
51 | tool | L5 | Recovery | Recovery — No project key | sra_recovery_advise | Recovery — No project key | {} | WARN | Expected keywords missing: ['Workfront'] | 0 |  | 📋 **Specify the project for recovery planning.** (Unable to retrieve project list) 💡 Example: *What are the recovery options for project 101?* |  | 2026-02-27T09:56:37.280572
58 | tool | L5 | Simulate | Simulate — Missing resource type (should prompt) | sra_simulate | Simulate — Missing resource type (should prompt) | {'project_key': '101'} | WARN | Expected keywords missing: ['Projected', 'Programme Impact'] | 0 |  | 📋 **Additional details required to run the scenario:** **Resource Type** — e.g. shuttering_gang / labor / equipment / overtime **Quantity** — e.g. 2 (gangs), 8 (overtime hours) 💡 Example: *What if I add 2 shuttering gangs to project 101?* |  | 2026-02-27T09:56:37.339059
59 | tool | L5 | Simulate | Simulate — Missing all params (should prompt) | sra_simulate | Simulate — Missing all params (should prompt) | {} | WARN | Expected keywords missing: ['Projected', 'Programme Impact'] | 0 |  | 📋 **Additional details required to run the scenario:** **Project** — which project? (Unable to retrieve project list) **Resource Type** — e.g. shuttering_gang / labor / equipment / overtime **Quantity** — e.g. 2 (gangs), 8 (overtime hours) 💡 Example: *What if I add 2 shuttering gangs to project 101?* |  | 2026-02-27T09:56:37.340059
72 | tool | L6 | Accountability | Trace — No project key | sra_accountability_trace | Trace — No project key | {} | WARN | Expected keywords missing: ['Report', 'Task'] | 0 |  | 📋 **Specify the project for accountability tracing.** (Unable to retrieve project list) |  | 2026-02-27T09:56:49.514911
79 | tool | L6 | Formula | Formula — No project key, SPI only | sra_explain_formula | Formula — No project key, SPI only | {'metric': 'SPI'} | WARN | Expected keywords missing: ['Definition'] | 0 |  | ## 📐 Schedule Metric Reference Guide ### 📈 SPI — Schedule Performance Index **Formula**: `SPI = Earned Progress % / Planned Progress %` Measures whether work is being executed at the rate the programme demands. An SPI of 1.0 means the project is earning exactly what was planned. Below 1.0 indicates the execution rate is lagging — the gap compounds over time on a critical path. ¦ Value ¦ Signal ¦ Interpretation ¦ ¦-------¦--------¦----------------¦ ¦ SPI > 1.0 ¦ 🟢 Ahead of Programme ¦ Execution exceeds plan ¦ ¦ SPI = 1.0 ¦ ✅ On Programme ¦ Performance exactly as planned ¦ ¦ SPI < 1.0 ¦ 🔴 Behind Programme ¦ Execution rate below plan ¦ --- 💡 *Ask about a specific metric for a live calculation against your project — e.g. 'Explain SPI for project 101'* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:49.582690

## ALL_RESULTS
RUN ID | MODE | LAYER | CATEGORY | TEST NAME | TOOL NAME | INPUT SUMMARY | KWARGS | STATUS | VALIDATION NOTE | DURATION SEC | ERROR | TOOL OUTPUT | INSIGHT | TIMESTAMP
1 | tool | L1 | Health | PEI — Full project health snapshot | sra_status_pei | PEI — Full project health snapshot | {'project_key': '101'} | WARN | Expected keywords missing: ['Programme'] | 0.61 |  | ## 🔴 Schedule Health: **Schedule Attention Required** **Mega PWS in 11 block of Ganjam District** · Ganjam, Odisha. *Report Date: 31 Jan 1970* 📊 **Cumulative Progress** — Planned: 100.0% ¦ Achieved: 22.8% ¦ Backlog: 77.2% ⚠️ *SPI at 0.23 — execution is 77.2% behind planned throughput* --- ### Schedule Performance Indices ¦ Index ¦ Value ¦ Signal ¦ Interpretation ¦ ¦-------¦-------¦--------¦----------------¦ ¦ 🔴 **SPI** ¦ 0.228 ¦ Behind Planned Throughput ¦ Earned progress vs planned ¦ ¦ 🔴 **PEI** ¦ 1.606 ¦ Forecast Exceeds Baseline Duration ¦ Forecast duration efficiency ¦ ¦ 🔴 **Health Score** ¦ 15.0/100 ¦ Red ¦ Composite schedule health ¦ ### EPC Domain Breakdown ¦ Domain ¦ Activities ¦ Planned % ¦ Achieved % ¦ Max Delay ¦ Domain SPI ¦ ¦--------¦-----------¦-----------¦------------¦-----------¦------------¦ ¦ 🟡 **Engineering** ¦ 290 ¦ 100.0% ¦ 88.1% ¦ 0d ¦ 0.88 ¦ ¦ 🟡 **Procurement** ¦ 112 ¦ 100.0% ¦ 27.1% ¦ 0d ¦ 0.27 ¦ ¦ 🟡 **Construction** ¦ 1704 ¦ 100.0% ¦ 8.7% ¦ 0d ¦ 0.09 ¦ ¦ ¦ **Overall** ¦ 100.0% ¦ 22.8% ¦ **463d** ¦ 0.228 ¦ ### Supporting Indicators - 🏗️ **Workfront Readiness**: 2.3% ⚠️ - 📅 **EOT Exposure**: 463d ¦ EOT Status: EOT Likely ? Forecast Exceeds Contract - 📋 **Data Freshness**: Recent ? Within Week (3d old) - 🔑 **Weakest Domain**: Construction 💬 *755 days of schedule recovery are required to meet the contractual completion date.* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:10.550486
2 | tool | L1 | Health | PEI — Missing project key (should list projects) | sra_status_pei | PEI — Missing project key (should list projects) | {} | WARN | Expected keywords missing: ['SPI', 'PEI', 'Programme'] | 0 |  | 📋 **Please specify the project to assess.** Available projects: (Unable to retrieve project list) 💡 Example: *What is the schedule health of project 101?* |  | 2026-02-27T09:56:10.551490
3 | tool | L1 | Health | PEI — Invalid project key (non-numeric) | sra_status_pei | PEI — Invalid project key (non-numeric) | {'project_key': 'ABC'} | WARN | Soft error in output: 'Invalid project key' | 0 |  | Invalid project key `ABC`. Please provide a numeric value (e.g. 101). |  | 2026-02-27T09:56:10.552487
4 | tool | L1 | Health | PEI — Non-existent project key | sra_status_pei | PEI — Non-existent project key | {'project_key': '9999'} | WARN | Soft error in output: 'No schedule data found' | 0.02 |  | No schedule data found for project key **9999**. Please verify the project reference. |  | 2026-02-27T09:56:10.567709
5 | tool | L1 | Activity | Activity — All activities, all domains | sra_activity_health | Activity — All activities, all domains | {'project_key': '101'} | WARN | Expected keywords missing: ['Status'] | 0.44 |  | ## 📋 Activity Health Review — Mega PWS in 11 block of Ganjam District *Domain filter: All ¦ Activity filter: All* **Summary** — Total: 2106 ¦ Complete: 277 ¦ In Progress: 291 ¦ Overdue / Not Mobilised: 0 ¦ Not Yet Due: 0 --- ### Activities Requiring Attention ✅ No activities are currently trending beyond their forecast completion. ### Workfront Constraint Watch **1828** activities have workfront readiness below 70.0%: ¦ Activity ¦ Domain ¦ Workfront % ¦ Gap Count ¦ Critical Path ¦ ¦----------¦--------¦-------------¦-----------¦---------------¦ ¦ None ¦ CON ¦ 0.0% ¦ 14 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ PCC ¦ CON ¦ 0.0% ¦ 1 ¦ No ¦ ¦ Reinforcement ¦ CON ¦ 0.0% ¦ 6 ¦ No ¦ ¦ Reinforcement ¦ CON ¦ 0.0% ¦ 8 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ RCC ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ Commissioning ¦ CON ¦ 0.0% ¦ 1 ¦ No ¦ ¦ RCC ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:11.005943
6 | tool | L1 | Activity | Activity — Engineering domain filter (ENG) | sra_activity_health | Activity — Engineering domain filter (ENG) | {'project_key': '101', 'domain_code': 'ENG'} | WARN | Expected keywords missing: ['Status'] | 0.1 |  | ## 📋 Activity Health Review — Mega PWS in 11 block of Ganjam District *Domain filter: ENG ¦ Activity filter: All* **Summary** — Total: 290 ¦ Complete: 194 ¦ In Progress: 72 ¦ Overdue / Not Mobilised: 0 ¦ Not Yet Due: 0 --- ### Activities Requiring Attention ✅ No activities are currently trending beyond their forecast completion. ### Workfront Constraint Watch **95** activities have workfront readiness below 70.0%: ¦ Activity ¦ Domain ¦ Workfront % ¦ Gap Count ¦ Critical Path ¦ ¦----------¦--------¦-------------¦-----------¦---------------¦ ¦ None ¦ ENG ¦ 0.0% ¦ 8 ¦ No ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 8 ¦ No ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 8 ¦ No ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 4 ¦ No ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 12 ¦ No ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 4 ¦ No ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 13 ¦ No ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 4 ¦ No ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 3 ¦ No ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 4 ¦ No ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:11.107910
7 | tool | L1 | Activity | Activity — Procurement domain filter (PRC) | sra_activity_health | Activity — Procurement domain filter (PRC) | {'project_key': '101', 'domain_code': 'PRC'} | WARN | Expected keywords missing: ['Status'] | 0.04 |  | ## 📋 Activity Health Review — Mega PWS in 11 block of Ganjam District *Domain filter: PRC ¦ Activity filter: All* **Summary** — Total: 112 ¦ Complete: 9 ¦ In Progress: 47 ¦ Overdue / Not Mobilised: 0 ¦ Not Yet Due: 0 --- ### Activities Requiring Attention ✅ No activities are currently trending beyond their forecast completion. ### Workfront Constraint Watch **103** activities have workfront readiness below 70.0%: ¦ Activity ¦ Domain ¦ Workfront % ¦ Gap Count ¦ Critical Path ¦ ¦----------¦--------¦-------------¦-----------¦---------------¦ ¦ Material Receipt Note ¦ PRC ¦ 0.0% ¦ 9 ¦ No ¦ ¦ Purchase Request ¦ PRC ¦ 0.0% ¦ 7 ¦ No ¦ ¦ Purchase Request ¦ PRC ¦ 0.0% ¦ 2 ¦ No ¦ ¦ Dispatch ¦ PRC ¦ 0.0% ¦ 29 ¦ No ¦ ¦ Purchase Order ¦ PRC ¦ 0.0% ¦ 29 ¦ No ¦ ¦ Material Receipt Note ¦ PRC ¦ 0.0% ¦ 40 ¦ No ¦ ¦ Manufacturing Clearence ¦ PRC ¦ 0.0% ¦ 21 ¦ No ¦ ¦ Dispatch ¦ PRC ¦ 0.0% ¦ 5 ¦ No ¦ ¦ None ¦ PRC ¦ 0.0% ¦ 6 ¦ No ¦ ¦ Inspection ¦ PRC ¦ 0.0% ¦ 40 ¦ No ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:11.149925
8 | tool | L1 | Activity | Activity — Construction domain filter (CON) | sra_activity_health | Activity — Construction domain filter (CON) | {'project_key': '101', 'domain_code': 'CON'} | WARN | Expected keywords missing: ['Status'] | 0.35 |  | ## 📋 Activity Health Review — Mega PWS in 11 block of Ganjam District *Domain filter: CON ¦ Activity filter: All* **Summary** — Total: 1704 ¦ Complete: 74 ¦ In Progress: 172 ¦ Overdue / Not Mobilised: 0 ¦ Not Yet Due: 0 --- ### Activities Requiring Attention ✅ No activities are currently trending beyond their forecast completion. ### Workfront Constraint Watch **1630** activities have workfront readiness below 70.0%: ¦ Activity ¦ Domain ¦ Workfront % ¦ Gap Count ¦ Critical Path ¦ ¦----------¦--------¦-------------¦-----------¦---------------¦ ¦ None ¦ CON ¦ 0.0% ¦ 14 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ PCC ¦ CON ¦ 0.0% ¦ 1 ¦ No ¦ ¦ Reinforcement ¦ CON ¦ 0.0% ¦ 6 ¦ No ¦ ¦ Reinforcement ¦ CON ¦ 0.0% ¦ 8 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ RCC ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ Commissioning ¦ CON ¦ 0.0% ¦ 1 ¦ No ¦ ¦ RCC ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:11.498225
9 | tool | L1 | Activity | Activity — No project key | sra_activity_health | Activity — No project key | {} | WARN | Expected keywords missing: ['Status', 'Domain', 'Workfront'] | 0 |  | 📋 **Specify the project for activity health review.** (Unable to retrieve project list) |  | 2026-02-27T09:56:11.499234
10 | tool | L1 | LookAhead | Task 2W — All domains, 2-week window | sra_task_lookahead | Task 2W — All domains, 2-week window | {'project_key': '101', 'window': '2W'} | PASS | All expected content present | 3.04 |  | ## 🗓️ 2-Week Look-Ahead — Mega PWS in 11 block of Ganjam District *Scope: All Domains ¦ Activity: All* **14868** tasks fall within the 2-week start window: — Workfront Available: **343** ¦ Workfront Constrained: **14525** ### Tasks Ready to Mobilise ✅ ¦ Task ¦ Activity ¦ Domain ¦ Forecast Start ¦ Forecast Finish ¦ Float ¦ Priority Score ¦ Critical ¦ ¦------¦----------¦--------¦---------------¦-----------------¦-------¦----------------¦----------¦ ¦ Architectural Detail of Filter House & Filter Annex Building for Scheme-2 ¦ — ¦ ENG ¦ 26 Feb ¦ 22 Jan ¦ — ¦ 40.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-18CHANDIPALLI-PR (BEGUNIAPADA) to Village (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 23 Feb ¦ 23 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-4 KANTAPADA-EX (BEGUNIAPADA) to Village (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 20 Feb ¦ 14 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-19 GHODAPADA-PR (BEGUNIAPADA) to Village (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 07 Feb ¦ 14 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-58 PAILIPADA-PR (BELAGUNTHA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 05 Feb ¦ 12 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-18 VENKATRAIPALLI-EX (ASKA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 07 Jan ¦ 17 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-10 SANTARPALLI(BARIDA)-PR (KS NAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 09 Jan ¦ 09 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-1 ARJUNAPALLI-EX (KS NAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 22 Feb ¦ 22 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-131 GOBARALUNDI-PR SORODA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 11 Jan ¦ 02 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme Diagram for Gravity Distribution main from OHT-14 TABHABANIA-PR (BEGUNIAPADA) to Village (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 19 Feb ¦ 14 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme drawing for Clear water Pumping main from CWR at WTP to OHTs & IBPS-1 - (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 16 Jan ¦ 16 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-104 DINDIPALLI-PR (BHANJNAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 23 Feb ¦ 19 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-42 MANGALAPUR -EX (BELAGUNTHA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 17 Feb ¦ 17 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-92 BEDIGOBA-PR (BHANJNAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 17 Jan ¦ 17 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-25 KUMBHARI-PR (ASKA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 11 Jan ¦ 02 Feb ¦ — ¦ 0.0 ¦ ¦ ### Workfront-Constrained Tasks — Action Required ⚠️ ¦ Task ¦ Activity ¦ Domain ¦ Forecast Start ¦ Float ¦ Block Flag ¦ ¦------¦----------¦--------¦---------------¦-------¦------------¦ ¦ Architectural Detail of Chlorine Building for Scheme-1 ¦ — ¦ ENG ¦ 26 Feb ¦ — ¦ Constrained ¦ ¦ Numeration and RC Detail of Cascade aerator, Parshall flume, Distribution chamber and Flash mixer for Scheme-1 ¦ — ¦ ENG ¦ 01 Jan ¦ — ¦ Constrained ¦ ¦ P&ID Drawing for CWR cum Pump House at IBPS-1- (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 11 Jan ¦ — ¦ Constrained ¦ ¦ Overall Single Line Diagram for IBPS 12 ¦ — ¦ ENG ¦ 14 Jan ¦ — ¦ Constrained ¦ ¦ MFC ¦ MFC ¦ PRC ¦ 16 Jan ¦ — ¦ Constrained ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 16 Jan ¦ — ¦ Constrained ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 08 Feb ¦ — ¦ Constrained ¦ ¦ Design Calculation of Intermediate Sump-1 for Scheme-1 ¦ — ¦ ENG ¦ 16 Feb ¦ — ¦ Constrained ¦ ¦ Instrument list for IBPS-5 ¦ — ¦ ENG ¦ 24 Jan ¦ — ¦ Constrained ¦ ¦ Lighting Layout for Intake ¦ — ¦ ENG ¦ 20 Jan ¦ — ¦ Constrained ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:14.540890
11 | tool | L1 | LookAhead | Task 4W — All domains, 4-week window | sra_task_lookahead | Task 4W — All domains, 4-week window | {'project_key': '101', 'window': '4W'} | PASS | All expected content present | 2.88 |  | ## 🗓️ 4-Week Look-Ahead — Mega PWS in 11 block of Ganjam District *Scope: All Domains ¦ Activity: All* **14868** tasks fall within the 4-week start window: — Workfront Available: **343** ¦ Workfront Constrained: **14525** ### Tasks Ready to Mobilise ✅ ¦ Task ¦ Activity ¦ Domain ¦ Forecast Start ¦ Forecast Finish ¦ Float ¦ Priority Score ¦ Critical ¦ ¦------¦----------¦--------¦---------------¦-----------------¦-------¦----------------¦----------¦ ¦ Architectural Detail of Filter House & Filter Annex Building for Scheme-2 ¦ — ¦ ENG ¦ 26 Feb ¦ 22 Jan ¦ — ¦ 40.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-18CHANDIPALLI-PR (BEGUNIAPADA) to Village (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 23 Feb ¦ 23 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-4 KANTAPADA-EX (BEGUNIAPADA) to Village (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 20 Feb ¦ 14 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-19 GHODAPADA-PR (BEGUNIAPADA) to Village (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 07 Feb ¦ 14 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-58 PAILIPADA-PR (BELAGUNTHA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 05 Feb ¦ 12 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-18 VENKATRAIPALLI-EX (ASKA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 07 Jan ¦ 17 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-10 SANTARPALLI(BARIDA)-PR (KS NAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 09 Jan ¦ 09 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-1 ARJUNAPALLI-EX (KS NAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 22 Feb ¦ 22 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-131 GOBARALUNDI-PR SORODA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 11 Jan ¦ 02 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme Diagram for Gravity Distribution main from OHT-14 TABHABANIA-PR (BEGUNIAPADA) to Village (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 19 Feb ¦ 14 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme drawing for Clear water Pumping main from CWR at WTP to OHTs & IBPS-1 - (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 16 Jan ¦ 16 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-104 DINDIPALLI-PR (BHANJNAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 23 Feb ¦ 19 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-42 MANGALAPUR -EX (BELAGUNTHA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 17 Feb ¦ 17 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-92 BEDIGOBA-PR (BHANJNAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 17 Jan ¦ 17 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-25 KUMBHARI-PR (ASKA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 11 Jan ¦ 02 Feb ¦ — ¦ 0.0 ¦ ¦ ### Workfront-Constrained Tasks — Action Required ⚠️ ¦ Task ¦ Activity ¦ Domain ¦ Forecast Start ¦ Float ¦ Block Flag ¦ ¦------¦----------¦--------¦---------------¦-------¦------------¦ ¦ Architectural Detail of Chlorine Building for Scheme-1 ¦ — ¦ ENG ¦ 26 Feb ¦ — ¦ Constrained ¦ ¦ Numeration and RC Detail of Cascade aerator, Parshall flume, Distribution chamber and Flash mixer for Scheme-1 ¦ — ¦ ENG ¦ 01 Jan ¦ — ¦ Constrained ¦ ¦ P&ID Drawing for CWR cum Pump House at IBPS-1- (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 11 Jan ¦ — ¦ Constrained ¦ ¦ Overall Single Line Diagram for IBPS 12 ¦ — ¦ ENG ¦ 14 Jan ¦ — ¦ Constrained ¦ ¦ MFC ¦ MFC ¦ PRC ¦ 16 Jan ¦ — ¦ Constrained ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 16 Jan ¦ — ¦ Constrained ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 08 Feb ¦ — ¦ Constrained ¦ ¦ Design Calculation of Intermediate Sump-1 for Scheme-1 ¦ — ¦ ENG ¦ 16 Feb ¦ — ¦ Constrained ¦ ¦ Instrument list for IBPS-5 ¦ — ¦ ENG ¦ 24 Jan ¦ — ¦ Constrained ¦ ¦ Lighting Layout for Intake ¦ — ¦ ENG ¦ 20 Jan ¦ — ¦ Constrained ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:17.422127
12 | tool | L1 | LookAhead | Task 2W — Construction domain only | sra_task_lookahead | Task 2W — Construction domain only | {'project_key': '101', 'window': '2W', 'domain_code': 'CON'} | PASS | All expected content present | 2.95 |  | ## 🗓️ 2-Week Look-Ahead — Mega PWS in 11 block of Ganjam District *Scope: CON ¦ Activity: All* **10991** tasks fall within the 2-week start window: — Workfront Available: **0** ¦ Workfront Constrained: **10991** ### Tasks Ready to Mobilise ✅ No workfront-available tasks in the look-ahead window. ### Workfront-Constrained Tasks — Action Required ⚠️ ¦ Task ¦ Activity ¦ Domain ¦ Forecast Start ¦ Float ¦ Block Flag ¦ ¦------¦----------¦--------¦---------------¦-------¦------------¦ ¦ Plastering ESR tank portion ¦ Plastering ¦ CON ¦ 01 Jan ¦ — ¦ Constrained ¦ ¦ Shuttering- upto FGL ¦ Shuttering ¦ CON ¦ 22 Jan ¦ — ¦ Constrained ¦ ¦ Disposal of excess earth ¦ — ¦ CON ¦ 22 Jan ¦ — ¦ Constrained ¦ ¦ Plastering ¦ Plastering ¦ CON ¦ 01 Jan ¦ — ¦ Constrained ¦ ¦ Stainless steel Ladder ¦ — ¦ CON ¦ 01 Jan ¦ — ¦ Constrained ¦ ¦ Shuttering - upto bottom slab ¦ — ¦ CON ¦ — ¦ — ¦ Constrained ¦ ¦ SS handrail ¦ — ¦ CON ¦ 22 Jan ¦ — ¦ Constrained ¦ ¦ Commissioning ¦ Commissioning ¦ CON ¦ 17 Feb ¦ — ¦ Constrained ¦ ¦ Hard barrication ¦ — ¦ CON ¦ — ¦ — ¦ Constrained ¦ ¦ Earthwork in Excavation in ordinary soil 1.5m - 3m ¦ — ¦ CON ¦ 22 Jan ¦ — ¦ Constrained ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:20.369763
13 | tool | L1 | LookAhead | Task 4W — Engineering domain only | sra_task_lookahead | Task 4W — Engineering domain only | {'project_key': '101', 'window': '4W', 'domain_code': 'ENG'} | PASS | All expected content present | 2.84 |  | ## 🗓️ 4-Week Look-Ahead — Mega PWS in 11 block of Ganjam District *Scope: ENG ¦ Activity: All* **2694** tasks fall within the 4-week start window: — Workfront Available: **343** ¦ Workfront Constrained: **2351** ### Tasks Ready to Mobilise ✅ ¦ Task ¦ Activity ¦ Domain ¦ Forecast Start ¦ Forecast Finish ¦ Float ¦ Priority Score ¦ Critical ¦ ¦------¦----------¦--------¦---------------¦-----------------¦-------¦----------------¦----------¦ ¦ Architectural Detail of Filter House & Filter Annex Building for Scheme-2 ¦ — ¦ ENG ¦ 26 Feb ¦ 22 Jan ¦ — ¦ 40.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-18CHANDIPALLI-PR (BEGUNIAPADA) to Village (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 23 Feb ¦ 23 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-4 KANTAPADA-EX (BEGUNIAPADA) to Village (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 20 Feb ¦ 14 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-19 GHODAPADA-PR (BEGUNIAPADA) to Village (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 07 Feb ¦ 14 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-58 PAILIPADA-PR (BELAGUNTHA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 05 Feb ¦ 12 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-18 VENKATRAIPALLI-EX (ASKA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 07 Jan ¦ 17 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-10 SANTARPALLI(BARIDA)-PR (KS NAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 09 Jan ¦ 09 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-1 ARJUNAPALLI-EX (KS NAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 22 Feb ¦ 22 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-131 GOBARALUNDI-PR SORODA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 11 Jan ¦ 02 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme Diagram for Gravity Distribution main from OHT-14 TABHABANIA-PR (BEGUNIAPADA) to Village (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 19 Feb ¦ 14 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme drawing for Clear water Pumping main from CWR at WTP to OHTs & IBPS-1 - (Ganjam Scheme-2) ¦ — ¦ ENG ¦ 16 Jan ¦ 16 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-104 DINDIPALLI-PR (BHANJNAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 23 Feb ¦ 19 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-42 MANGALAPUR -EX (BELAGUNTHA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 17 Feb ¦ 17 Feb ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-92 BEDIGOBA-PR (BHANJNAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 17 Jan ¦ 17 Jan ¦ — ¦ 0.0 ¦ ¦ ¦ Scheme diagram for Gravity Distribution main from OHT-25 KUMBHARI-PR (ASKA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 11 Jan ¦ 02 Feb ¦ — ¦ 0.0 ¦ ¦ ### Workfront-Constrained Tasks — Action Required ⚠️ ¦ Task ¦ Activity ¦ Domain ¦ Forecast Start ¦ Float ¦ Block Flag ¦ ¦------¦----------¦--------¦---------------¦-------¦------------¦ ¦ Architectural Detail of Chlorine Building for Scheme-1 ¦ — ¦ ENG ¦ 26 Feb ¦ — ¦ Constrained ¦ ¦ Numeration and RC Detail of Cascade aerator, Parshall flume, Distribution chamber and Flash mixer for Scheme-1 ¦ — ¦ ENG ¦ 01 Jan ¦ — ¦ Constrained ¦ ¦ P&ID Drawing for CWR cum Pump House at IBPS-1- (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 11 Jan ¦ — ¦ Constrained ¦ ¦ Overall Single Line Diagram for IBPS 12 ¦ — ¦ ENG ¦ 14 Jan ¦ — ¦ Constrained ¦ ¦ Design Calculation of Intermediate Sump-1 for Scheme-1 ¦ — ¦ ENG ¦ 16 Feb ¦ — ¦ Constrained ¦ ¦ Instrument list for IBPS-5 ¦ — ¦ ENG ¦ 24 Jan ¦ — ¦ Constrained ¦ ¦ Lighting Layout for Intake ¦ — ¦ ENG ¦ 20 Jan ¦ — ¦ Constrained ¦ ¦ 33/11 kV Switchyard Layout for IBPS 1 ¦ — ¦ ENG ¦ 14 Jan ¦ — ¦ Constrained ¦ ¦ Surge Analysis Report for Clear water Pumping main from IBPS-09 (PM-2) to OHTs Ganjam WSS (Scheme-1) ¦ — ¦ ENG ¦ 30 Jan ¦ — ¦ Constrained ¦ ¦ Control And Interlock Details for IBPS-4 ¦ — ¦ ENG ¦ 24 Jan ¦ — ¦ Constrained ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:23.210848
14 | tool | L1 | LookAhead | Task 2W — Procurement domain only | sra_task_lookahead | Task 2W — Procurement domain only | {'project_key': '101', 'window': '2W', 'domain_code': 'PRC'} | PASS | All expected content present | 2.99 |  | ## 🗓️ 2-Week Look-Ahead — Mega PWS in 11 block of Ganjam District *Scope: PRC ¦ Activity: All* **1183** tasks fall within the 2-week start window: — Workfront Available: **0** ¦ Workfront Constrained: **1183** ### Tasks Ready to Mobilise ✅ No workfront-available tasks in the look-ahead window. ### Workfront-Constrained Tasks — Action Required ⚠️ ¦ Task ¦ Activity ¦ Domain ¦ Forecast Start ¦ Float ¦ Block Flag ¦ ¦------¦----------¦--------¦---------------¦-------¦------------¦ ¦ MFC ¦ MFC ¦ PRC ¦ 16 Jan ¦ — ¦ Constrained ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 16 Jan ¦ — ¦ Constrained ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 08 Feb ¦ — ¦ Constrained ¦ ¦ MRN ¦ MRN ¦ PRC ¦ 27 Feb ¦ — ¦ Constrained ¦ ¦ PR ¦ PR ¦ PRC ¦ 22 Jan ¦ — ¦ Constrained ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 16 Jan ¦ — ¦ Constrained ¦ ¦ PO ¦ PO ¦ PRC ¦ 16 Jan ¦ — ¦ Constrained ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 16 Jan ¦ — ¦ Constrained ¦ ¦ PR ¦ PR ¦ PRC ¦ 02 Mar ¦ — ¦ Constrained ¦ ¦ PO ¦ PO ¦ PRC ¦ 16 Jan ¦ — ¦ Constrained ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:26.203806
15 | tool | L1 | LookAhead | Task 2W — No project key | sra_task_lookahead | Task 2W — No project key | {} | WARN | Expected keywords missing: ['Task', 'Forecast'] | 0 |  | 📋 **Specify the project for the look-ahead window.** (Unable to retrieve project list) |  | 2026-02-27T09:56:26.205261
16 | tool | L2 | CritPath | Critical Path — Full project CP analysis | sra_critical_path | Critical Path — Full project CP analysis | {'project_key': '101'} | PASS | All expected content present | 2.97 |  | ## 🔴 Critical Path Analysis — Mega PWS in 11 block of Ganjam District **CP Task Count**: 0 ¦ **Total Tasks**: 14868 --- ### Float Distribution Summary ¦ Float Band ¦ Task Count ¦ % of Programme ¦ ¦-----------¦-----------¦----------------¦ ¦ 🔴 Negative Float ¦ 0 ¦ 0.0% ¦ ¦ 🔴 Zero Float (Critical) ¦ 0 ¦ 0.0% ¦ ¦ 🟡 Near-Critical (≤5d) ¦ 0 ¦ 0.0% ¦ ¦ 🟢 Healthy Float ¦ 0 ¦ 0.0% ¦ ¦ **Project Min Float** ¦ — ¦ **0d** ¦ ¦ **Average Float** ¦ — ¦ **0d** ¦ ### Controlling Critical Path Tasks (Top 15) No critical path tasks identified under current float parameters. --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:29.171490
17 | tool | L2 | CritPath | Critical Path — No project key | sra_critical_path | Critical Path — No project key | {} | WARN | Expected keywords missing: ['Float', 'CP'] | 0 |  | 📋 **Specify the project for critical path analysis.** (Unable to retrieve project list) |  | 2026-02-27T09:56:29.172490
18 | tool | L2 | CritPath | Critical Path — Non-existent project | sra_critical_path | Critical Path — Non-existent project | {'project_key': '9999'} | WARN | Soft error in output: 'No schedule data found' | 0.01 |  | No schedule data found for project key **9999**. |  | 2026-02-27T09:56:29.181159
19 | tool | L2 | Float | Float — Full programme float analysis | sra_float_analysis | Float — Full programme float analysis | {'project_key': '101'} | PASS | All expected content present | 0.42 |  | ## ⏳ Float Analysis & Near-Critical Watch — Mega PWS in 11 block of Ganjam District **Programme Float Health**: — ¦ **At-Risk Float**: 0.0% ¦ **Min Float**: 0d --- ### Near-Critical Activity Watch (Float ≤ 5 days) ✅ No activities are within the 5-day near-critical threshold. ### Float Erosion Watch ✅ No float erosion flags are currently active across the selected scope. ⚠️ **54 activities have breached the Critical Activity Density (CAD) threshold** — these require schedule management escalation. --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:29.600963
20 | tool | L2 | Float | Float — Construction domain float watch | sra_float_analysis | Float — Construction domain float watch | {'project_key': '101', 'domain_code': 'CON'} | PASS | All expected content present | 0.5 |  | ## ⏳ Float Analysis & Near-Critical Watch — Mega PWS in 11 block of Ganjam District **Programme Float Health**: — ¦ **At-Risk Float**: 0.0% ¦ **Min Float**: 0d --- ### Near-Critical Activity Watch (Float ≤ 5 days) ✅ No activities are within the 5-day near-critical threshold. ### Float Erosion Watch ✅ No float erosion flags are currently active across the selected scope. --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:30.102553
21 | tool | L2 | Float | Float — Engineering domain float watch | sra_float_analysis | Float — Engineering domain float watch | {'project_key': '101', 'domain_code': 'ENG'} | PASS | All expected content present | 0.44 |  | ## ⏳ Float Analysis & Near-Critical Watch — Mega PWS in 11 block of Ganjam District **Programme Float Health**: — ¦ **At-Risk Float**: 0.0% ¦ **Min Float**: 0d --- ### Near-Critical Activity Watch (Float ≤ 5 days) ✅ No activities are within the 5-day near-critical threshold. ### Float Erosion Watch ✅ No float erosion flags are currently active across the selected scope. ⚠️ **19 activities have breached the Critical Activity Density (CAD) threshold** — these require schedule management escalation. --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:30.540142
22 | tool | L2 | Float | Float — Procurement domain float watch | sra_float_analysis | Float — Procurement domain float watch | {'project_key': '101', 'domain_code': 'PRC'} | PASS | All expected content present | 0.4 |  | ## ⏳ Float Analysis & Near-Critical Watch — Mega PWS in 11 block of Ganjam District **Programme Float Health**: — ¦ **At-Risk Float**: 0.0% ¦ **Min Float**: 0d --- ### Near-Critical Activity Watch (Float ≤ 5 days) ✅ No activities are within the 5-day near-critical threshold. ### Float Erosion Watch ✅ No float erosion flags are currently active across the selected scope. ⚠️ **35 activities have breached the Critical Activity Density (CAD) threshold** — these require schedule management escalation. --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:30.944182
23 | tool | L2 | Float | Float — No project key | sra_float_analysis | Float — No project key | {} | WARN | Expected keywords missing: ['Near-Critical', 'Erosion'] | 0 |  | 📋 **Specify the project for float analysis.** (Unable to retrieve project list) |  | 2026-02-27T09:56:30.945182
24 | tool | L2 | Rate | Productivity — Full rate gap analysis | sra_productivity_rate | Productivity — Full rate gap analysis | {'project_key': '101'} | PASS | All expected content present | 0.41 |  | ## ⚡ Productivity & Rate Analysis — Mega PWS in 11 block of Ganjam District *Scope: All Domains ¦ Activity: All* **Executable Progress (Overall)**: 0.2% ¦ **E**: 0.0% **P**: 3.5% **C**: 0.1% --- ### Execution Rate Gap — Activities Below Required Rate *A rate shortfall is a leading indicator of schedule slippage — even activities marked In Progress can drive future delays if the production rate is below what the plan demands.* **1714** activities are tracking below the required progress rate: ¦ Activity ¦ Domain ¦ Planned % ¦ Achieved % ¦ Variance ¦ Required Rate/Day ¦ Earned Qty ¦ Planned Qty ¦ ¦----------¦--------¦-----------¦------------¦----------¦-------------------¦-----------¦-------------¦ ¦ None ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.61728 ¦ 0.0 ¦ 74.9 ¦ ¦ PCC ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ -3.22581 ¦ 0.0 ¦ 352.6 ¦ ¦ Reinforcement ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 7.69231 ¦ 0.0 ¦ 2935.0 ¦ ¦ Reinforcement ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 3.125 ¦ 0.0 ¦ 1800.0 ¦ ¦ Shuttering ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.44843 ¦ 0.0 ¦ 16029.2 ¦ ¦ RCC ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.45662 ¦ 0.0 ¦ 1320.0 ¦ ¦ Shuttering ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ -3.84615 ¦ 0.0 ¦ 2033.9 ¦ ¦ Commissioning ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.5291 ¦ 0.0 ¦ 82.0 ¦ ¦ RCC ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 1.0101 ¦ 0.0 ¦ 151.7 ¦ ¦ Reinforcement ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 5.26316 ¦ 0.0 ¦ 151.1 ¦ ¦ Plastering ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.53476 ¦ 0.0 ¦ 22479.5 ¦ ¦ Plastering ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.4065 ¦ 0.0 ¦ 25476.7 ¦ ¦ Reinforcement ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ -4.34783 ¦ 0.0 ¦ 72.1 ¦ ¦ PCC ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 11.11111 ¦ 0.0 ¦ 102.7 ¦ ¦ Shuttering ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.45045 ¦ 0.0 ¦ 106864.3 ¦ ¦ Reinforcement ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.65359 ¦ 0.0 ¦ 51.9 ¦ ¦ Material Receipt Note ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.50761 ¦ 0.0 ¦ 6525.0 ¦ ¦ None ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.72993 ¦ 0.0 ¦ 38993.5 ¦ ¦ PCC ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ -3.44828 ¦ 0.0 ¦ 77.7 ¦ ¦ None ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ -2.94118 ¦ 0.0 ¦ 1230.0 ¦ ### Top Contributors to Project Progress ¦ Activity ¦ Domain ¦ Contribution % ¦ SPI ¦ Status ¦ ¦----------¦--------¦----------------¦-----¦--------¦ ¦ Laying & Jointing ¦ CON ¦ 3.1% ¦ 0.37 ¦ In Progress ¦ ¦ Laying & Jointing ¦ CON ¦ 2.1% ¦ 0.00 ¦ Pending ¦ ¦ Laying & Jointing ¦ CON ¦ 1.6% ¦ 0.76 ¦ In Progress ¦ ¦ Purchase Order ¦ PRC ¦ 1.0% ¦ 0.28 ¦ In Progress ¦ ¦ None ¦ CON ¦ 0.9% ¦ 0.21 ¦ In Progress ¦ ¦ Inspection ¦ PRC ¦ 0.8% ¦ 0.28 ¦ In Progress ¦ ¦ Laying & Jointing ¦ CON ¦ 0.8% ¦ 0.29 ¦ In Progress ¦ ¦ HSC Installation ¦ CON ¦ 0.7% ¦ 1.00 ¦ In Progress ¦ ¦ Laying & Jointing ¦ CON ¦ 0.6% ¦ 0.00 ¦ Pending ¦ ¦ Laying & Jointing ¦ CON ¦ 0.6% ¦ 0.41 ¦ In Progress ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:31.351198
25 | tool | L2 | Rate | Productivity — Construction rate analysis | sra_productivity_rate | Productivity — Construction rate analysis | {'project_key': '101', 'domain_code': 'CON'} | PASS | All expected content present | 0.42 |  | ## ⚡ Productivity & Rate Analysis — Mega PWS in 11 block of Ganjam District *Scope: CON ¦ Activity: All* **Executable Progress (Overall)**: 0.2% ¦ **E**: 0.0% **P**: 3.5% **C**: 0.1% --- ### Execution Rate Gap — Activities Below Required Rate *A rate shortfall is a leading indicator of schedule slippage — even activities marked In Progress can drive future delays if the production rate is below what the plan demands.* **1612** activities are tracking below the required progress rate: ¦ Activity ¦ Domain ¦ Planned % ¦ Achieved % ¦ Variance ¦ Required Rate/Day ¦ Earned Qty ¦ Planned Qty ¦ ¦----------¦--------¦-----------¦------------¦----------¦-------------------¦-----------¦-------------¦ ¦ None ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.61728 ¦ 0.0 ¦ 74.9 ¦ ¦ PCC ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ -3.22581 ¦ 0.0 ¦ 352.6 ¦ ¦ Reinforcement ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 7.69231 ¦ 0.0 ¦ 2935.0 ¦ ¦ Reinforcement ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 3.125 ¦ 0.0 ¦ 1800.0 ¦ ¦ Shuttering ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.44843 ¦ 0.0 ¦ 16029.2 ¦ ¦ RCC ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.45662 ¦ 0.0 ¦ 1320.0 ¦ ¦ Shuttering ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ -3.84615 ¦ 0.0 ¦ 2033.9 ¦ ¦ Commissioning ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.5291 ¦ 0.0 ¦ 82.0 ¦ ¦ RCC ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 1.0101 ¦ 0.0 ¦ 151.7 ¦ ¦ Reinforcement ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 5.26316 ¦ 0.0 ¦ 151.1 ¦ ¦ Plastering ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.53476 ¦ 0.0 ¦ 22479.5 ¦ ¦ Plastering ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.4065 ¦ 0.0 ¦ 25476.7 ¦ ¦ Reinforcement ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ -4.34783 ¦ 0.0 ¦ 72.1 ¦ ¦ PCC ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 11.11111 ¦ 0.0 ¦ 102.7 ¦ ¦ Shuttering ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.45045 ¦ 0.0 ¦ 106864.3 ¦ ¦ Reinforcement ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.65359 ¦ 0.0 ¦ 51.9 ¦ ¦ None ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.72993 ¦ 0.0 ¦ 38993.5 ¦ ¦ PCC ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ -3.44828 ¦ 0.0 ¦ 77.7 ¦ ¦ None ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ -2.94118 ¦ 0.0 ¦ 1230.0 ¦ ¦ Plastering ¦ CON ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 1.16279 ¦ 0.0 ¦ 1838.3 ¦ ### Top Contributors to Project Progress ¦ Activity ¦ Domain ¦ Contribution % ¦ SPI ¦ Status ¦ ¦----------¦--------¦----------------¦-----¦--------¦ ¦ Laying & Jointing ¦ CON ¦ 3.1% ¦ 0.37 ¦ In Progress ¦ ¦ Laying & Jointing ¦ CON ¦ 2.1% ¦ 0.00 ¦ Pending ¦ ¦ Laying & Jointing ¦ CON ¦ 1.6% ¦ 0.76 ¦ In Progress ¦ ¦ None ¦ CON ¦ 0.9% ¦ 0.21 ¦ In Progress ¦ ¦ Laying & Jointing ¦ CON ¦ 0.8% ¦ 0.29 ¦ In Progress ¦ ¦ HSC Installation ¦ CON ¦ 0.7% ¦ 1.00 ¦ In Progress ¦ ¦ Laying & Jointing ¦ CON ¦ 0.6% ¦ 0.00 ¦ Pending ¦ ¦ Laying & Jointing ¦ CON ¦ 0.6% ¦ 0.41 ¦ In Progress ¦ ¦ None ¦ CON ¦ 0.6% ¦ 0.00 ¦ Pending ¦ ¦ None ¦ CON ¦ 0.5% ¦ 0.48 ¦ In Progress ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:31.773396
26 | tool | L2 | Rate | Productivity — Engineering rate analysis | sra_productivity_rate | Productivity — Engineering rate analysis | {'project_key': '101', 'domain_code': 'ENG'} | WARN | Expected keywords missing: ['Earned', 'Planned'] | 0.43 |  | ## ⚡ Productivity & Rate Analysis — Mega PWS in 11 block of Ganjam District *Scope: ENG ¦ Activity: All* **Executable Progress (Overall)**: 0.2% ¦ **E**: 0.0% **P**: 3.5% **C**: 0.1% --- ### Execution Rate Gap — Activities Below Required Rate *A rate shortfall is a leading indicator of schedule slippage — even activities marked In Progress can drive future delays if the production rate is below what the plan demands.* ✅ All active activities are tracking at or above the required progress rate. ### Top Contributors to Project Progress ¦ Activity ¦ Domain ¦ Contribution % ¦ SPI ¦ Status ¦ ¦----------¦--------¦----------------¦-----¦--------¦ ¦ None ¦ ENG ¦ 0.1% ¦ 0.85 ¦ In Progress ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 0.00 ¦ Pending ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 1.00 ¦ Complete ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 0.00 ¦ Pending ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 1.00 ¦ Complete ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 1.00 ¦ Complete ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 1.00 ¦ Complete ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 0.00 ¦ Pending ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 1.00 ¦ Complete ¦ ¦ None ¦ ENG ¦ 0.0% ¦ 1.00 ¦ Complete ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:32.203966
27 | tool | L2 | Rate | Productivity — Procurement rate analysis | sra_productivity_rate | Productivity — Procurement rate analysis | {'project_key': '101', 'domain_code': 'PRC'} | PASS | All expected content present | 0.42 |  | ## ⚡ Productivity & Rate Analysis — Mega PWS in 11 block of Ganjam District *Scope: PRC ¦ Activity: All* **Executable Progress (Overall)**: 0.2% ¦ **E**: 0.0% **P**: 3.5% **C**: 0.1% --- ### Execution Rate Gap — Activities Below Required Rate *A rate shortfall is a leading indicator of schedule slippage — even activities marked In Progress can drive future delays if the production rate is below what the plan demands.* **102** activities are tracking below the required progress rate: ¦ Activity ¦ Domain ¦ Planned % ¦ Achieved % ¦ Variance ¦ Required Rate/Day ¦ Earned Qty ¦ Planned Qty ¦ ¦----------¦--------¦-----------¦------------¦----------¦-------------------¦-----------¦-------------¦ ¦ Material Receipt Note ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.50761 ¦ 0.0 ¦ 6525.0 ¦ ¦ Purchase Request ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 1.04167 ¦ — ¦ 113940.6 ¦ ¦ Dispatch ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 1.04167 ¦ — ¦ 2545.9 ¦ ¦ Purchase Order ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 1.04167 ¦ — ¦ 2545.9 ¦ ¦ Material Receipt Note ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.43103 ¦ — ¦ 128268.0 ¦ ¦ None ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 1.04167 ¦ — ¦ 19680.0 ¦ ¦ Inspection ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.43103 ¦ — ¦ 128268.0 ¦ ¦ Dispatch ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.43103 ¦ — ¦ 128268.0 ¦ ¦ None ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.43103 ¦ — ¦ 128268.0 ¦ ¦ Purchase Order ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 1.04167 ¦ — ¦ 19680.0 ¦ ¦ Purchase Request ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.50761 ¦ — ¦ 6525.0 ¦ ¦ Purchase Request ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 1.04167 ¦ — ¦ 19680.0 ¦ ¦ Material Receipt Note ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 1.04167 ¦ — ¦ 41580.0 ¦ ¦ Purchase Request ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.43103 ¦ — ¦ 128268.0 ¦ ¦ Manufacturing Clearence ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.43103 ¦ — ¦ 128268.0 ¦ ¦ Inspection ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 1.04167 ¦ — ¦ 2545.9 ¦ ¦ Purchase Order ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 1.04167 ¦ — ¦ 113940.6 ¦ ¦ None ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.43103 ¦ — ¦ 128268.0 ¦ ¦ Dispatch ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 1.04167 ¦ — ¦ 19680.0 ¦ ¦ Inspection ¦ PRC ¦ 100.0% ¦ 0.0% ¦ -100.0% ¦ 0.50761 ¦ — ¦ 6525.0 ¦ ### Top Contributors to Project Progress ¦ Activity ¦ Domain ¦ Contribution % ¦ SPI ¦ Status ¦ ¦----------¦--------¦----------------¦-----¦--------¦ ¦ Purchase Order ¦ PRC ¦ 1.0% ¦ 0.28 ¦ In Progress ¦ ¦ Inspection ¦ PRC ¦ 0.8% ¦ 0.28 ¦ In Progress ¦ ¦ None ¦ PRC ¦ 0.6% ¦ 0.28 ¦ In Progress ¦ ¦ Manufacturing Clearence ¦ PRC ¦ 0.6% ¦ 0.28 ¦ In Progress ¦ ¦ Material Receipt Note ¦ PRC ¦ 0.4% ¦ 0.28 ¦ In Progress ¦ ¦ Dispatch ¦ PRC ¦ 0.4% ¦ 0.28 ¦ In Progress ¦ ¦ Purchase Request ¦ PRC ¦ 0.2% ¦ 0.63 ¦ In Progress ¦ ¦ Purchase Order ¦ PRC ¦ 0.1% ¦ 0.70 ¦ In Progress ¦ ¦ Purchase Order ¦ PRC ¦ 0.1% ¦ 1.00 ¦ Complete ¦ ¦ Purchase Order ¦ PRC ¦ 0.1% ¦ 1.00 ¦ Complete ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:32.625037
28 | tool | L2 | Rate | Productivity — No project key | sra_productivity_rate | Productivity — No project key | {} | WARN | Expected keywords missing: ['Progress', 'Earned', 'Planned'] | 0 |  | 📋 **Specify the project for productivity rate analysis.** (Unable to retrieve project list) |  | 2026-02-27T09:56:32.625037
29 | tool | L3 | Baseline | Baseline — JCR/PMS dates, drift analysis | sra_baseline_management | Baseline — JCR/PMS dates, drift analysis | {'project_key': '101'} | PASS | All expected content present | 0.42 |  | ## 📐 Baseline Management — Mega PWS in 11 block of Ganjam District ### Approved Schedule Reference Points ¦ Baseline Marker ¦ Date ¦ Notes ¦ ¦----------------¦------¦-------¦ ¦ **Original Baseline Start** ¦ 01 Jan 1970 ¦ JCR-approved programme start ¦ ¦ **Original Baseline Finish** ¦ 31 Jan 1970 ¦ JCR-approved completion ¦ ¦ **JCR Approved Date** ¦ 01 Jan 1970 ¦ Joint Construction Review ¦ ¦ **PMS Approved Date** ¦ 01 Jan 1970 ¦ Project Management Schedule ¦ ¦ **Rescheduled Baseline** ¦ 21 Jan 1970 ¦ Current approved revision ¦ ¦ **Contractual Completion** ¦ 01 Jan 1970 ¦ Client contract date ¦ ¦ **Forecast Completion** ¦ 24 Jan 1970 ¦ Current projection ¦ ### Baseline Drift Summary ¦ Drift Metric ¦ Value ¦ Assessment ¦ ¦-------------¦-------¦------------¦ ¦ Baseline vs Rescheduled Slip ¦ -14 ¦ Approved revision from original ¦ ¦ Current vs Rescheduled Slip ¦ 555 ¦ Forecast drift from revision ¦ ¦ Overall Slip Days ¦ 541d ¦ Baseline to forecast ¦ ¦ Schedule Variance ¦ -541d ¦ Earned vs planned ¦ ¦ **Baseline Integrity** ¦ **Significant Drift ? Review Required** ¦ ⬜ ¦ ### Activities with Baseline Drift ✅ All activities are tracking within their approved baseline parameters. --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:33.046356
30 | tool | L3 | Baseline | Baseline — No project key | sra_baseline_management | Baseline — No project key | {} | WARN | Expected keywords missing: ['Drift', 'JCR', 'Slip'] | 0 |  | 📋 **Specify the project for baseline management review.** (Unable to retrieve project list) |  | 2026-02-27T09:56:33.046356
31 | tool | L3 | Baseline | Baseline — Non-existent project | sra_baseline_management | Baseline — Non-existent project | {'project_key': '9999'} | WARN | Soft error in output: 'No schedule data found' | 0.01 |  | No schedule data found for project key **9999**. |  | 2026-02-27T09:56:33.061292
32 | tool | L3 | Quality | Quality — Data freshness + LAC compliance (full) | sra_schedule_quality | Quality — Data freshness + LAC compliance (full) | {'project_key': '101'} | PASS | All expected content present | 0.01 |  | ## 🔎 Schedule Quality & Integrity — Mega PWS in 11 block of Ganjam District ### Data Freshness ¦ Indicator ¦ Value ¦ ¦-----------¦-------¦ ¦ Dashboard As-On Date ¦ 31 Jan 1970 ¦ ¦ Data Age ¦ 3d ¦ ¦ Freshness Status ¦ Recent ? Within Week ¦ ### Look-Ahead Compliance (LAC) *LAC measures the percentage of look-ahead commitments that were executed on time. A reading below 80% indicates a disconnect between short-term planning and site execution.* ¦ Domain ¦ LAC (Week) ¦ LAC (Month) ¦ Overdue Rules ¦ At-Risk 7d ¦ At-Risk 30d ¦ Pending ¦ ¦--------¦------------¦-------------¦---------------¦-----------¦------------¦--------¦ ¦ 🔴 **Construction** ¦ 0.0% ¦ 0.0% ¦ 1 ¦ 1 ¦ 1 ¦ 1 ¦ ¦ 🔴 **Procurement** ¦ 0.0% ¦ 0.0% ¦ 1 ¦ 0 ¦ 0 ¦ 0 ¦ ### Activity Completion Health ¦ Status ¦ Count ¦ Rate ¦ ¦--------¦-------¦------¦ ¦ Total Activities ¦ 14868 ¦ — ¦ ¦ Complete ¦ 2348 ¦ 15.8% ¦ ¦ In Progress ¦ 1878 ¦ — ¦ ¦ Overdue / Not Mobilised ¦ 1323 ¦ 8.9% ¦ ¦ Not Yet Due ¦ — ¦ — ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:33.075426
33 | tool | L3 | Quality | Quality — No project key | sra_schedule_quality | Quality — No project key | {} | WARN | Expected keywords missing: ['LAC', 'Compliance', 'Data Freshness'] | 0 |  | 📋 **Specify the project for schedule quality review.** (Unable to retrieve project list) |  | 2026-02-27T09:56:33.077427
34 | tool | L3 | Quality | Quality — Non-existent project | sra_schedule_quality | Quality — Non-existent project | {'project_key': '9999'} | WARN | Soft error in output: 'No schedule data found' | 0.01 |  | No schedule data found for project key **9999**. |  | 2026-02-27T09:56:33.091672
35 | tool | L4 | Delay | Delay — Full delay & risk analysis | sra_drill_delay | Delay — Full delay & risk analysis | {'project_key': '101'} | PASS | All expected content present | 0.47 |  | ## 🔍 Delay & Risk Analysis — Mega PWS in 11 block of Ganjam District **Location**: Ganjam, Odisha. ¦ **Forecast Delay (Overall)**: 463d **Delay by Domain** — E: 390d P: 476d C: 463d 🔴 **Delay Hotspot Domain**: Procurement ¦ **Concentration Domain**: Procurement ⚠️ **Delay Risk Classification**: High ? Escalate --- ### Top Activities Contributing to Schedule Slippage **1980** activities are tracking beyond their forecast completion (0 on critical path): ¦ Activity ¦ Domain ¦ Status ¦ Delay (d) ¦ Critical ¦ Workfront ¦ Delay Source ¦ Severity ¦ ¦----------¦--------¦--------¦-----------¦----------¦-----------¦--------------¦----------¦ ¦ None ¦ ENG ¦ Complete ¦ 60d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ None ¦ ENG ¦ Complete ¦ 60d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Dispatch ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Material Receipt Note ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Plastering ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ None ¦ ENG ¦ Complete ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Inspection ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ None ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ RCC ¦ CON ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Shuttering ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Laying & Jointing ¦ CON ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ None ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ RCC ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Manufacturing Clearence ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Reinforcement ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ### Workfront & Access Constraints **1828** active activities have workfront readiness below 70.0% — unresolved constraints are a primary driver of execution shortfall: ¦ Activity ¦ Domain ¦ Readiness % ¦ Gap Count ¦ Critical ¦ ¦----------¦--------¦-------------¦-----------¦----------¦ ¦ None ¦ CON ¦ 0.0% ¦ 14 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ PCC ¦ CON ¦ 0.0% ¦ 1 ¦ No ¦ ¦ Reinforcement ¦ CON ¦ 0.0% ¦ 6 ¦ No ¦ ¦ Reinforcement ¦ CON ¦ 0.0% ¦ 8 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ RCC ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ Commissioning ¦ CON ¦ 0.0% ¦ 1 ¦ No ¦ ¦ RCC ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ### Summary Statistics - Total Activities: **2106** - Activities with Forecast Slippage: **1980** - Critical Path Activities Slipping: **0** - Average Activity Delay: **23.9d** - Workfront-Constrained Activities: **1828** --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:33.562595
36 | tool | L4 | Delay | Delay — With start/end date window | sra_drill_delay | Delay — With start/end date window | {'project_key': '101', 'start_date': '2025-01-01', 'end_date': '2025-06-30'} | PASS | All expected content present | 0.43 |  | ## 🔍 Delay & Risk Analysis — Mega PWS in 11 block of Ganjam District **Location**: Ganjam, Odisha. ¦ **Forecast Delay (Overall)**: 463d **Delay by Domain** — E: 390d P: 476d C: 463d 🔴 **Delay Hotspot Domain**: Procurement ¦ **Concentration Domain**: Procurement ⚠️ **Delay Risk Classification**: High ? Escalate --- ### Top Activities Contributing to Schedule Slippage **1980** activities are tracking beyond their forecast completion (0 on critical path): ¦ Activity ¦ Domain ¦ Status ¦ Delay (d) ¦ Critical ¦ Workfront ¦ Delay Source ¦ Severity ¦ ¦----------¦--------¦--------¦-----------¦----------¦-----------¦--------------¦----------¦ ¦ None ¦ ENG ¦ Complete ¦ 60d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ None ¦ ENG ¦ Complete ¦ 60d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Dispatch ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Material Receipt Note ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Plastering ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ None ¦ ENG ¦ Complete ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Inspection ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ None ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ RCC ¦ CON ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Shuttering ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Laying & Jointing ¦ CON ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ None ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ RCC ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Manufacturing Clearence ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Reinforcement ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ### Workfront & Access Constraints **1828** active activities have workfront readiness below 70.0% — unresolved constraints are a primary driver of execution shortfall: ¦ Activity ¦ Domain ¦ Readiness % ¦ Gap Count ¦ Critical ¦ ¦----------¦--------¦-------------¦-----------¦----------¦ ¦ None ¦ CON ¦ 0.0% ¦ 14 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ PCC ¦ CON ¦ 0.0% ¦ 1 ¦ No ¦ ¦ Reinforcement ¦ CON ¦ 0.0% ¦ 6 ¦ No ¦ ¦ Reinforcement ¦ CON ¦ 0.0% ¦ 8 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ RCC ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ Commissioning ¦ CON ¦ 0.0% ¦ 1 ¦ No ¦ ¦ RCC ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ### Summary Statistics - Total Activities: **2106** - Activities with Forecast Slippage: **1980** - Critical Path Activities Slipping: **0** - Average Activity Delay: **23.9d** - Workfront-Constrained Activities: **1828** --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:33.992756
37 | tool | L4 | Delay | Delay — Q3 2025 date window | sra_drill_delay | Delay — Q3 2025 date window | {'project_key': '101', 'start_date': '2025-07-01', 'end_date': '2025-09-30'} | PASS | All expected content present | 0.41 |  | ## 🔍 Delay & Risk Analysis — Mega PWS in 11 block of Ganjam District **Location**: Ganjam, Odisha. ¦ **Forecast Delay (Overall)**: 463d **Delay by Domain** — E: 390d P: 476d C: 463d 🔴 **Delay Hotspot Domain**: Procurement ¦ **Concentration Domain**: Procurement ⚠️ **Delay Risk Classification**: High ? Escalate --- ### Top Activities Contributing to Schedule Slippage **1980** activities are tracking beyond their forecast completion (0 on critical path): ¦ Activity ¦ Domain ¦ Status ¦ Delay (d) ¦ Critical ¦ Workfront ¦ Delay Source ¦ Severity ¦ ¦----------¦--------¦--------¦-----------¦----------¦-----------¦--------------¦----------¦ ¦ None ¦ ENG ¦ Complete ¦ 60d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ None ¦ ENG ¦ Complete ¦ 60d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Dispatch ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Material Receipt Note ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Plastering ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ None ¦ ENG ¦ Complete ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Inspection ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ None ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ RCC ¦ CON ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Shuttering ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Laying & Jointing ¦ CON ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ None ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ RCC ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Manufacturing Clearence ¦ PRC ¦ In Progress ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ¦ Reinforcement ¦ CON ¦ Pending ¦ 59d ¦ No ¦ ⚠️ 0.0% ¦ Progress Delay Only ¦ On Track ¦ ### Workfront & Access Constraints **1828** active activities have workfront readiness below 70.0% — unresolved constraints are a primary driver of execution shortfall: ¦ Activity ¦ Domain ¦ Readiness % ¦ Gap Count ¦ Critical ¦ ¦----------¦--------¦-------------¦-----------¦----------¦ ¦ None ¦ CON ¦ 0.0% ¦ 14 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ PCC ¦ CON ¦ 0.0% ¦ 1 ¦ No ¦ ¦ Reinforcement ¦ CON ¦ 0.0% ¦ 6 ¦ No ¦ ¦ Reinforcement ¦ CON ¦ 0.0% ¦ 8 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ RCC ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ Shuttering ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ¦ Commissioning ¦ CON ¦ 0.0% ¦ 1 ¦ No ¦ ¦ RCC ¦ CON ¦ 0.0% ¦ 7 ¦ No ¦ ### Summary Statistics - Total Activities: **2106** - Activities with Forecast Slippage: **1980** - Critical Path Activities Slipping: **0** - Average Activity Delay: **23.9d** - Workfront-Constrained Activities: **1828** --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:34.405055
38 | tool | L4 | Delay | Delay — No project key | sra_drill_delay | Delay — No project key | {} | WARN | Expected keywords missing: ['Hotspot', 'Workfront'] | 0 |  | 📋 **Please specify the project for delay analysis.** Available projects: (Unable to retrieve project list) 💡 Example: *Analyse delay exposure for project 101* |  | 2026-02-27T09:56:34.406053
39 | tool | L4 | Delay | Delay — Non-existent project | sra_drill_delay | Delay — Non-existent project | {'project_key': '9999'} | WARN | Soft error in output: 'No schedule data found' | 0.01 |  | No schedule data found for project key **9999**. |  | 2026-02-27T09:56:34.414001
40 | tool | L4 | Procurement | PRC — Procurement rule alignment (full) | sra_procurement_alignment | PRC — Procurement rule alignment (full) | {'project_key': '101'} | PASS | All expected content present | 0.66 |  | ## 📦 Procurement & Material Schedule Alignment — Mega PWS in 11 block of Ganjam District ### Procurement LAC Compliance ¦ Metric ¦ Week ¦ Month ¦ RAG ¦ ¦--------¦------¦-------¦-----¦ ¦ 🔴 PRC LAC Compliance ¦ 0.0% ¦ 0.0% ¦ Red ¦ ### Procurement Rule Status ¦ Rule Category ¦ Count ¦ ¦--------------¦-------¦ ¦ Overdue Rules ¦ 🔴 1 ¦ ¦ At Risk (7-day window) ¦ 🟡 0 ¦ ¦ At Risk (30-day window) ¦ 🟡 0 ¦ ¦ Pending ¦ 0 ¦ ¦ Completed ¦ 0 ¦ ### Activity-Level Procurement Risk **5** activities have procurement rules at risk of non-compliance: ¦ Activity ¦ Domain ¦ Total Rules ¦ Overdue ¦ At Risk 7d ¦ At Risk 30d ¦ LAC Week ¦ ¦----------¦--------¦-------------¦---------¦------------¦------------¦----------¦ ¦ Dispatch ¦ PRC ¦ 1 ¦ 🔴 1 ¦ 🟡 0 ¦ 0 ¦ 0.0% ¦ ¦ None ¦ PRC ¦ 1 ¦ 🔴 1 ¦ 🟡 0 ¦ 0 ¦ 0.0% ¦ ¦ Inspection ¦ PRC ¦ 1 ¦ 🔴 1 ¦ 🟡 0 ¦ 0 ¦ 0.0% ¦ ¦ Manufacturing Clearence ¦ PRC ¦ 1 ¦ 🔴 1 ¦ 🟡 0 ¦ 0 ¦ 0.0% ¦ ¦ Purchase Order ¦ PRC ¦ 1 ¦ 🔴 1 ¦ 🟡 0 ¦ 0 ¦ 0.0% ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:35.077525
41 | tool | L4 | Procurement | PRC — No project key | sra_procurement_alignment | PRC — No project key | {} | WARN | Expected keywords missing: ['PRC', 'LAC'] | 0 |  | 📋 **Specify the project for procurement alignment review.** (Unable to retrieve project list) |  | 2026-02-27T09:56:35.078523
42 | tool | L4 | Procurement | PRC — Non-existent project | sra_procurement_alignment | PRC — Non-existent project | {'project_key': '9999'} | WARN | Soft error in output: 'No schedule data found' | 0.01 |  | No schedule data found for project key **9999**. |  | 2026-02-27T09:56:35.090693
43 | tool | L4 | EOT | EOT — Exposure and contractual buffer analysis | sra_eot_exposure | EOT — Exposure and contractual buffer analysis | {'project_key': '101'} | PASS | All expected content present | 0.01 |  | ## ⚖️ EOT Exposure & Contractual Buffer — Mega PWS in 11 block of Ganjam District ¦ Contractual Metric ¦ Value ¦ Assessment ¦ ¦-------------------¦-------¦------------¦ ¦ Contractual Completion Date ¦ 01 Jan 1970 ¦ Client contract ¦ ¦ Forecast Completion Date ¦ 24 Jan 1970 ¦ Current projection ¦ ¦ Days to Contractual End ¦ -240d ¦ Remaining contractual window ¦ ¦ Days to Forecast End ¦ 515d ¦ Remaining programme window ¦ ¦ **EOT Exposure** ¦ **463d** ¦ 🔴 Delay beyond contractual end ¦ ¦ EOT Buffer ¦ -755d ¦ Approved buffer before breach ¦ ¦ **EOT RAG Status** ¦ **Red** ¦ 🔴 ¦ ¦ EOT Eligibility ¦ EOT Likely ? Forecast Exceeds Contract ¦ Contractual entitlement assessment ¦ ### Schedule Recovery Requirement ¦ Recovery Metric ¦ Value ¦ ¦----------------¦-------¦ ¦ Schedule Recovery Required ¦ 755d ¦ ¦ Recovery SPI Required ¦ -3.034 ¦ ¦ Recovery Plan Status ¦ Formal Recovery Plan Required ¦ ¦ Compression Headroom ¦ 0.0% ¦ ⚠️ **The project is currently tracking 463 days beyond the contractual completion date.** An EOT submission may be warranted — review entitlement basis. --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:35.103231
44 | tool | L4 | EOT | EOT — No project key | sra_eot_exposure | EOT — No project key | {} | WARN | Expected keywords missing: ['Contractual', 'Buffer'] | 0 |  | 📋 **Specify the project for EOT exposure assessment.** (Unable to retrieve project list) |  | 2026-02-27T09:56:35.104231
45 | tool | L4 | EOT | EOT — Non-existent project | sra_eot_exposure | EOT — Non-existent project | {'project_key': '9999'} | WARN | Soft error in output: 'No schedule data found' | 0.01 |  | No schedule data found for project key **9999**. |  | 2026-02-27T09:56:35.112823
46 | tool | L5 | Recovery | Recovery — Generic options (no resource type) | sra_recovery_advise | Recovery — Generic options (no resource type) | {'project_key': '101'} | PASS | All expected content present | 0.42 |  | ## 🔧 Recovery Planning — Mega PWS in 11 block of Ganjam District ### Current Programme Position ¦ Metric ¦ Value ¦ ¦--------¦-------¦ ¦ PEI ¦ 1.606 ¦ ¦ SPI ¦ 0.228 ¦ ¦ Forecast Delay ¦ 463d ¦ ¦ Recovery Required ¦ 755d ¦ ¦ Workfront Readiness ¦ 0% ¦ ¦ Compression Headroom ¦ 0.0% ¦ ¦ Recovery Plan Status ¦ Formal Recovery Plan Required ¦ --- ### Recovery Strategy Options **Option 1 — Resource Augmentation** 👷 - Deploy additional crews to critical path and near-critical activities - Applicable where workfront is available and site capacity permits - Estimated programme recovery: 3–5 days per fortnight of augmentation - Risk level: Medium — quality assurance protocols must be maintained **Option 2 — Schedule Compression (Crashing)** ⏱️ - Introduce extended working hours or additional shifts on critical path activities - Compression headroom available: 0.0% - Estimated programme recovery: 5–8 days - Risk level: Medium — premium cost increase of approximately 12–18% **Option 3 — Fast-Tracking** 🚀 - Introduce concurrent execution of activities currently sequenced in series - Applicable where logical dependencies permit parallel working - Estimated programme recovery: 4–7 days - Risk level: High — increased coordination and interface management required **Option 4 — Resequencing & Scope Deferral** 📋 - Advance high-priority critical path deliverables; defer non-critical scope - Requires stakeholder alignment and change management approval - Estimated programme recovery: 2–4 days - Risk level: Low-Medium — contract implications to be assessed **Option 5 — Workfront Constraint Resolution** 🚧 - Only 0% of activities have confirmed workfront availability - 2101 activities are constrained by material delivery, RoW, or access clearance - Resolving constraints unlocks execution capacity and is the highest-leverage intervention - Coordinate with procurement, land, and logistics teams immediately - Estimated programme recovery: 5–12 days depending on constraint type - Risk level: Low — this is process-driven, not cost-driven --- 💬 *Select an option to simulate its schedule impact, or request that a recovery action be logged for the site planning team.* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:35.528137
47 | tool | L5 | Recovery | Recovery — Labor-targeted recovery advice | sra_recovery_advise | Recovery — Labor-targeted recovery advice | {'project_key': '101', 'resource_type': 'labor'} | PASS | All expected content present | 0.41 |  | ## 🔧 Recovery Planning — Mega PWS in 11 block of Ganjam District ### Current Programme Position ¦ Metric ¦ Value ¦ ¦--------¦-------¦ ¦ PEI ¦ 1.606 ¦ ¦ SPI ¦ 0.228 ¦ ¦ Forecast Delay ¦ 463d ¦ ¦ Recovery Required ¦ 755d ¦ ¦ Workfront Readiness ¦ 0% ¦ ¦ Compression Headroom ¦ 0.0% ¦ ¦ Recovery Plan Status ¦ Formal Recovery Plan Required ¦ --- ### Recovery Strategy Options **Option 1 — Resource Augmentation** 👷 - Deploy additional crews to critical path and near-critical activities - Targeted resource type: labor - Applicable where workfront is available and site capacity permits - Estimated programme recovery: 3–5 days per fortnight of augmentation - Risk level: Medium — quality assurance protocols must be maintained **Option 2 — Schedule Compression (Crashing)** ⏱️ - Introduce extended working hours or additional shifts on critical path activities - Compression headroom available: 0.0% - Estimated programme recovery: 5–8 days - Risk level: Medium — premium cost increase of approximately 12–18% **Option 3 — Fast-Tracking** 🚀 - Introduce concurrent execution of activities currently sequenced in series - Applicable where logical dependencies permit parallel working - Estimated programme recovery: 4–7 days - Risk level: High — increased coordination and interface management required **Option 4 — Resequencing & Scope Deferral** 📋 - Advance high-priority critical path deliverables; defer non-critical scope - Requires stakeholder alignment and change management approval - Estimated programme recovery: 2–4 days - Risk level: Low-Medium — contract implications to be assessed **Option 5 — Workfront Constraint Resolution** 🚧 - Only 0% of activities have confirmed workfront availability - 2101 activities are constrained by material delivery, RoW, or access clearance - Resolving constraints unlocks execution capacity and is the highest-leverage intervention - Coordinate with procurement, land, and logistics teams immediately - Estimated programme recovery: 5–12 days depending on constraint type - Risk level: Low — this is process-driven, not cost-driven --- 💬 *Select an option to simulate its schedule impact, or request that a recovery action be logged for the site planning team.* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:35.941051
48 | tool | L5 | Recovery | Recovery — Equipment-targeted recovery advice | sra_recovery_advise | Recovery — Equipment-targeted recovery advice | {'project_key': '101', 'resource_type': 'equipment'} | PASS | All expected content present | 0.53 |  | ## 🔧 Recovery Planning — Mega PWS in 11 block of Ganjam District ### Current Programme Position ¦ Metric ¦ Value ¦ ¦--------¦-------¦ ¦ PEI ¦ 1.606 ¦ ¦ SPI ¦ 0.228 ¦ ¦ Forecast Delay ¦ 463d ¦ ¦ Recovery Required ¦ 755d ¦ ¦ Workfront Readiness ¦ 0% ¦ ¦ Compression Headroom ¦ 0.0% ¦ ¦ Recovery Plan Status ¦ Formal Recovery Plan Required ¦ --- ### Recovery Strategy Options **Option 1 — Resource Augmentation** 👷 - Deploy additional crews to critical path and near-critical activities - Targeted resource type: equipment - Applicable where workfront is available and site capacity permits - Estimated programme recovery: 3–5 days per fortnight of augmentation - Risk level: Medium — quality assurance protocols must be maintained **Option 2 — Schedule Compression (Crashing)** ⏱️ - Introduce extended working hours or additional shifts on critical path activities - Compression headroom available: 0.0% - Estimated programme recovery: 5–8 days - Risk level: Medium — premium cost increase of approximately 12–18% **Option 3 — Fast-Tracking** 🚀 - Introduce concurrent execution of activities currently sequenced in series - Applicable where logical dependencies permit parallel working - Estimated programme recovery: 4–7 days - Risk level: High — increased coordination and interface management required **Option 4 — Resequencing & Scope Deferral** 📋 - Advance high-priority critical path deliverables; defer non-critical scope - Requires stakeholder alignment and change management approval - Estimated programme recovery: 2–4 days - Risk level: Low-Medium — contract implications to be assessed **Option 5 — Workfront Constraint Resolution** 🚧 - Only 0% of activities have confirmed workfront availability - 2101 activities are constrained by material delivery, RoW, or access clearance - Resolving constraints unlocks execution capacity and is the highest-leverage intervention - Coordinate with procurement, land, and logistics teams immediately - Estimated programme recovery: 5–12 days depending on constraint type - Risk level: Low — this is process-driven, not cost-driven --- 💬 *Select an option to simulate its schedule impact, or request that a recovery action be logged for the site planning team.* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:36.468812
49 | tool | L5 | Recovery | Recovery — Material-targeted recovery advice | sra_recovery_advise | Recovery — Material-targeted recovery advice | {'project_key': '101', 'resource_type': 'material'} | PASS | All expected content present | 0.41 |  | ## 🔧 Recovery Planning — Mega PWS in 11 block of Ganjam District ### Current Programme Position ¦ Metric ¦ Value ¦ ¦--------¦-------¦ ¦ PEI ¦ 1.606 ¦ ¦ SPI ¦ 0.228 ¦ ¦ Forecast Delay ¦ 463d ¦ ¦ Recovery Required ¦ 755d ¦ ¦ Workfront Readiness ¦ 0% ¦ ¦ Compression Headroom ¦ 0.0% ¦ ¦ Recovery Plan Status ¦ Formal Recovery Plan Required ¦ --- ### Recovery Strategy Options **Option 1 — Resource Augmentation** 👷 - Deploy additional crews to critical path and near-critical activities - Targeted resource type: material - Applicable where workfront is available and site capacity permits - Estimated programme recovery: 3–5 days per fortnight of augmentation - Risk level: Medium — quality assurance protocols must be maintained **Option 2 — Schedule Compression (Crashing)** ⏱️ - Introduce extended working hours or additional shifts on critical path activities - Compression headroom available: 0.0% - Estimated programme recovery: 5–8 days - Risk level: Medium — premium cost increase of approximately 12–18% **Option 3 — Fast-Tracking** 🚀 - Introduce concurrent execution of activities currently sequenced in series - Applicable where logical dependencies permit parallel working - Estimated programme recovery: 4–7 days - Risk level: High — increased coordination and interface management required **Option 4 — Resequencing & Scope Deferral** 📋 - Advance high-priority critical path deliverables; defer non-critical scope - Requires stakeholder alignment and change management approval - Estimated programme recovery: 2–4 days - Risk level: Low-Medium — contract implications to be assessed **Option 5 — Workfront Constraint Resolution** 🚧 - Only 0% of activities have confirmed workfront availability - 2101 activities are constrained by material delivery, RoW, or access clearance - Resolving constraints unlocks execution capacity and is the highest-leverage intervention - Coordinate with procurement, land, and logistics teams immediately - Estimated programme recovery: 5–12 days depending on constraint type - Risk level: Low — this is process-driven, not cost-driven --- 💬 *Select an option to simulate its schedule impact, or request that a recovery action be logged for the site planning team.* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:36.882528
50 | tool | L5 | Recovery | Recovery — Activity-focused (activity_id provided) | sra_recovery_advise | Recovery — Activity-focused (activity_id provided) | {'project_key': '101', 'resource_type': 'labor', 'activity_id': 'ACT-001'} | PASS | All expected content present | 0.4 |  | ## 🔧 Recovery Planning — Mega PWS in 11 block of Ganjam District ### Current Programme Position ¦ Metric ¦ Value ¦ ¦--------¦-------¦ ¦ PEI ¦ 1.606 ¦ ¦ SPI ¦ 0.228 ¦ ¦ Forecast Delay ¦ 463d ¦ ¦ Recovery Required ¦ 755d ¦ ¦ Workfront Readiness ¦ 0% ¦ ¦ Compression Headroom ¦ 0.0% ¦ ¦ Recovery Plan Status ¦ Formal Recovery Plan Required ¦ --- ### Recovery Strategy Options **Option 1 — Resource Augmentation** 👷 - Deploy additional crews to critical path and near-critical activities - Targeted resource type: labor - Applicable where workfront is available and site capacity permits - Estimated programme recovery: 3–5 days per fortnight of augmentation - Risk level: Medium — quality assurance protocols must be maintained **Option 2 — Schedule Compression (Crashing)** ⏱️ - Introduce extended working hours or additional shifts on critical path activities - Compression headroom available: 0.0% - Estimated programme recovery: 5–8 days - Risk level: Medium — premium cost increase of approximately 12–18% **Option 3 — Fast-Tracking** 🚀 - Introduce concurrent execution of activities currently sequenced in series - Recommended focal point: activity ACT-001 - Applicable where logical dependencies permit parallel working - Estimated programme recovery: 4–7 days - Risk level: High — increased coordination and interface management required **Option 4 — Resequencing & Scope Deferral** 📋 - Advance high-priority critical path deliverables; defer non-critical scope - Requires stakeholder alignment and change management approval - Estimated programme recovery: 2–4 days - Risk level: Low-Medium — contract implications to be assessed **Option 5 — Workfront Constraint Resolution** 🚧 - Only 0% of activities have confirmed workfront availability - 2101 activities are constrained by material delivery, RoW, or access clearance - Resolving constraints unlocks execution capacity and is the highest-leverage intervention - Coordinate with procurement, land, and logistics teams immediately - Estimated programme recovery: 5–12 days depending on constraint type - Risk level: Low — this is process-driven, not cost-driven --- 💬 *Select an option to simulate its schedule impact, or request that a recovery action be logged for the site planning team.* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:37.279574
51 | tool | L5 | Recovery | Recovery — No project key | sra_recovery_advise | Recovery — No project key | {} | WARN | Expected keywords missing: ['Workfront'] | 0 |  | 📋 **Specify the project for recovery planning.** (Unable to retrieve project list) 💡 Example: *What are the recovery options for project 101?* |  | 2026-02-27T09:56:37.280572
52 | tool | L5 | Simulate | Simulate — 2 shuttering gangs | sra_simulate | Simulate — 2 shuttering gangs | {'project_key': '101', 'resource_type': 'shuttering_gang', 'value_amount': 2} | PASS | All expected content present | 0.01 |  | ## 📊 Scenario Analysis — Mega PWS in 11 block of Ganjam District **Scenario**: Deploy 2 × shuttering_gang --- ### Projected Programme Impact ¦ Metric ¦ Current ¦ Projected ¦ Change ¦ ¦--------¦---------¦-----------¦--------¦ ¦ Forecast Delay ¦ 463d ¦ 325d ¦ **−138d** ¦ ¦ SPI ¦ 0.228 ¦ 0.258 ¦ +0.030 ¦ ¦ Productivity Rate ¦ Baseline ¦ +30.0% ¦ ✅ Enhanced ¦ ### Cost Impact - **Incremental Cost Estimate**: ₹50,000 - **Cost per Day Recovered**: ₹362 ### Risk & Implementation Considerations - Coordination overhead with newly mobilised teams; site induction and productivity ramp-up period applies. - Confirm impact on concurrent activities and interface obligations before deployment - Review against EOT entitlement basis if acceleration cost is to be claimed --- 💬 *Shall I log this scenario as an approved recovery action for the planning team?* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:37.289090
53 | tool | L5 | Simulate | Simulate — 5 additional labor (manpower) | sra_simulate | Simulate — 5 additional labor (manpower) | {'project_key': '101', 'resource_type': 'labor', 'value_amount': 5} | PASS | All expected content present | 0.01 |  | ## 📊 Scenario Analysis — Mega PWS in 11 block of Ganjam District **Scenario**: Deploy 5 × labor --- ### Projected Programme Impact ¦ Metric ¦ Current ¦ Projected ¦ Change ¦ ¦--------¦---------¦-----------¦--------¦ ¦ Forecast Delay ¦ 463d ¦ 348d ¦ **−115d** ¦ ¦ SPI ¦ 0.228 ¦ 0.253 ¦ +0.025 ¦ ¦ Productivity Rate ¦ Baseline ¦ +25.0% ¦ ✅ Enhanced ¦ ### Cost Impact - **Incremental Cost Estimate**: ₹25,000 - **Cost per Day Recovered**: ₹217 ### Risk & Implementation Considerations - Workforce absorption capacity and supervisory ratio should be validated before deployment. - Confirm impact on concurrent activities and interface obligations before deployment - Review against EOT entitlement basis if acceleration cost is to be claimed --- 💬 *Shall I log this scenario as an approved recovery action for the planning team?* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:37.302088
54 | tool | L5 | Simulate | Simulate — 1 excavator deployment | sra_simulate | Simulate — 1 excavator deployment | {'project_key': '101', 'resource_type': 'equipment', 'value_amount': 1} | PASS | All expected content present | 0.01 |  | ## 📊 Scenario Analysis — Mega PWS in 11 block of Ganjam District **Scenario**: Deploy 1 × equipment --- ### Projected Programme Impact ¦ Metric ¦ Current ¦ Projected ¦ Change ¦ ¦--------¦---------¦-----------¦--------¦ ¦ Forecast Delay ¦ 463d ¦ 371d ¦ **−92d** ¦ ¦ SPI ¦ 0.228 ¦ 0.248 ¦ +0.020 ¦ ¦ Productivity Rate ¦ Baseline ¦ +20.0% ¦ ✅ Enhanced ¦ ### Cost Impact - **Incremental Cost Estimate**: ₹50,000 - **Cost per Day Recovered**: ₹543 ### Risk & Implementation Considerations - Equipment mobilisation lead time and site access must be confirmed prior to deployment. - Confirm impact on concurrent activities and interface obligations before deployment - Review against EOT entitlement basis if acceleration cost is to be claimed --- 💬 *Shall I log this scenario as an approved recovery action for the planning team?* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:37.311854
55 | tool | L5 | Simulate | Simulate — Sunday overtime working | sra_simulate | Simulate — Sunday overtime working | {'project_key': '101', 'resource_type': 'overtime', 'value_amount': 1, 'date_range': 'this Sunday'} | PASS | All expected content present | 0.01 |  | ## 📊 Scenario Analysis — Mega PWS in 11 block of Ganjam District **Scenario**: Deploy 1 × overtime (this Sunday) --- ### Projected Programme Impact ¦ Metric ¦ Current ¦ Projected ¦ Change ¦ ¦--------¦---------¦-----------¦--------¦ ¦ Forecast Delay ¦ 463d ¦ 408d ¦ **−55d** ¦ ¦ SPI ¦ 0.228 ¦ 0.240 ¦ +0.012 ¦ ¦ Productivity Rate ¦ Baseline ¦ +12.0% ¦ ✅ Enhanced ¦ ### Cost Impact - **Incremental Cost Estimate**: ₹15,000 - **Cost per Day Recovered**: ₹273 ### Risk & Implementation Considerations - Fatigue management protocols apply; overtime premium rates and quality oversight must be maintained. - Confirm impact on concurrent activities and interface obligations before deployment - Review against EOT entitlement basis if acceleration cost is to be claimed --- 💬 *Shall I log this scenario as an approved recovery action for the planning team?* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:37.319532
56 | tool | L5 | Simulate | Simulate — Extended hours with date range | sra_simulate | Simulate — Extended hours with date range | {'project_key': '101', 'resource_type': 'extended_hours', 'value_amount': 8, 'date_range': '2025-07-15 to 2025-07-20'} | PASS | All expected content present | 0.01 |  | ## 📊 Scenario Analysis — Mega PWS in 11 block of Ganjam District **Scenario**: Deploy 8 × extended_hours (2025-07-15 to 2025-07-20) --- ### Projected Programme Impact ¦ Metric ¦ Current ¦ Projected ¦ Change ¦ ¦--------¦---------¦-----------¦--------¦ ¦ Forecast Delay ¦ 463d ¦ 408d ¦ **−55d** ¦ ¦ SPI ¦ 0.228 ¦ 0.240 ¦ +0.012 ¦ ¦ Productivity Rate ¦ Baseline ¦ +12.0% ¦ ✅ Enhanced ¦ ### Cost Impact - **Incremental Cost Estimate**: ₹15,000 - **Cost per Day Recovered**: ₹273 ### Risk & Implementation Considerations - Fatigue management protocols apply; overtime premium rates and quality oversight must be maintained. - Confirm impact on concurrent activities and interface obligations before deployment - Review against EOT entitlement basis if acceleration cost is to be claimed --- 💬 *Shall I log this scenario as an approved recovery action for the planning team?* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:37.328539
57 | tool | L5 | Simulate | Simulate — 3 formwork gangs with date | sra_simulate | Simulate — 3 formwork gangs with date | {'project_key': '101', 'resource_type': 'formwork_gang', 'value_amount': 3, 'date_range': 'next fortnight'} | PASS | All expected content present | 0.01 |  | ## 📊 Scenario Analysis — Mega PWS in 11 block of Ganjam District **Scenario**: Deploy 3 × formwork_gang (next fortnight) --- ### Projected Programme Impact ¦ Metric ¦ Current ¦ Projected ¦ Change ¦ ¦--------¦---------¦-----------¦--------¦ ¦ Forecast Delay ¦ 463d ¦ 255d ¦ **−208d** ¦ ¦ SPI ¦ 0.228 ¦ 0.273 ¦ +0.045 ¦ ¦ Productivity Rate ¦ Baseline ¦ +45.0% ¦ ✅ Enhanced ¦ ### Cost Impact - **Incremental Cost Estimate**: ₹75,000 - **Cost per Day Recovered**: ₹361 ### Risk & Implementation Considerations - Coordination overhead with newly mobilised teams; site induction and productivity ramp-up period applies. - Confirm impact on concurrent activities and interface obligations before deployment - Review against EOT entitlement basis if acceleration cost is to be claimed --- 💬 *Shall I log this scenario as an approved recovery action for the planning team?* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:37.338061
58 | tool | L5 | Simulate | Simulate — Missing resource type (should prompt) | sra_simulate | Simulate — Missing resource type (should prompt) | {'project_key': '101'} | WARN | Expected keywords missing: ['Projected', 'Programme Impact'] | 0 |  | 📋 **Additional details required to run the scenario:** **Resource Type** — e.g. shuttering_gang / labor / equipment / overtime **Quantity** — e.g. 2 (gangs), 8 (overtime hours) 💡 Example: *What if I add 2 shuttering gangs to project 101?* |  | 2026-02-27T09:56:37.339059
59 | tool | L5 | Simulate | Simulate — Missing all params (should prompt) | sra_simulate | Simulate — Missing all params (should prompt) | {} | WARN | Expected keywords missing: ['Projected', 'Programme Impact'] | 0 |  | 📋 **Additional details required to run the scenario:** **Project** — which project? (Unable to retrieve project list) **Resource Type** — e.g. shuttering_gang / labor / equipment / overtime **Quantity** — e.g. 2 (gangs), 8 (overtime hours) 💡 Example: *What if I add 2 shuttering gangs to project 101?* |  | 2026-02-27T09:56:37.340059
60 | tool | L5 | Actions | Create Action — Approve Option 1 (resource augmentation) | sra_create_action | Create Action — Approve Option 1 (resource augmentation) | {'project_key': '101', 'action_choice': 'Approve Option 1 — Resource Augmentation', 'user_id': 'site_planner'} | PASS | All expected content present | 0.01 |  | ## ✅ Recovery Action Logged **Action ID**: `ACT-101-20260227095637` --- ### Action Record ¦ Field ¦ Detail ¦ ¦-------¦--------¦ ¦ Project ¦ Mega PWS in 11 block of Ganjam District (Key: 101) ¦ ¦ Action ¦ Approve Option 1 — Resource Augmentation ¦ ¦ Assigned To ¦ site_planner ¦ ¦ Status ¦ 🟡 **Open — Pending Execution** ¦ ¦ Logged ¦ 27 Feb 2026 09:56 ¦ ### Current Programme Context - PEI: 1.606 - SPI: 0.228 - Forecast Delay: 463d - EOT Exposure: 463d 💡 *This action has been logged for tracking. The assigned team member will receive notification for follow-through.* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:37.348048
61 | tool | L5 | Actions | Create Action — Approve Option 2 (schedule compression) | sra_create_action | Create Action — Approve Option 2 (schedule compression) | {'project_key': '101', 'action_choice': 'Approve Option 2 — Schedule Compression', 'user_id': 'planning_manager'} | PASS | All expected content present | 0.01 |  | ## ✅ Recovery Action Logged **Action ID**: `ACT-101-20260227095637` --- ### Action Record ¦ Field ¦ Detail ¦ ¦-------¦--------¦ ¦ Project ¦ Mega PWS in 11 block of Ganjam District (Key: 101) ¦ ¦ Action ¦ Approve Option 2 — Schedule Compression ¦ ¦ Assigned To ¦ planning_manager ¦ ¦ Status ¦ 🟡 **Open — Pending Execution** ¦ ¦ Logged ¦ 27 Feb 2026 09:56 ¦ ### Current Programme Context - PEI: 1.606 - SPI: 0.228 - Forecast Delay: 463d - EOT Exposure: 463d 💡 *This action has been logged for tracking. The assigned team member will receive notification for follow-through.* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:37.359049
62 | tool | L5 | Actions | Create Action — Fast-track decision | sra_create_action | Create Action — Fast-track decision | {'project_key': '101', 'action_choice': 'Approve Option 3 — Fast-Tracking', 'user_id': 'project_director'} | PASS | All expected content present | 0.01 |  | ## ✅ Recovery Action Logged **Action ID**: `ACT-101-20260227095637` --- ### Action Record ¦ Field ¦ Detail ¦ ¦-------¦--------¦ ¦ Project ¦ Mega PWS in 11 block of Ganjam District (Key: 101) ¦ ¦ Action ¦ Approve Option 3 — Fast-Tracking ¦ ¦ Assigned To ¦ project_director ¦ ¦ Status ¦ 🟡 **Open — Pending Execution** ¦ ¦ Logged ¦ 27 Feb 2026 09:56 ¦ ### Current Programme Context - PEI: 1.606 - SPI: 0.228 - Forecast Delay: 463d - EOT Exposure: 463d 💡 *This action has been logged for tracking. The assigned team member will receive notification for follow-through.* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:37.369532
63 | tool | L5 | Actions | Create Action — Raise alert to site planner | sra_create_action | Create Action — Raise alert to site planner | {'project_key': '101', 'action_choice': 'Raise alert to site planner — CP breach imminent', 'user_id': 'site_planner'} | PASS | All expected content present | 0.01 |  | ## ✅ Recovery Action Logged **Action ID**: `ACT-101-20260227095637` --- ### Action Record ¦ Field ¦ Detail ¦ ¦-------¦--------¦ ¦ Project ¦ Mega PWS in 11 block of Ganjam District (Key: 101) ¦ ¦ Action ¦ Raise alert to site planner — CP breach imminent ¦ ¦ Assigned To ¦ site_planner ¦ ¦ Status ¦ 🟡 **Open — Pending Execution** ¦ ¦ Logged ¦ 27 Feb 2026 09:56 ¦ ### Alert Dispatch - Alert type: **Schedule Recovery — Immediate Action Required** - Recipient: site_planner - Priority: **High** - Channels: 📧 Email + 📱 Push notification queued ### Current Programme Context - PEI: 1.606 - SPI: 0.228 - Forecast Delay: 463d - EOT Exposure: 463d 💡 *This action has been logged for tracking. The assigned team member will receive notification for follow-through.* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:37.376527
64 | tool | L5 | Actions | Create Action — Escalate to PM (no user_id) | sra_create_action | Create Action — Escalate to PM (no user_id) | {'project_key': '101', 'action_choice': 'Escalate workfront constraints to PM'} | PASS | All expected content present | 0.01 |  | ## ✅ Recovery Action Logged **Action ID**: `ACT-101-20260227095637` --- ### Action Record ¦ Field ¦ Detail ¦ ¦-------¦--------¦ ¦ Project ¦ Mega PWS in 11 block of Ganjam District (Key: 101) ¦ ¦ Action ¦ Escalate workfront constraints to PM ¦ ¦ Assigned To ¦ Unassigned — Pending Nomination ¦ ¦ Status ¦ 🟡 **Open — Pending Execution** ¦ ¦ Logged ¦ 27 Feb 2026 09:56 ¦ ### Alert Dispatch - Alert type: **Schedule Recovery — Immediate Action Required** - Recipient: Site Planner / Planning Manager - Priority: **High** - Channels: 📧 Email + 📱 Push notification queued ### Current Programme Context - PEI: 1.606 - SPI: 0.228 - Forecast Delay: 463d - EOT Exposure: 463d 💡 *This action has been logged for tracking. The assigned team member will receive notification for follow-through.* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:37.387534
65 | tool | L5 | Actions | Create Action — Notify procurement team | sra_create_action | Create Action — Notify procurement team | {'project_key': '101', 'action_choice': 'Notify procurement team of overdue PRC rules', 'user_id': 'procurement_lead'} | PASS | All expected content present | 0.01 |  | ## ✅ Recovery Action Logged **Action ID**: `ACT-101-20260227095637` --- ### Action Record ¦ Field ¦ Detail ¦ ¦-------¦--------¦ ¦ Project ¦ Mega PWS in 11 block of Ganjam District (Key: 101) ¦ ¦ Action ¦ Notify procurement team of overdue PRC rules ¦ ¦ Assigned To ¦ procurement_lead ¦ ¦ Status ¦ 🟡 **Open — Pending Execution** ¦ ¦ Logged ¦ 27 Feb 2026 09:56 ¦ ### Alert Dispatch - Alert type: **Schedule Recovery — Immediate Action Required** - Recipient: procurement_lead - Priority: **High** - Channels: 📧 Email + 📱 Push notification queued ### Current Programme Context - PEI: 1.606 - SPI: 0.228 - Forecast Delay: 463d - EOT Exposure: 463d 💡 *This action has been logged for tracking. The assigned team member will receive notification for follow-through.* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:37.396565
66 | tool | L5 | Actions | Create Action — No action choice (should prompt) | sra_create_action | Create Action — No action choice (should prompt) | {'project_key': '101'} | WARN | Expected keywords missing: ['Action Logged', 'ACT-', 'Recovery Action'] | 0 |  | 📋 **Additional details required to log the action:** **Action** — what should be logged? (e.g. 'Approve Option 2 — Schedule Compression') 💡 Example: *Log Option 1 for project 101 and assign to site planner* |  | 2026-02-27T09:56:37.397533
67 | tool | L5 | Actions | Create Action — No inputs at all | sra_create_action | Create Action — No inputs at all | {} | WARN | Expected keywords missing: ['Action Logged', 'ACT-', 'Recovery Action'] | 0 |  | 📋 **Additional details required to log the action:** **Project** — which project? (Unable to retrieve project list) **Action** — what should be logged? (e.g. 'Approve Option 2 — Schedule Compression') 💡 Example: *Log Option 1 for project 101 and assign to site planner* |  | 2026-02-27T09:56:37.398820
68 | tool | L6 | Accountability | Trace — All domains, all tasks | sra_accountability_trace | Trace — All domains, all tasks | {'project_key': '101'} | PASS | All expected content present | 2.79 |  | ## 📝 Accountability & Reporting Traceability — Mega PWS in 11 block of Ganjam District *Scope: All Domains ¦ Activity: All* ### Report-Flagged Tasks (Current Period) **11899** tasks are flagged for narrative reporting this period: ¦ Task ¦ Activity ¦ Domain ¦ Health RAG ¦ Accountability ¦ Narrative Label ¦ ¦------¦----------¦--------¦------------¦----------------¦----------------¦ ¦ Plastering ESR tank portion ¦ Plastering ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ PO ¦ PO ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Background ¦ ¦ PR ¦ PR ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Background ¦ ¦ Shuttering- upto FGL ¦ Shuttering ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Disposal of excess earth ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Plastering ¦ Plastering ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Stainless steel Ladder ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Shuttering - upto bottom slab ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ SS handrail ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Commissioning ¦ Commissioning ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Hard barrication ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Earthwork in Excavation in ordinary soil 1.5m - 3m ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Reinforcement - upto bottom slab ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ RCC - Vertical Side wall upto Roof slab ¦ RCC ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Shuttering - Vertical Side wall upto half height ¦ Shuttering ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Hard barrication ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ RCC - upto 100% staging height ¦ RCC ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Reinforcement - upto GL ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ SS handrail ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Shuttering - Vertical Side wall upto half height ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ### Delay Attribution Trace **14868** tasks have delay attribution records — relevant for variance reporting and potential EOT substantiation: ¦ Task ¦ Activity ¦ Domain ¦ Delay (d) ¦ Attribution ¦ Baseline Drift ¦ ¦------¦----------¦--------¦-----------¦-------------¦----------------¦ ¦ Plastering ESR tank portion ¦ Plastering ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Numeration and RC Detail of ESR of 80KL Capacity 10m Staging height at Pangidi for Scheme-I ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Numeration and RC Detail of ESR of 230KL Capacity 12m Staging height at Chingudighai for Scheme-I ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ PO ¦ PO ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ PR ¦ PR ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Shuttering- upto FGL ¦ Shuttering ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Disposal of excess earth ¦ — ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Plastering ¦ Plastering ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Stainless steel Ladder ¦ — ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Shuttering - upto bottom slab ¦ — ¦ CON ¦ 0d ¦ No Attributable Delay ¦ Significant Slip ? Over 1 Month ¦ ¦ SS handrail ¦ — ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Commissioning ¦ Commissioning ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Hard barrication ¦ — ¦ CON ¦ 0d ¦ No Attributable Delay ¦ Significant Slip ? Over 1 Month ¦ ¦ Earthwork in Excavation in ordinary soil 1.5m - 3m ¦ — ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Reinforcement - upto bottom slab ¦ — ¦ CON ¦ 0d ¦ No Attributable Delay ¦ Significant Slip ? Over 1 Month ¦ ### Recovery Candidate Tasks - **Crash Candidates** (eligible for resource augmentation): 823 - **Fast-Track Candidates** (eligible for concurrent working): 0 ### As-Built vs Baseline Duration (Completed Tasks) ¦ Task ¦ Baseline Duration ¦ As-Built Duration ¦ Duration Variance ¦ ¦------¦------------------¦-------------------¦------------------¦ ¦ Numeration and RC Detail of ESR of 80KL Capacity 10m Staging height at Pangidi for Scheme-I ¦ 40d ¦ 319d ¦ 🔴 279d ¦ ¦ Numeration and RC Detail of ESR of 230KL Capacity 12m Staging height at Chingudighai for Scheme-I ¦ 40d ¦ 148d ¦ 🔴 108d ¦ ¦ Numeration and RC Detail of GLSR of 425KL Capacity at Barida for Scheme-II ¦ 45d ¦ 286d ¦ 🔴 241d ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-316 KENDUPADARA-PR(ASKA) to Village (Ganjam Scheme-1) ¦ 46d ¦ 46d ¦ ✅ 0d ¦ ¦ Numeration and RC Detail of ESR of 210KL Capacity 16m Staging height at Debabhumi for Scheme-I ¦ 40d ¦ 162d ¦ 🔴 122d ¦ ¦ Numeration and RC Detail of Cascade aerator, Parshall flume, Distribution chamber and Flash mixer for Scheme-1 ¦ 45d ¦ 581d ¦ 🔴 536d ¦ ¦ Reinforcement - upto 100% staging height ¦ 10d ¦ 71d ¦ 🔴 61d ¦ ¦ Numeration and RC Detail of Filter Annex Building for Scheme-1 ¦ 40d ¦ 328d ¦ 🔴 288d ¦ ¦ Design Calculation of ESR of 325KL Capacity 16m Staging height at Saurachachina for Scheme-II ¦ 45d ¦ 290d ¦ 🔴 245d ¦ ¦ Hydraulic Flow Diagram for WTP ¦ 45d ¦ 302d ¦ 🔴 257d ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:40.188603
69 | tool | L6 | Accountability | Trace — Construction domain tasks | sra_accountability_trace | Trace — Construction domain tasks | {'project_key': '101', 'domain_code': 'CON'} | PASS | All expected content present | 3 |  | ## 📝 Accountability & Reporting Traceability — Mega PWS in 11 block of Ganjam District *Scope: CON ¦ Activity: All* ### Report-Flagged Tasks (Current Period) **10223** tasks are flagged for narrative reporting this period: ¦ Task ¦ Activity ¦ Domain ¦ Health RAG ¦ Accountability ¦ Narrative Label ¦ ¦------¦----------¦--------¦------------¦----------------¦----------------¦ ¦ Plastering ESR tank portion ¦ Plastering ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Shuttering- upto FGL ¦ Shuttering ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Disposal of excess earth ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Plastering ¦ Plastering ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Stainless steel Ladder ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Shuttering - upto bottom slab ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ SS handrail ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Commissioning ¦ Commissioning ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Hard barrication ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Earthwork in Excavation in ordinary soil 1.5m - 3m ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Reinforcement - upto bottom slab ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ RCC - Vertical Side wall upto Roof slab ¦ RCC ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Shuttering - Vertical Side wall upto half height ¦ Shuttering ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Hard barrication ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ RCC - upto 100% staging height ¦ RCC ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Reinforcement - upto GL ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ SS handrail ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Shuttering - Vertical Side wall upto half height ¦ — ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ Commissioning ¦ Commissioning ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ¦ RCC - Vertical Side Roof slab ¦ RCC ¦ CON ¦ 🔴 Red ¦ Construction Team ¦ Background ¦ ### Delay Attribution Trace **10991** tasks have delay attribution records — relevant for variance reporting and potential EOT substantiation: ¦ Task ¦ Activity ¦ Domain ¦ Delay (d) ¦ Attribution ¦ Baseline Drift ¦ ¦------¦----------¦--------¦-----------¦-------------¦----------------¦ ¦ Plastering ESR tank portion ¦ Plastering ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Shuttering- upto FGL ¦ Shuttering ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Disposal of excess earth ¦ — ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Plastering ¦ Plastering ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Stainless steel Ladder ¦ — ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Shuttering - upto bottom slab ¦ — ¦ CON ¦ 0d ¦ No Attributable Delay ¦ Significant Slip ? Over 1 Month ¦ ¦ SS handrail ¦ — ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Commissioning ¦ Commissioning ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Hard barrication ¦ — ¦ CON ¦ 0d ¦ No Attributable Delay ¦ Significant Slip ? Over 1 Month ¦ ¦ Earthwork in Excavation in ordinary soil 1.5m - 3m ¦ — ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Reinforcement - upto bottom slab ¦ — ¦ CON ¦ 0d ¦ No Attributable Delay ¦ Significant Slip ? Over 1 Month ¦ ¦ RCC - Vertical Side wall upto Roof slab ¦ RCC ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Shuttering - Vertical Side wall upto half height ¦ Shuttering ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Hard barrication ¦ — ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ RCC - upto 100% staging height ¦ RCC ¦ CON ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ### As-Built vs Baseline Duration (Completed Tasks) ¦ Task ¦ Baseline Duration ¦ As-Built Duration ¦ Duration Variance ¦ ¦------¦------------------¦-------------------¦------------------¦ ¦ Reinforcement - upto 100% staging height ¦ 10d ¦ 71d ¦ 🔴 61d ¦ ¦ Reinforcement - upto GL ¦ 6d ¦ 146d ¦ 🔴 140d ¦ ¦ Shuttering - upto 100% staging height ¦ 12d ¦ 28d ¦ 🔴 16d ¦ ¦ RCC - upto bottom slab ¦ 5d ¦ 77d ¦ 🔴 72d ¦ ¦ Reinforcement - Vertical Side wall upto half height ¦ 4d ¦ 3d ¦ ✅ -1d ¦ ¦ Shuttering - upto GL ¦ 16d ¦ 65d ¦ 🔴 49d ¦ ¦ RCC - upto GL ¦ 7d ¦ 62d ¦ 🔴 55d ¦ ¦ Reinforcement - upto first floor roof slab ¦ 11d ¦ 74d ¦ 🔴 63d ¦ ¦ Shuttering - upto 100% staging height ¦ 16d ¦ 79d ¦ 🔴 63d ¦ ¦ RCC - upto GL ¦ 7d ¦ 221d ¦ 🔴 214d ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:43.191685
70 | tool | L6 | Accountability | Trace — Engineering domain tasks | sra_accountability_trace | Trace — Engineering domain tasks | {'project_key': '101', 'domain_code': 'ENG'} | PASS | All expected content present | 2.91 |  | ## 📝 Accountability & Reporting Traceability — Mega PWS in 11 block of Ganjam District *Scope: ENG ¦ Activity: All* ### Report-Flagged Tasks (Current Period) **549** tasks are flagged for narrative reporting this period: ¦ Task ¦ Activity ¦ Domain ¦ Health RAG ¦ Accountability ¦ Narrative Label ¦ ¦------¦----------¦--------¦------------¦----------------¦----------------¦ ¦ Design Calculation of Switchyard at IBPS-9 for Scheme-1 ¦ — ¦ ENG ¦ 🔴 Red ¦ Engineering Team ¦ Background ¦ ¦ Architectural Detail of Chlorine Building for Scheme-1 ¦ — ¦ ENG ¦ 🟡 Amber ¦ Engineering Team ¦ Background ¦ ¦ Numeration and RC Detail of Cascade aerator, Parshall flume, Distribution chamber and Flash mixer for Scheme-1 ¦ — ¦ ENG ¦ 🟢 Green ¦ Engineering Team ¦ Background ¦ ¦ P&ID Drawing for CWR cum Pump House at IBPS-1- (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 🟡 Amber ¦ Engineering Team ¦ Background ¦ ¦ Overall Single Line Diagram for IBPS 12 ¦ — ¦ ENG ¦ 🟡 Amber ¦ Engineering Team ¦ Background ¦ ¦ Design Calculation of Intermediate Sump-1 for Scheme-1 ¦ — ¦ ENG ¦ 🟡 Amber ¦ Engineering Team ¦ Background ¦ ¦ Instrument list for IBPS-5 ¦ — ¦ ENG ¦ 🟡 Amber ¦ Engineering Team ¦ Background ¦ ¦ Lighting Layout for Intake ¦ — ¦ ENG ¦ 🔴 Red ¦ Engineering Team ¦ Critical Exception ¦ ¦ 33/11 kV Switchyard Layout for IBPS 1 ¦ — ¦ ENG ¦ 🟡 Amber ¦ Engineering Team ¦ Background ¦ ¦ Design Calculation of Switchyard at IBPS-1 for Scheme-1 ¦ — ¦ ENG ¦ 🔴 Red ¦ Engineering Team ¦ Background ¦ ¦ Surge Analysis Report for Clear water Pumping main from IBPS-09 (PM-2) to OHTs Ganjam WSS (Scheme-1) ¦ — ¦ ENG ¦ 🟡 Amber ¦ Engineering Team ¦ Background ¦ ¦ Control And Interlock Details for IBPS-4 ¦ — ¦ ENG ¦ 🟡 Amber ¦ Engineering Team ¦ Background ¦ ¦ Numeration and RC Detail of Intermediate Pump House-7 for Scheme-1 ¦ — ¦ ENG ¦ 🟡 Amber ¦ Engineering Team ¦ Background ¦ ¦ Numeration and RC Detail of ESR of 325KL Capacity 20m Staging height at Betarsingi for Scheme-I ¦ — ¦ ENG ¦ 🟡 Amber ¦ Engineering Team ¦ Background ¦ ¦ Earthing Layout for IBPS 9 ¦ — ¦ ENG ¦ 🟡 Amber ¦ Engineering Team ¦ Background ¦ ¦ Design Calculation of Valve Chambers for Scheme-2 ¦ — ¦ ENG ¦ 🔴 Red ¦ Engineering Team ¦ Critical Exception ¦ ¦ Numeration and RC Detail of Intermediate Sump-3 for Scheme-1 ¦ — ¦ ENG ¦ 🟡 Amber ¦ Engineering Team ¦ Background ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-179 AMBILLIJHARA-PR (GAN) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 🟡 Amber ¦ Engineering Team ¦ Background ¦ ¦ Instrumentation Cable schedule for IBPS-1 ¦ — ¦ ENG ¦ 🟡 Amber ¦ Engineering Team ¦ Background ¦ ¦ DG Sizing calculation Intake, WTP ¦ — ¦ ENG ¦ 🟡 Amber ¦ Engineering Team ¦ Background ¦ ### Delay Attribution Trace **2694** tasks have delay attribution records — relevant for variance reporting and potential EOT substantiation: ¦ Task ¦ Activity ¦ Domain ¦ Delay (d) ¦ Attribution ¦ Baseline Drift ¦ ¦------¦----------¦--------¦-----------¦-------------¦----------------¦ ¦ Numeration and RC Detail of ESR of 80KL Capacity 10m Staging height at Pangidi for Scheme-I ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Numeration and RC Detail of ESR of 230KL Capacity 12m Staging height at Chingudighai for Scheme-I ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Numeration and RC Detail of GLSR of 425KL Capacity at Barida for Scheme-II ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Design Calculation of Switchyard at IBPS-9 for Scheme-1 ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-316 KENDUPADARA-PR(ASKA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Architectural Detail of Chlorine Building for Scheme-1 ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Design Calculation of ESR of 60KL Capacity 10m Staging height at Khadabhaga for Scheme-I ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Numeration and RC Detail of ESR of 210KL Capacity 16m Staging height at Debabhumi for Scheme-I ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Numeration and RC Detail of Cascade aerator, Parshall flume, Distribution chamber and Flash mixer for Scheme-1 ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ P&ID Drawing for CWR cum Pump House at IBPS-1- (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Hydraulics Design for Gravity Distribution main from OHT-115 BALLIPADAR-EX (BUGUDA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Numeration and RC Detail of Filter Annex Building for Scheme-1 ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Architectural Detail of Filter House & Filter Annex Building for Scheme-2 ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Overall Single Line Diagram for IBPS 12 ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Design Calculation of ESR of 325KL Capacity 16m Staging height at Saurachachina for Scheme-II ¦ — ¦ ENG ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ### Recovery Candidate Tasks - **Crash Candidates** (eligible for resource augmentation): 475 - **Fast-Track Candidates** (eligible for concurrent working): 0 ### As-Built vs Baseline Duration (Completed Tasks) ¦ Task ¦ Baseline Duration ¦ As-Built Duration ¦ Duration Variance ¦ ¦------¦------------------¦-------------------¦------------------¦ ¦ Numeration and RC Detail of ESR of 80KL Capacity 10m Staging height at Pangidi for Scheme-I ¦ 40d ¦ 319d ¦ 🔴 279d ¦ ¦ Numeration and RC Detail of ESR of 230KL Capacity 12m Staging height at Chingudighai for Scheme-I ¦ 40d ¦ 148d ¦ 🔴 108d ¦ ¦ Numeration and RC Detail of GLSR of 425KL Capacity at Barida [... truncated at 6000 chars] |  | 2026-02-27T09:56:46.098911
71 | tool | L6 | Accountability | Trace — Procurement domain tasks | sra_accountability_trace | Trace — Procurement domain tasks | {'project_key': '101', 'domain_code': 'PRC'} | PASS | All expected content present | 3.42 |  | ## 📝 Accountability & Reporting Traceability — Mega PWS in 11 block of Ganjam District *Scope: PRC ¦ Activity: All* ### Report-Flagged Tasks (Current Period) **1127** tasks are flagged for narrative reporting this period: ¦ Task ¦ Activity ¦ Domain ¦ Health RAG ¦ Accountability ¦ Narrative Label ¦ ¦------¦----------¦--------¦------------¦----------------¦----------------¦ ¦ PO ¦ PO ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Background ¦ ¦ PR ¦ PR ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Background ¦ ¦ PO ¦ PO ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Background ¦ ¦ PO ¦ PO ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Background ¦ ¦ PR ¦ PR ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Background ¦ ¦ MRN ¦ MRN ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Background ¦ ¦ MFC ¦ MFC ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Critical Exception ¦ ¦ PR ¦ PR ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Background ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Critical Exception ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Critical Exception ¦ ¦ Inspection ¦ INS ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Background ¦ ¦ MRN ¦ MRN ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Critical Exception ¦ ¦ MFC ¦ MFC ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Background ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Background ¦ ¦ PR ¦ PR ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Critical Exception ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Critical Exception ¦ ¦ PO ¦ PO ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Critical Exception ¦ ¦ MFC ¦ MFC ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Background ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Critical Exception ¦ ¦ PR ¦ PR ¦ PRC ¦ 🔴 Red ¦ Procurement Team ¦ Critical Exception ¦ ### Delay Attribution Trace **1183** tasks have delay attribution records — relevant for variance reporting and potential EOT substantiation: ¦ Task ¦ Activity ¦ Domain ¦ Delay (d) ¦ Attribution ¦ Baseline Drift ¦ ¦------¦----------¦--------¦-----------¦-------------¦----------------¦ ¦ PO ¦ PO ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ PR ¦ PR ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ PO ¦ PO ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ PO ¦ PO ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ PR ¦ PR ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ MRN ¦ MRN ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ MFC ¦ MFC ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ PR ¦ PR ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Inspection ¦ INS ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Inspection ¦ INS ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ MRN ¦ MRN ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ MFC ¦ MFC ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 0d ¦ Internal Progress Lag ¦ Significant Slip ? Over 1 Month ¦ ### Recovery Candidate Tasks - **Crash Candidates** (eligible for resource augmentation): 348 - **Fast-Track Candidates** (eligible for concurrent working): 0 ### As-Built vs Baseline Duration (Completed Tasks) ¦ Task ¦ Baseline Duration ¦ As-Built Duration ¦ Duration Variance ¦ ¦------¦------------------¦-------------------¦------------------¦ ¦ PO ¦ 134d ¦ 333d ¦ 🔴 199d ¦ ¦ PR ¦ 134d ¦ 344d ¦ 🔴 210d ¦ ¦ Dispatch Clearance ¦ 135d ¦ 388d ¦ 🔴 253d ¦ ¦ Dispatch Clearance ¦ 135d ¦ 409d ¦ 🔴 274d ¦ ¦ MFC ¦ 134d ¦ 118d ¦ ✅ -16d ¦ ¦ Inspection ¦ 134d ¦ 118d ¦ ✅ -16d ¦ ¦ MRN ¦ 134d ¦ 515d ¦ 🔴 381d ¦ ¦ MRN ¦ 134d ¦ 272d ¦ 🔴 138d ¦ ¦ Post Order & QAP Approval ¦ 135d ¦ 413d ¦ 🔴 278d ¦ ¦ PR ¦ 134d ¦ 391d ¦ 🔴 257d ¦ --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:49.513911
72 | tool | L6 | Accountability | Trace — No project key | sra_accountability_trace | Trace — No project key | {} | WARN | Expected keywords missing: ['Report', 'Task'] | 0 |  | 📋 **Specify the project for accountability tracing.** (Unable to retrieve project list) |  | 2026-02-27T09:56:49.514911
73 | tool | L6 | Formula | Formula — Explain SPI (with live project context) | sra_explain_formula | Formula — Explain SPI (with live project context) | {'project_key': '101', 'metric': 'SPI'} | WARN | Expected keywords missing: ['Definition'] | 0.01 |  | ## 📐 Schedule Metric Reference Guide *Live context: Mega PWS in 11 block of Ganjam District (Key: 101)* --- ### 📈 SPI — Schedule Performance Index **Formula**: `SPI = Earned Progress % / Planned Progress %` Measures whether work is being executed at the rate the programme demands. An SPI of 1.0 means the project is earning exactly what was planned. Below 1.0 indicates the execution rate is lagging — the gap compounds over time on a critical path. ¦ Value ¦ Signal ¦ Interpretation ¦ ¦-------¦--------¦----------------¦ ¦ SPI > 1.0 ¦ 🟢 Ahead of Programme ¦ Execution exceeds plan ¦ ¦ SPI = 1.0 ¦ ✅ On Programme ¦ Performance exactly as planned ¦ ¦ SPI < 1.0 ¦ 🔴 Behind Programme ¦ Execution rate below plan ¦ *Current SPI: **0.228** — Behind by 77.2%* --- 💡 *Ask about a specific metric for a live calculation against your project — e.g. 'Explain SPI for project 101'* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:49.523085
74 | tool | L6 | Formula | Formula — Explain PEI (with live project context) | sra_explain_formula | Formula — Explain PEI (with live project context) | {'project_key': '101', 'metric': 'PEI'} | WARN | Expected keywords missing: ['Definition'] | 0.01 |  | ## 📐 Schedule Metric Reference Guide *Live context: Mega PWS in 11 block of Ganjam District (Key: 101)* --- ### 📊 PEI — Project Execution Index **Formula**: `PEI = Forecast Duration / Planned Duration` Measures whether the overall programme duration is expanding beyond its original plan. A PEI above 1.0 means the project is consuming more time than the baseline allocated — a direct signal of schedule overrun risk even if individual activities appear on track. ¦ Value ¦ Signal ¦ Interpretation ¦ ¦-------¦--------¦----------------¦ ¦ PEI < 1.0 ¦ 🟢 Duration Efficient ¦ Forecast shorter than baseline ¦ ¦ PEI = 1.0 ¦ ✅ On Programme ¦ Forecast equals baseline duration ¦ ¦ PEI > 1.0 ¦ 🔴 Duration Overrun ¦ Forecast exceeds baseline ¦ *Current PEI: **1.606** — 60.6% over baseline duration* --- 💡 *Ask about a specific metric for a live calculation against your project — e.g. 'Explain SPI for project 101'* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:49.533054
75 | tool | L6 | Formula | Formula — Explain LAC compliance | sra_explain_formula | Formula — Explain LAC compliance | {'project_key': '101', 'metric': 'LAC'} | WARN | Expected keywords missing: ['Definition', 'Interpretation'] | 0.01 |  | ## 📐 Schedule Metric Reference Guide *Live context: Mega PWS in 11 block of Ganjam District (Key: 101)* --- ### 🎯 LAC — Look-Ahead Compliance **Formula**: `LAC % = (Rules Completed On Time / Total Rules Planned) × 100` LAC is the construction industry's primary execution reliability metric. It measures the percentage of short-term commitments (rules) that were fulfilled within the look-ahead window. A declining LAC is an early warning of execution discipline breakdown — it typically precedes SPI deterioration by 2–4 weeks. ¦ Value ¦ Signal ¦ ¦-------¦--------¦ ¦ ≥ 80% ¦ ✅ Strong execution reliability ¦ ¦ 60–79% ¦ 🟡 Execution gap — root cause review warranted ¦ ¦ < 60% ¦ 🔴 Systemic planning/execution disconnect — escalation required ¦ --- 💡 *Ask about a specific metric for a live calculation against your project — e.g. 'Explain SPI for project 101'* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:49.546845
76 | tool | L6 | Formula | Formula — Explain Float | sra_explain_formula | Formula — Explain Float | {'project_key': '101', 'metric': 'float'} | WARN | Expected keywords missing: ['Formula', 'Interpretation'] | 0.01 |  | ## 📐 Schedule Metric Reference Guide *Live context: Mega PWS in 11 block of Ganjam District (Key: 101)* --- ### ⏳ Total Float **Definition**: The maximum amount of time a task can be delayed without delaying the project completion date. Float is the scheduling buffer in the network. Zero float means any delay to that task directly extends the project end date (Critical Path). Negative float means the task is already causing a projected overrun. Near-critical tasks (≤5 days float) require active monitoring as they can migrate onto the critical path with a single disruption event. ¦ Float Band ¦ Classification ¦ ¦-----------¦----------------¦ ¦ < 0 ¦ 🔴 Overrun — already impacting completion ¦ ¦ = 0 ¦ 🔴 Critical Path ¦ ¦ 1–5d ¦ 🟡 Near-Critical Watch ¦ ¦ > 5d ¦ 🟢 Schedule Buffer Available ¦ --- 💡 *Ask about a specific metric for a live calculation against your project — e.g. 'Explain SPI for project 101'* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:49.559561
77 | tool | L6 | Formula | Formula — Explain EOT | sra_explain_formula | Formula — Explain EOT | {'project_key': '101', 'metric': 'EOT'} | WARN | Expected keywords missing: ['Formula', 'Interpretation'] | 0.01 |  | ## 📐 Schedule Metric Reference Guide *Live context: Mega PWS in 11 block of Ganjam District (Key: 101)* --- ### ⚖️ EOT — Extension of Time **Definition**: A contractual entitlement to extend the project completion date without penalty, typically granted when delay events arise from Employer risk or force majeure events. **EOT Exposure** represents the number of days the current forecast completion exceeds the contractual date. EOT Eligibility assesses whether the delay has a contractual basis for an extension claim. Unsubstantiated EOT exposure translates directly into Liquidated Damages (LD) liability. EOT forensic analysis requires establishing: the delay event timeline, its impact on the critical path at the time of occurrence, concurrent delay assessment, and the causal chain from event to completion date shift. --- 💡 *Ask about a specific metric for a live calculation against your project — e.g. 'Explain SPI for project 101'* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:49.570439
78 | tool | L6 | Formula | Formula — Explain ALL metrics | sra_explain_formula | Formula — Explain ALL metrics | {'project_key': '101', 'metric': 'all'} | PASS | All expected content present | 0.01 |  | ## 📐 Schedule Metric Reference Guide *Live context: Mega PWS in 11 block of Ganjam District (Key: 101)* --- ### 📈 SPI — Schedule Performance Index **Formula**: `SPI = Earned Progress % / Planned Progress %` Measures whether work is being executed at the rate the programme demands. An SPI of 1.0 means the project is earning exactly what was planned. Below 1.0 indicates the execution rate is lagging — the gap compounds over time on a critical path. ¦ Value ¦ Signal ¦ Interpretation ¦ ¦-------¦--------¦----------------¦ ¦ SPI > 1.0 ¦ 🟢 Ahead of Programme ¦ Execution exceeds plan ¦ ¦ SPI = 1.0 ¦ ✅ On Programme ¦ Performance exactly as planned ¦ ¦ SPI < 1.0 ¦ 🔴 Behind Programme ¦ Execution rate below plan ¦ *Current SPI: **0.228** — Behind by 77.2%* ### 📊 PEI — Project Execution Index **Formula**: `PEI = Forecast Duration / Planned Duration` Measures whether the overall programme duration is expanding beyond its original plan. A PEI above 1.0 means the project is consuming more time than the baseline allocated — a direct signal of schedule overrun risk even if individual activities appear on track. ¦ Value ¦ Signal ¦ Interpretation ¦ ¦-------¦--------¦----------------¦ ¦ PEI < 1.0 ¦ 🟢 Duration Efficient ¦ Forecast shorter than baseline ¦ ¦ PEI = 1.0 ¦ ✅ On Programme ¦ Forecast equals baseline duration ¦ ¦ PEI > 1.0 ¦ 🔴 Duration Overrun ¦ Forecast exceeds baseline ¦ *Current PEI: **1.606** — 60.6% over baseline duration* ### 🎯 LAC — Look-Ahead Compliance **Formula**: `LAC % = (Rules Completed On Time / Total Rules Planned) × 100` LAC is the construction industry's primary execution reliability metric. It measures the percentage of short-term commitments (rules) that were fulfilled within the look-ahead window. A declining LAC is an early warning of execution discipline breakdown — it typically precedes SPI deterioration by 2–4 weeks. ¦ Value ¦ Signal ¦ ¦-------¦--------¦ ¦ ≥ 80% ¦ ✅ Strong execution reliability ¦ ¦ 60–79% ¦ 🟡 Execution gap — root cause review warranted ¦ ¦ < 60% ¦ 🔴 Systemic planning/execution disconnect — escalation required ¦ ### ⏳ Total Float **Definition**: The maximum amount of time a task can be delayed without delaying the project completion date. Float is the scheduling buffer in the network. Zero float means any delay to that task directly extends the project end date (Critical Path). Negative float means the task is already causing a projected overrun. Near-critical tasks (≤5 days float) require active monitoring as they can migrate onto the critical path with a single disruption event. ¦ Float Band ¦ Classification ¦ ¦-----------¦----------------¦ ¦ < 0 ¦ 🔴 Overrun — already impacting completion ¦ ¦ = 0 ¦ 🔴 Critical Path ¦ ¦ 1–5d ¦ 🟡 Near-Critical Watch ¦ ¦ > 5d ¦ 🟢 Schedule Buffer Available ¦ ### ⚖️ EOT — Extension of Time **Definition**: A contractual entitlement to extend the project completion date without penalty, typically granted when delay events arise from Employer risk or force majeure events. **EOT Exposure** represents the number of days the current forecast completion exceeds the contractual date. EOT Eligibility assesses whether the delay has a contractual basis for an extension claim. Unsubstantiated EOT exposure translates directly into Liquidated Damages (LD) liability. EOT forensic analysis requires establishing: the delay event timeline, its impact on the critical path at the time of occurrence, concurrent delay assessment, and the causal chain from event to completion date shift. --- 💡 *Ask about a specific metric for a live calculation against your project — e.g. 'Explain SPI for project 101'* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:49.581691
79 | tool | L6 | Formula | Formula — No project key, SPI only | sra_explain_formula | Formula — No project key, SPI only | {'metric': 'SPI'} | WARN | Expected keywords missing: ['Definition'] | 0 |  | ## 📐 Schedule Metric Reference Guide ### 📈 SPI — Schedule Performance Index **Formula**: `SPI = Earned Progress % / Planned Progress %` Measures whether work is being executed at the rate the programme demands. An SPI of 1.0 means the project is earning exactly what was planned. Below 1.0 indicates the execution rate is lagging — the gap compounds over time on a critical path. ¦ Value ¦ Signal ¦ Interpretation ¦ ¦-------¦--------¦----------------¦ ¦ SPI > 1.0 ¦ 🟢 Ahead of Programme ¦ Execution exceeds plan ¦ ¦ SPI = 1.0 ¦ ✅ On Programme ¦ Performance exactly as planned ¦ ¦ SPI < 1.0 ¦ 🔴 Behind Programme ¦ Execution rate below plan ¦ --- 💡 *Ask about a specific metric for a live calculation against your project — e.g. 'Explain SPI for project 101'* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:49.582690
80 | tool | L6 | Formula | Formula — No inputs at all | sra_explain_formula | Formula — No inputs at all | {} | PASS | All expected content present | 0 |  | ## 📐 Schedule Metric Reference Guide ### 📈 SPI — Schedule Performance Index **Formula**: `SPI = Earned Progress % / Planned Progress %` Measures whether work is being executed at the rate the programme demands. An SPI of 1.0 means the project is earning exactly what was planned. Below 1.0 indicates the execution rate is lagging — the gap compounds over time on a critical path. ¦ Value ¦ Signal ¦ Interpretation ¦ ¦-------¦--------¦----------------¦ ¦ SPI > 1.0 ¦ 🟢 Ahead of Programme ¦ Execution exceeds plan ¦ ¦ SPI = 1.0 ¦ ✅ On Programme ¦ Performance exactly as planned ¦ ¦ SPI < 1.0 ¦ 🔴 Behind Programme ¦ Execution rate below plan ¦ ### 📊 PEI — Project Execution Index **Formula**: `PEI = Forecast Duration / Planned Duration` Measures whether the overall programme duration is expanding beyond its original plan. A PEI above 1.0 means the project is consuming more time than the baseline allocated — a direct signal of schedule overrun risk even if individual activities appear on track. ¦ Value ¦ Signal ¦ Interpretation ¦ ¦-------¦--------¦----------------¦ ¦ PEI < 1.0 ¦ 🟢 Duration Efficient ¦ Forecast shorter than baseline ¦ ¦ PEI = 1.0 ¦ ✅ On Programme ¦ Forecast equals baseline duration ¦ ¦ PEI > 1.0 ¦ 🔴 Duration Overrun ¦ Forecast exceeds baseline ¦ ### 🎯 LAC — Look-Ahead Compliance **Formula**: `LAC % = (Rules Completed On Time / Total Rules Planned) × 100` LAC is the construction industry's primary execution reliability metric. It measures the percentage of short-term commitments (rules) that were fulfilled within the look-ahead window. A declining LAC is an early warning of execution discipline breakdown — it typically precedes SPI deterioration by 2–4 weeks. ¦ Value ¦ Signal ¦ ¦-------¦--------¦ ¦ ≥ 80% ¦ ✅ Strong execution reliability ¦ ¦ 60–79% ¦ 🟡 Execution gap — root cause review warranted ¦ ¦ < 60% ¦ 🔴 Systemic planning/execution disconnect — escalation required ¦ ### ⏳ Total Float **Definition**: The maximum amount of time a task can be delayed without delaying the project completion date. Float is the scheduling buffer in the network. Zero float means any delay to that task directly extends the project end date (Critical Path). Negative float means the task is already causing a projected overrun. Near-critical tasks (≤5 days float) require active monitoring as they can migrate onto the critical path with a single disruption event. ¦ Float Band ¦ Classification ¦ ¦-----------¦----------------¦ ¦ < 0 ¦ 🔴 Overrun — already impacting completion ¦ ¦ = 0 ¦ 🔴 Critical Path ¦ ¦ 1–5d ¦ 🟡 Near-Critical Watch ¦ ¦ > 5d ¦ 🟢 Schedule Buffer Available ¦ ### ⚖️ EOT — Extension of Time **Definition**: A contractual entitlement to extend the project completion date without penalty, typically granted when delay events arise from Employer risk or force majeure events. **EOT Exposure** represents the number of days the current forecast completion exceeds the contractual date. EOT Eligibility assesses whether the delay has a contractual basis for an extension claim. Unsubstantiated EOT exposure translates directly into Liquidated Damages (LD) liability. EOT forensic analysis requires establishing: the delay event timeline, its impact on the critical path at the time of occurrence, concurrent delay assessment, and the causal chain from event to completion date shift. --- 💡 *Ask about a specific metric for a live calculation against your project — e.g. 'Explain SPI for project 101'* --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:49.582690
81 | tool | L0 | SQL-NL | SQL — NL: List project summary / portfolio view | sra_sql_agent | SQL — NL: List project summary / portfolio view | {'question': 'List all projects with SPI, health score and delay', 'project_key': '101'} | WARN | Expected keywords missing: ['Activity', 'Task'] | 0.09 |  | ## ⚠️ Query Syntax Issue The database reported a syntax or access error: > column "project_key" does not exist HINT: Perhaps you meant to reference the column "tbl_01_project_summary.Project_Key". **Query attempted:** ```sql SELECT Project_Key, Project_Name, Project_Location, SPI_Overall, Project_Execution_Index, Max_Forecast_Delay_Days_Overall, EOT_Exposure_Days, Schedule_Health_RAG, Schedule_Health_Score, Data_Freshness_Label FROM tbl_01_project_summary WHERE Project_Key = 101 ORDER BY Max_Forecast_Delay_Days_Overall DESC NULLS LAST LIMIT 500 ``` Please review the column names and table references. Column names follow the `PascalCase_With_Underscores` convention. |  | 2026-02-27T09:56:49.673033
82 | tool | L0 | SQL-NL | SQL — NL: Critical tasks on CP (project scope) | sra_sql_agent | SQL — NL: Critical tasks on CP (project scope) | {'question': 'Show all critical tasks in project', 'project_key': '101'} | PASS | All expected content present | 0.14 |  | ## ⚠️ Query Syntax Issue The database reported a syntax or access error: > column "task_key" does not exist HINT: Perhaps you meant to reference the column "tbl_03_project_task.Task_Key". **Query attempted:** ```sql SELECT Task_Key, Task_Name, Activity_Code, Domain_Code, Task_Status, Total_Float_Days, Forecast_Delay_Days, Task_Health_RAG, Slip_Days FROM tbl_03_project_task WHERE Project_Key = 101 AND Is_Critical_Wrench = TRUE ORDER BY Total_Float_Days ASC LIMIT 500 ``` Please review the column names and table references. Column names follow the `PascalCase_With_Underscores` convention. |  | 2026-02-27T09:56:49.810620
83 | tool | L0 | SQL-NL | SQL — NL: Delayed tasks with risk tier | sra_sql_agent | SQL — NL: Delayed tasks with risk tier | {'question': 'Show delayed tasks with risk tier', 'project_key': '101'} | PASS | All expected content present | 0.08 |  | ## ⚠️ Query Syntax Issue The database reported a syntax or access error: > column "task_key" does not exist HINT: Perhaps you meant to reference the column "tbl_03_project_task.Task_Key". **Query attempted:** ```sql SELECT Task_Key, Task_Name, Activity_Code, Domain_Code, Task_Status, Forecast_Delay_Days, Slip_Days, Total_Float_Days, Task_Risk_Tier FROM tbl_03_project_task WHERE Project_Key = 101 AND Forecast_Delay_Days > 0 ORDER BY Forecast_Delay_Days DESC LIMIT 500 ``` Please review the column names and table references. Column names follow the `PascalCase_With_Underscores` convention. |  | 2026-02-27T09:56:49.892891
84 | tool | L0 | SQL-NL | SQL — NL: Float distribution across tasks | sra_sql_agent | SQL — NL: Float distribution across tasks | {'question': 'Float distribution for all tasks', 'project_key': '101'} | PASS | All expected content present | 0.12 |  | ## ⚠️ Query Syntax Issue The database reported a syntax or access error: > column "task_key" does not exist HINT: Perhaps you meant to reference the column "tbl_03_project_task.Task_Key". **Query attempted:** ```sql SELECT Task_Key, Task_Name, Activity_Code, Domain_Code, Total_Float_Days, Float_Health_Status, Float_RAG_Label, Is_Critical_Wrench, Float_Erosion_Flag FROM tbl_03_project_task WHERE Project_Key = 101 ORDER BY Total_Float_Days ASC LIMIT 500 ``` Please review the column names and table references. Column names follow the `PascalCase_With_Underscores` convention. |  | 2026-02-27T09:56:50.012125
85 | tool | L0 | SQL-NL | SQL — NL: 2-week look-ahead tasks | sra_sql_agent | SQL — NL: 2-week look-ahead tasks | {'question': 'Show tasks in the 2 week look ahead window', 'project_key': '101'} | PASS | All expected content present | 0.09 |  | ## ⚠️ Query Syntax Issue The database reported a syntax or access error: > column "task_key" does not exist HINT: Perhaps you meant to reference the column "tbl_03_project_task.Task_Key". **Query attempted:** ```sql SELECT Task_Key, Task_Name, Activity_Code, Domain_Code, Forecast_Start_Date, Forecast_Finish_Date, Is_WorkFront_Available, LookAhead_Priority_Score, Total_Float_Days FROM tbl_03_project_task WHERE Project_Key = 101 AND In_2W_Start_Window IS NOT NULL ORDER BY LookAhead_Priority_Score DESC LIMIT 500 ``` Please review the column names and table references. Column names follow the `PascalCase_With_Underscores` convention. |  | 2026-02-27T09:56:50.101965
86 | tool | L0 | SQL-NL | SQL — NL: Milestones and their status | sra_sql_agent | SQL — NL: Milestones and their status | {'question': 'List all milestones and their status', 'project_key': '101'} | PASS | All expected content present | 0 |  | ## 🔍 Ad-Hoc Query — Clarification Required The question **"List all milestones and their status"** falls outside the coverage of the structured schedule intelligence tools, and could not be automatically translated into a targeted database query. To proceed, please provide one of the following: 1. **A more specific question** — include the grain (task/activity/project), domain (ENG/PRC/CON), and the specific metrics or conditions you need. 2. **A raw SQL SELECT** — pass it via the `raw_sql` parameter. ### Available Tables ¦ Table ¦ Grain ¦ Key Columns ¦ ¦-------¦-------¦-------------¦ ¦ `tbl_01_project_summary` ¦ One row per project ¦ Project_Key, SPI_Overall, PEI, EOT_Exposure_Days, Schedule_Health_RAG ¦ ¦ `tbl_02_project_activity` ¦ One row per activity ¦ Activity_Code, Domain_Code, Forecast_Delay_Days, Float_Days, LAC_Pct ¦ ¦ `tbl_03_project_task` ¦ One row per task ¦ Task_Key, Activity_Code, Float_Days, Is_Critical_Wrench, Task_Health_RAG ¦ 💡 *Example: "Show all Construction tasks in project 101 with negative float" or "List activities with CON_LAC_Week_Pct below 60% for project 101"* |  | 2026-02-27T09:56:50.101965
87 | tool | L0 | SQL-NL | SQL — NL: Delayed activities with SPI | sra_sql_agent | SQL — NL: Delayed activities with SPI | {'question': 'Which activities have slipped and what is their SPI', 'project_key': '101'} | WARN | Expected keywords missing: ['Task'] | 0.08 |  | ## ⚠️ Query Syntax Issue The database reported a syntax or access error: > column "activity_code" does not exist HINT: Perhaps you meant to reference the column "tbl_02_project_activity.Activity_Code". **Query attempted:** ```sql SELECT Activity_Code, Activity_Description, Domain_Code, Activity_Status, Forecast_Delay_Days, Slip_Days, SPI_RAG_Label, Delay_Magnitude_Label, Is_Critical_Wrench FROM tbl_02_project_activity WHERE Project_Key = 101 AND Forecast_Delay_Days > 0 ORDER BY Forecast_Delay_Days DESC LIMIT 500 ``` Please review the column names and table references. Column names follow the `PascalCase_With_Underscores` convention. |  | 2026-02-27T09:56:50.177537
88 | tool | L0 | SQL-NL | SQL — NL: Workfront-constrained activities | sra_sql_agent | SQL — NL: Workfront-constrained activities | {'question': 'Activities with low workfront readiness', 'project_key': '101'} | WARN | Expected keywords missing: ['Task'] | 0.08 |  | ## ⚠️ Query Syntax Issue The database reported a syntax or access error: > column "activity_code" does not exist HINT: Perhaps you meant to reference the column "tbl_02_project_activity.Activity_Code". **Query attempted:** ```sql SELECT Activity_Code, Activity_Description, Domain_Code, Workfront_Ready_Pct, Workfront_Gap_Count, CAD_Breach_Flag, Is_Critical_Wrench, Activity_Status FROM tbl_02_project_activity WHERE Project_Key = 101 AND Workfront_Ready_Pct < 70 ORDER BY Workfront_Ready_Pct ASC LIMIT 500 ``` Please review the column names and table references. Column names follow the `PascalCase_With_Underscores` convention. |  | 2026-02-27T09:56:50.255997
89 | tool | L0 | SQL-NL | SQL — NL: LAC compliance per activity | sra_sql_agent | SQL — NL: LAC compliance per activity | {'question': 'Show LAC compliance per activity', 'project_key': '101'} | WARN | Expected keywords missing: ['Task'] | 0.14 |  | ## ⚠️ Query Syntax Issue The database reported a syntax or access error: > column "activity_code" does not exist HINT: Perhaps you meant to reference the column "tbl_02_project_activity.Activity_Code". **Query attempted:** ```sql SELECT Activity_Code, Activity_Description, Domain_Code, Activity_Status, Planned_Progress_Pct, Actual_Progress_Pct, Forecast_Delay_Days, Total_Float_Days, Activity_Health_RAG FROM tbl_02_project_activity WHERE Project_Key = 101 ORDER BY Forecast_Delay_Days DESC NULLS LAST LIMIT 500 ``` Please review the column names and table references. Column names follow the `PascalCase_With_Underscores` convention. |  | 2026-02-27T09:56:50.398189
90 | tool | L0 | SQL-NL | SQL — NL: Critical activities (CP focus) | sra_sql_agent | SQL — NL: Critical activities (CP focus) | {'question': 'Which activities are on the critical path', 'project_key': '101'} | WARN | Expected keywords missing: ['Task'] | 0.08 |  | ## ⚠️ Query Syntax Issue The database reported a syntax or access error: > column "activity_code" does not exist HINT: Perhaps you meant to reference the column "tbl_02_project_activity.Activity_Code". **Query attempted:** ```sql SELECT Activity_Code, Activity_Description, Domain_Code, Activity_Status, Planned_Progress_Pct, Actual_Progress_Pct, Forecast_Delay_Days, Total_Float_Days, Activity_Health_RAG FROM tbl_02_project_activity WHERE Project_Key = 101 ORDER BY Forecast_Delay_Days DESC NULLS LAST LIMIT 500 ``` Please review the column names and table references. Column names follow the `PascalCase_With_Underscores` convention. |  | 2026-02-27T09:56:50.476819
91 | tool | L0 | SQL-NL | SQL — NL: Procurement at-risk activities | sra_sql_agent | SQL — NL: Procurement at-risk activities | {'question': 'Procurement activities with overdue rules', 'project_key': '101'} | WARN | Expected keywords missing: ['Task'] | 0.1 |  | ## ⚠️ Query Syntax Issue The database reported a syntax or access error: > column "activity_code" does not exist HINT: Perhaps you meant to reference the column "tbl_02_project_activity.Activity_Code". **Query attempted:** ```sql SELECT Activity_Code, Activity_Description, Domain_Code, Activity_Status, Planned_Progress_Pct, Actual_Progress_Pct, Forecast_Delay_Days, Total_Float_Days, Activity_Health_RAG FROM tbl_02_project_activity WHERE Project_Key = 101 ORDER BY Forecast_Delay_Days DESC NULLS LAST LIMIT 500 ``` Please review the column names and table references. Column names follow the `PascalCase_With_Underscores` convention. |  | 2026-02-27T09:56:50.579407
92 | tool | L0 | SQL-NL | SQL — NL: EOT exposure per project | sra_sql_agent | SQL — NL: EOT exposure per project | {'question': 'EOT exposure and contractual buffer for the project', 'project_key': '101'} | WARN | Expected keywords missing: ['Activity', 'Task'] | 0.08 |  | ## ⚠️ Query Syntax Issue The database reported a syntax or access error: > column "project_key" does not exist HINT: Perhaps you meant to reference the column "tbl_01_project_summary.Project_Key". **Query attempted:** ```sql SELECT Project_Key, Project_Name, Project_Location, SPI_Overall, Project_Execution_Index, Max_Forecast_Delay_Days_Overall, EOT_Exposure_Days, Schedule_Health_RAG, Schedule_Health_Score, Data_Freshness_Label FROM tbl_01_project_summary WHERE Project_Key = 101 ORDER BY Max_Forecast_Delay_Days_Overall DESC NULLS LAST LIMIT 500 ``` Please review the column names and table references. Column names follow the `PascalCase_With_Underscores` convention. |  | 2026-02-27T09:56:50.656085
93 | tool | L0 | SQL-NL | SQL — NL: Baseline drift activities | sra_sql_agent | SQL — NL: Baseline drift activities | {'question': 'Activities with baseline drift and slip', 'project_key': '101'} | WARN | Expected keywords missing: ['Task'] | 0.08 |  | ## ⚠️ Query Syntax Issue The database reported a syntax or access error: > column "activity_code" does not exist HINT: Perhaps you meant to reference the column "tbl_02_project_activity.Activity_Code". **Query attempted:** ```sql SELECT Activity_Code, Activity_Description, Domain_Code, Activity_Status, Planned_Progress_Pct, Actual_Progress_Pct, Forecast_Delay_Days, Total_Float_Days, Activity_Health_RAG FROM tbl_02_project_activity WHERE Project_Key = 101 ORDER BY Forecast_Delay_Days DESC NULLS LAST LIMIT 500 ``` Please review the column names and table references. Column names follow the `PascalCase_With_Underscores` convention. |  | 2026-02-27T09:56:50.736180
94 | tool | L0 | SQL-NL | SQL — NL: Portfolio view (no project filter) | sra_sql_agent | SQL — NL: Portfolio view (no project filter) | {'question': 'Show all projects with health score and SPI overall'} | WARN | Expected keywords missing: ['Activity', 'Task'] | 0.08 |  | ## ⚠️ Query Syntax Issue The database reported a syntax or access error: > column "project_key" does not exist HINT: Perhaps you meant to reference the column "tbl_01_project_summary.Project_Key". **Query attempted:** ```sql SELECT Project_Key, Project_Name, Project_Location, SPI_Overall, Project_Execution_Index, Max_Forecast_Delay_Days_Overall, EOT_Exposure_Days, Schedule_Health_RAG, Schedule_Health_Score, Data_Freshness_Label FROM tbl_01_project_summary ORDER BY Max_Forecast_Delay_Days_Overall DESC NULLS LAST LIMIT 500 ``` Please review the column names and table references. Column names follow the `PascalCase_With_Underscores` convention. |  | 2026-02-27T09:56:50.815211
95 | tool | L0 | SQL-RAW | SQL RAW — Project summary: key health KPIs | sra_sql_agent | SQL RAW — Project summary: key health KPIs | {'question': 'Raw SQL: project KPIs', 'project_key': '101', 'raw_sql': 'SELECT "Project_Key", "Project_Name", "Project_Location", "SPI_Overall", "Project_Execution_Index", "Max_Forecast_Delay_Days_Overall", "EOT_Exposure_Days", "Schedule_Health_RAG", "Schedule_Health_Score", "Weakest_Domain", "Data_Freshness_Label" FROM public.tbl_01_project_summary WHERE "Project_Key" = 101 ORDER BY "Max_Forecast_Delay_Days_Overall" DESC NULLS LAST LIMIT 10'} | WARN | Expected keywords missing: ['Activity', 'Task'] | 0.09 |  | ## 📊 Ad-Hoc Schedule Query Results *Question: Raw SQL: project KPIs* *Scope: Project 101* *Rows returned: 1* --- ¦ Project_Key ¦ Project_Name ¦ Project_Location ¦ SPI_Overall ¦ Project_Execution_Index ¦ Max_Forecast_Delay_Days_Overall ¦ EOT_Exposure_Days ¦ Schedule_Health_RAG ¦ Schedule_Health_Score ¦ Weakest_Domain ¦ Data_Freshness_Label ¦ ¦-------------¦--------------¦------------------¦-------------¦-------------------------¦---------------------------------¦-------------------¦---------------------¦-----------------------¦----------------¦----------------------¦ ¦ 101 ¦ Mega PWS in 11 block of Ganjam District ¦ Ganjam, Odisha. ¦ 0.228 ¦ 1.60551 ¦ 463 ¦ 463 ¦ Red ¦ 15 ¦ Construction ¦ Recent ? Within Week ¦ --- <details><summary>📋 SQL Executed</summary> ```sql SELECT "Project_Key", "Project_Name", "Project_Location", "SPI_Overall", "Project_Execution_Index", "Max_Forecast_Delay_Days_Overall", "EOT_Exposure_Days", "Schedule_Health_RAG", "Schedule_Health_Score", "Weakest_Domain", "Data_Freshness_Label" FROM public.tbl_01_project_summary WHERE "Project_Key" = 101 ORDER BY "Max_Forecast_Delay_Days_Overall" DESC NULLS LAST LIMIT 10 ``` </details> --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:50.901962
96 | tool | L0 | SQL-RAW | SQL RAW — Top 10 delayed activities with CP flag | sra_sql_agent | SQL RAW — Top 10 delayed activities with CP flag | {'question': 'Raw SQL: top delayed activities', 'project_key': '101', 'raw_sql': 'SELECT "Activity_Code", "Activity_Description", "Domain_Code", "Activity_Status", "Forecast_Delay_Days", "Slip_Days", "Is_Critical_Wrench", "Delay_Magnitude_Label", "Delay_Source_Label", "Compound_Risk_Score" FROM public.tbl_02_project_activity WHERE "Project_Key" = 101 AND "Forecast_Delay_Days" > 0 ORDER BY "Forecast_Delay_Days" DESC LIMIT 10'} | WARN | Expected keywords missing: ['Task'] | 0.1 |  | ## 📊 Ad-Hoc Schedule Query Results *Question: Raw SQL: top delayed activities* *Scope: Project 101* *Rows returned: 0* --- The query returned no records matching the specified criteria. --- <details><summary>📋 SQL Executed</summary> ```sql SELECT "Activity_Code", "Activity_Description", "Domain_Code", "Activity_Status", "Forecast_Delay_Days", "Slip_Days", "Is_Critical_Wrench", "Delay_Magnitude_Label", "Delay_Source_Label", "Compound_Risk_Score" FROM public.tbl_02_project_activity WHERE "Project_Key" = 101 AND "Forecast_Delay_Days" > 0 ORDER BY "Forecast_Delay_Days" DESC LIMIT 10 ``` </details> --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:51.004830
97 | tool | L0 | SQL-RAW | SQL RAW — Tasks near-critical (float ≤ 5d) | sra_sql_agent | SQL RAW — Tasks near-critical (float ≤ 5d) | {'question': 'Raw SQL: near-critical tasks', 'project_key': '101', 'raw_sql': 'SELECT "Task_Key", "Task_Name", "Activity_Code", "Domain_Code", "Total_Float_Days", "Float_Health_Status", "Float_RAG_Label", "Is_Critical_Wrench", "Forecast_Delay_Days", "Task_Health_RAG" FROM public.tbl_03_project_task WHERE "Project_Key" = 101 AND "Total_Float_Days" >= 0 AND "Total_Float_Days" <= 5 ORDER BY "Total_Float_Days" ASC LIMIT 20'} | PASS | All expected content present | 0.09 |  | ## 📊 Ad-Hoc Schedule Query Results *Question: Raw SQL: near-critical tasks* *Scope: Project 101* *Rows returned: 0* --- The query returned no records matching the specified criteria. --- <details><summary>📋 SQL Executed</summary> ```sql SELECT "Task_Key", "Task_Name", "Activity_Code", "Domain_Code", "Total_Float_Days", "Float_Health_Status", "Float_RAG_Label", "Is_Critical_Wrench", "Forecast_Delay_Days", "Task_Health_RAG" FROM public.tbl_03_project_task WHERE "Project_Key" = 101 AND "Total_Float_Days" >= 0 AND "Total_Float_Days" <= 5 ORDER BY "Total_Float_Days" ASC LIMIT 20 ``` </details> --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:51.092300
98 | tool | L0 | SQL-RAW | SQL RAW — Milestones forecast vs baseline | sra_sql_agent | SQL RAW — Milestones forecast vs baseline | {'question': 'Raw SQL: milestones', 'project_key': '101', 'raw_sql': 'SELECT "Task_Key", "Task_Name", "Activity_Code", "Domain_Code", "Baseline_Finish_Date", "Forecast_Finish_Date", "Milestone_Status_Label", "Slip_Days" FROM public.tbl_03_project_task WHERE "Project_Key" = 101 AND "Is_Milestone" = TRUE ORDER BY "Forecast_Finish_Date" ASC LIMIT 20'} | PASS | All expected content present | 0.14 |  | ## 📊 Ad-Hoc Schedule Query Results *Question: Raw SQL: milestones* *Scope: Project 101* *Rows returned: 0* --- The query returned no records matching the specified criteria. --- <details><summary>📋 SQL Executed</summary> ```sql SELECT "Task_Key", "Task_Name", "Activity_Code", "Domain_Code", "Baseline_Finish_Date", "Forecast_Finish_Date", "Milestone_Status_Label", "Slip_Days" FROM public.tbl_03_project_task WHERE "Project_Key" = 101 AND "Is_Milestone" = TRUE ORDER BY "Forecast_Finish_Date" ASC LIMIT 20 ``` </details> --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:51.233980
99 | tool | L0 | SQL-RAW | SQL RAW — Procurement rule summary per activity | sra_sql_agent | SQL RAW — Procurement rule summary per activity | {'question': 'Raw SQL: procurement rules', 'project_key': '101', 'raw_sql': 'SELECT "Activity_Code", "Activity_Description", "Domain_Code", "PRC_Total_Rules", "PRC_Completed_Rules", "PRC_Overdue_Rules", "PRC_At_Risk_Rules_7Day", "PRC_At_Risk_Rules_30Day", "PRC_LAC_Week_Pct", "PRC_LAC_RAG" FROM public.tbl_02_project_activity WHERE "Project_Key" = 101 AND "PRC_Total_Rules" > 0 ORDER BY "PRC_Overdue_Rules" DESC LIMIT 15'} | WARN | Expected keywords missing: ['Task'] | 0.14 |  | ## 📊 Ad-Hoc Schedule Query Results *Question: Raw SQL: procurement rules* *Scope: Project 101* *Rows returned: 5* --- ¦ Activity_Code ¦ Activity_Description ¦ Domain_Code ¦ PRC_Total_Rules ¦ PRC_Completed_Rules ¦ PRC_Overdue_Rules ¦ PRC_At_Risk_Rules_7Day ¦ PRC_At_Risk_Rules_30Day ¦ PRC_LAC_Week_Pct ¦ PRC_LAC_RAG ¦ ¦---------------¦----------------------¦-------------¦-----------------¦---------------------¦-------------------¦------------------------¦-------------------------¦------------------¦-------------¦ ¦ Dispatch ¦ Dispatch ¦ PRC ¦ 1 ¦ 0 ¦ 1 ¦ 0 ¦ 0 ¦ 0 ¦ Red ¦ ¦ — ¦ — ¦ PRC ¦ 1 ¦ 0 ¦ 1 ¦ 0 ¦ 0 ¦ 0 ¦ Red ¦ ¦ INS ¦ Inspection ¦ PRC ¦ 1 ¦ 0 ¦ 1 ¦ 0 ¦ 0 ¦ 0 ¦ Red ¦ ¦ MFC ¦ Manufacturing Clearence ¦ PRC ¦ 1 ¦ 0 ¦ 1 ¦ 0 ¦ 0 ¦ 0 ¦ Red ¦ ¦ PO ¦ Purchase Order ¦ PRC ¦ 1 ¦ 0 ¦ 1 ¦ 0 ¦ 0 ¦ 0 ¦ Red ¦ --- <details><summary>📋 SQL Executed</summary> ```sql SELECT "Activity_Code", "Activity_Description", "Domain_Code", "PRC_Total_Rules", "PRC_Completed_Rules", "PRC_Overdue_Rules", "PRC_At_Risk_Rules_7Day", "PRC_At_Risk_Rules_30Day", "PRC_LAC_Week_Pct", "PRC_LAC_RAG" FROM public.tbl_02_project_activity WHERE "Project_Key" = 101 AND "PRC_Total_Rules" > 0 ORDER BY "PRC_Overdue_Rules" DESC LIMIT 15 ``` </details> --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:51.372834
100 | tool | L0 | SQL-RAW | SQL RAW — Construction LAC per activity | sra_sql_agent | SQL RAW — Construction LAC per activity | {'question': 'Raw SQL: construction LAC', 'project_key': '101', 'raw_sql': 'SELECT "Activity_Code", "Activity_Description", "Domain_Code", "CON_Total_Rules", "CON_Completed_Rules", "CON_Overdue_Rules", "CON_At_Risk_Rules_7Day", "CON_LAC_Week_Pct", "CON_LAC_Month_Pct", "CON_LAC_RAG" FROM public.tbl_02_project_activity WHERE "Project_Key" = 101 AND "CON_Total_Rules" > 0 ORDER BY "CON_LAC_Week_Pct" ASC LIMIT 15'} | WARN | Expected keywords missing: ['Task'] | 0.08 |  | ## 📊 Ad-Hoc Schedule Query Results *Question: Raw SQL: construction LAC* *Scope: Project 101* *Rows returned: 15* --- ¦ Activity_Code ¦ Activity_Description ¦ Domain_Code ¦ CON_Total_Rules ¦ CON_Completed_Rules ¦ CON_Overdue_Rules ¦ CON_At_Risk_Rules_7Day ¦ CON_LAC_Week_Pct ¦ CON_LAC_Month_Pct ¦ CON_LAC_RAG ¦ ¦---------------¦----------------------¦-------------¦-----------------¦---------------------¦-------------------¦------------------------¦------------------¦-------------------¦-------------¦ ¦ PCC ¦ PCC ¦ CON ¦ 1 ¦ 0 ¦ 1 ¦ 1 ¦ 0 ¦ 0 ¦ Red ¦ ¦ Shuttering ¦ Shuttering ¦ CON ¦ 1 ¦ 0 ¦ 1 ¦ 1 ¦ 0 ¦ 0 ¦ Red ¦ ¦ PCC ¦ PCC ¦ CON ¦ 1 ¦ 0 ¦ 1 ¦ 1 ¦ 0 ¦ 0 ¦ Red ¦ ¦ Reinforcement ¦ Reinforcement ¦ CON ¦ 1 ¦ 0 ¦ 1 ¦ 1 ¦ 0 ¦ 0 ¦ Red ¦ ¦ Reinforcement ¦ Reinforcement ¦ CON ¦ 1 ¦ 0 ¦ 1 ¦ 1 ¦ 0 ¦ 0 ¦ Red ¦ ¦ Shuttering ¦ Shuttering ¦ CON ¦ 1 ¦ 0 ¦ 1 ¦ 1 ¦ 0 ¦ 0 ¦ Red ¦ ¦ RCC ¦ RCC ¦ CON ¦ 1 ¦ 0 ¦ 1 ¦ 1 ¦ 0 ¦ 0 ¦ Red ¦ ¦ Shuttering ¦ Shuttering ¦ CON ¦ 1 ¦ 0 ¦ 1 ¦ 1 ¦ 0 ¦ 0 ¦ Red ¦ ¦ Commissioning ¦ Commissioning ¦ CON ¦ 1 ¦ 0 ¦ 1 ¦ 1 ¦ 0 ¦ 0 ¦ Red ¦ ¦ PCC ¦ PCC ¦ CON ¦ 1 ¦ 0 ¦ 1 ¦ 1 ¦ 0 ¦ 0 ¦ Red ¦ ¦ RCC ¦ RCC ¦ CON ¦ 1 ¦ 0 ¦ 1 ¦ 1 ¦ 0 ¦ 0 ¦ Red ¦ ¦ Road Cutting (Cum) ¦ Road Cutting (Cum) ¦ CON ¦ 1 ¦ 0 ¦ 1 ¦ 1 ¦ 0 ¦ 0 ¦ Red ¦ ¦ Reinforcement ¦ Reinforcement ¦ CON ¦ 1 ¦ 0 ¦ 1 ¦ 1 ¦ 0 ¦ 0 ¦ Red ¦ ¦ Plastering ¦ Plastering ¦ CON ¦ 1 ¦ 0 ¦ 1 ¦ 1 ¦ 0 ¦ 0 ¦ Red ¦ ¦ — ¦ — ¦ CON ¦ 1 ¦ 0 ¦ 1 ¦ 1 ¦ 0 ¦ 0 ¦ Red ¦ --- <details><summary>📋 SQL Executed</summary> ```sql SELECT "Activity_Code", "Activity_Description", "Domain_Code", "CON_Total_Rules", "CON_Completed_Rules", "CON_Overdue_Rules", "CON_At_Risk_Rules_7Day", "CON_LAC_Week_Pct", "CON_LAC_Month_Pct", "CON_LAC_RAG" FROM public.tbl_02_project_activity WHERE "Project_Key" = 101 AND "CON_Total_Rules" > 0 ORDER BY "CON_LAC_Week_Pct" ASC LIMIT 15 ``` </details> --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:51.448901
101 | tool | L0 | SQL-RAW | SQL RAW — Recovery candidates (crash + fast-track) | sra_sql_agent | SQL RAW — Recovery candidates (crash + fast-track) | {'question': 'Raw SQL: recovery candidates', 'project_key': '101', 'raw_sql': 'SELECT "Task_Key", "Task_Name", "Activity_Code", "Domain_Code", "Crash_Candidate_Flag", "FastTrack_Candidate_Flag", "Task_Acceleration_Days", "Task_Recovery_SPI_Required", "Recovery_Feasibility_Label", "Task_Health_RAG" FROM public.tbl_03_project_task WHERE "Project_Key" = 101 AND ("Crash_Candidate_Flag" = TRUE OR "FastTrack_Candidate_Flag" = TRUE) ORDER BY "Task_Acceleration_Days" DESC NULLS LAST LIMIT 15'} | PASS | All expected content present | 0.09 |  | ## 📊 Ad-Hoc Schedule Query Results *Question: Raw SQL: recovery candidates* *Scope: Project 101* *Rows returned: 15* --- ¦ Task_Key ¦ Task_Name ¦ Activity_Code ¦ Domain_Code ¦ Crash_Candidate_Flag ¦ FastTrack_Candidate_Flag ¦ Task_Acceleration_Days ¦ Task_Recovery_SPI_Required ¦ Recovery_Feasibility_Label ¦ Task_Health_RAG ¦ ¦----------¦-----------¦---------------¦-------------¦----------------------¦--------------------------¦------------------------¦----------------------------¦----------------------------¦-----------------¦ ¦ 10184992 ¦ Detailed scheme report (DSR) ¦ — ¦ ENG ¦ True ¦ False ¦ 926 ¦ — ¦ Recovery Unlikely Without Resequencing ¦ Amber ¦ ¦ 10185106 ¦ Detailed scheme report (DSR) ¦ — ¦ ENG ¦ True ¦ False ¦ 923 ¦ — ¦ Recovery Unlikely Without Resequencing ¦ Amber ¦ ¦ 1014069 ¦ Numeration and RC Detail of Switchyard at IBPS-1 for Scheme-2 ¦ — ¦ ENG ¦ True ¦ False ¦ 882 ¦ — ¦ Recovery Unlikely Without Resequencing ¦ Red ¦ ¦ 1012985 ¦ Approach Channel ¦ — ¦ ENG ¦ True ¦ False ¦ 875 ¦ — ¦ Recovery Unlikely Without Resequencing ¦ Red ¦ ¦ 10134111 ¦ Design Calculation of ESR of 125KL Capacity 14m Staging height at Baragaom for Scheme-I ¦ — ¦ ENG ¦ True ¦ False ¦ 870 ¦ — ¦ Recovery Unlikely Without Resequencing ¦ Red ¦ ¦ 10126411 ¦ Inspection ¦ INS ¦ PRC ¦ True ¦ False ¦ 869 ¦ — ¦ Recovery Unlikely Without Resequencing ¦ Red ¦ ¦ 10126410 ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ True ¦ False ¦ 869 ¦ — ¦ Recovery Unlikely Without Resequencing ¦ Red ¦ ¦ 10126409 ¦ MFC ¦ MFC ¦ PRC ¦ True ¦ False ¦ 869 ¦ — ¦ Recovery Unlikely Without Resequencing ¦ Red ¦ ¦ 10126408 ¦ Post Order & QAP Approval ¦ — ¦ PRC ¦ True ¦ False ¦ 869 ¦ — ¦ Recovery Unlikely Without Resequencing ¦ Red ¦ ¦ 1013598 ¦ Cable Design Memorandum and Typical Voltage Drop & Cable Design Calculationsfor Intake, WTP ¦ — ¦ ENG ¦ True ¦ False ¦ 865 ¦ — ¦ Recovery Unlikely Without Resequencing ¦ Red ¦ ¦ 1012371 ¦ L Section for Clear Water Pumping Main from IBPS 11 (PM-2) to OHT-(Ganjam Scheme-1) ¦ — ¦ ENG ¦ True ¦ False ¦ 863 ¦ — ¦ Recovery Unlikely Without Resequencing ¦ Red ¦ ¦ 1014048 ¦ Architectural Detail of Clear Water Pump House for Scheme-2 ¦ — ¦ ENG ¦ True ¦ False ¦ 860 ¦ — ¦ Recovery Unlikely Without Resequencing ¦ Red ¦ ¦ 1012388 ¦ Surge Analysis Report for Clear water Pumping main from IBPS-11 (PM-1) to OHTs Ganjam WSS (Scheme-1) ¦ — ¦ ENG ¦ True ¦ False ¦ 852 ¦ — ¦ Recovery Unlikely Without Resequencing ¦ Red ¦ ¦ 1014137 ¦ Numeration and RC Detail of Valve Chambers for Scheme-2 ¦ — ¦ ENG ¦ True ¦ False ¦ 851 ¦ — ¦ Recovery Unlikely Without Resequencing ¦ Red ¦ ¦ 1014134 ¦ Numeration and RC Detail of Valve Chambers for Scheme-2 ¦ — ¦ ENG ¦ True ¦ False ¦ 851 ¦ — ¦ Recovery Unlikely Without Resequencing ¦ Red ¦ --- <details><summary>📋 SQL Executed</summary> ```sql SELECT "Task_Key", "Task_Name", "Activity_Code", "Domain_Code", "Crash_Candidate_Flag", "FastTrack_Candidate_Flag", "Task_Acceleration_Days", "Task_Recovery_SPI_Required", "Recovery_Feasibility_Label", "Task_Health_RAG" FROM public.tbl_03_project_task WHERE "Project_Key" = 101 AND ("Crash_Candidate_Flag" = TRUE OR "FastTrack_Candidate_Flag" = TRUE) ORDER BY "Task_Acceleration_Days" DESC NULLS LAST LIMIT 15 ``` </details> --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:51.537933
102 | tool | L0 | SQL-RAW | SQL RAW — As-built vs baseline (completed tasks) | sra_sql_agent | SQL RAW — As-built vs baseline (completed tasks) | {'question': 'Raw SQL: as-built variance', 'project_key': '101', 'raw_sql': 'SELECT "Task_Key", "Task_Name", "Activity_Code", "Domain_Code", "Baseline_Duration_Days", "As_Built_Duration_Days", "Duration_Variance_Days", "Task_Status", "Actual_Finish_Date" FROM public.tbl_03_project_task WHERE "Project_Key" = 101 AND "Task_Status" = \'Complete\' AND "As_Built_Duration_Days" IS NOT NULL ORDER BY "Duration_Variance_Days" DESC NULLS LAST LIMIT 15'} | PASS | All expected content present | 0.09 |  | ## 📊 Ad-Hoc Schedule Query Results *Question: Raw SQL: as-built variance* *Scope: Project 101* *Rows returned: 15* --- ¦ Task_Key ¦ Task_Name ¦ Activity_Code ¦ Domain_Code ¦ Baseline_Duration_Days ¦ As_Built_Duration_Days ¦ Duration_Variance_Days ¦ Task_Status ¦ Actual_Finish_Date ¦ ¦----------¦-----------¦---------------¦-------------¦------------------------¦------------------------¦------------------------¦-------------¦--------------------¦ ¦ 10134120 ¦ Numeration and RC Detail of ESR of 500KL Capacity 12m Staging height at Chandipalli for Scheme-II ¦ — ¦ ENG ¦ 46 ¦ 742 ¦ 696 ¦ Complete ¦ 14 Feb 1970 ¦ ¦ 10134121 ¦ Numeration and RC Detail of ESR of 500KL Capacity 12m Staging height at Chandipalli for Scheme-II ¦ — ¦ ENG ¦ 46 ¦ 742 ¦ 696 ¦ Complete ¦ 14 Feb 1970 ¦ ¦ 10134119 ¦ Design Calculation of ESR of 500KL Capacity 12m Staging height at Chandipalli for Scheme-II ¦ — ¦ ENG ¦ 46 ¦ 742 ¦ 696 ¦ Complete ¦ 14 Feb 1970 ¦ ¦ 10134122 ¦ Numeration and RC Detail of ESR of 500KL Capacity 12m Staging height at Chandipalli for Scheme-II ¦ — ¦ ENG ¦ 46 ¦ 742 ¦ 696 ¦ Complete ¦ 13 Feb 1970 ¦ ¦ 1012938 ¦ Scheme diagram for Gravity Distribution main from OHT-261 HUKUMA-EX (SORODA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 46 ¦ 732 ¦ 686 ¦ Complete ¦ 28 Jan 1970 ¦ ¦ 1012937 ¦ Hydraulics Design for Gravity Distribution main from OHT-261 HUKUMA-EX (SORODA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 46 ¦ 732 ¦ 686 ¦ Complete ¦ 28 Jan 1970 ¦ ¦ 1012966 ¦ Scheme diagram for Gravity Distribution main from OHT-275 GOUDAGOTHA-EX (SORODA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 45 ¦ 687 ¦ 642 ¦ Complete ¦ 02 Feb 1970 ¦ ¦ 1012965 ¦ Hydraulics Design for Gravity Distribution main from OHT-275 GOUDAGOTHA-EX (SORODA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 45 ¦ 687 ¦ 642 ¦ Complete ¦ 03 Feb 1970 ¦ ¦ 1012446 ¦ Scheme diagram for Gravity Distribution main from OHT-15 ATHAGADAPATNA-PR (KS NAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 45 ¦ 656 ¦ 611 ¦ Complete ¦ 28 Jan 1970 ¦ ¦ 1012445 ¦ Hydraulics Design for Gravity Distribution main from OHT-15 ATHAGADAPATNA-PR (KS NAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 45 ¦ 656 ¦ 611 ¦ Complete ¦ 28 Jan 1970 ¦ ¦ 1012903 ¦ Hydraulics Design for Gravity Distribution main from OHT-244 KHURA-PR (POLASARA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 46 ¦ 648 ¦ 602 ¦ Complete ¦ 28 Jan 1970 ¦ ¦ 1012904 ¦ Scheme diagram for Gravity Distribution main from OHT-244 KHURA-PR (POLASARA) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 46 ¦ 648 ¦ 602 ¦ Complete ¦ 28 Jan 1970 ¦ ¦ 1012290 ¦ Surge Analysis Report for Raw water pumping main from Intake well to RW-IBPS - (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 45 ¦ 618 ¦ 573 ¦ Complete ¦ 27 Feb 1970 ¦ ¦ 10852992 ¦ Scheme diagram for Gravity Distribution main from OHT-296 ATHAGADAPATNA-EX GLSR (KS NAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 46 ¦ 609 ¦ 563 ¦ Complete ¦ 29 Jan 1970 ¦ ¦ 10852991 ¦ Hydraulics Design for Gravity Distribution main from OHT-296 ATHAGADAPATNA-EX GLSR (KS NAGAR) to Village (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 46 ¦ 609 ¦ 563 ¦ Complete ¦ 29 Jan 1970 ¦ --- <details><summary>📋 SQL Executed</summary> ```sql SELECT "Task_Key", "Task_Name", "Activity_Code", "Domain_Code", "Baseline_Duration_Days", "As_Built_Duration_Days", "Duration_Variance_Days", "Task_Status", "Actual_Finish_Date" FROM public.tbl_03_project_task WHERE "Project_Key" = 101 AND "Task_Status" = 'Complete' AND "As_Built_Duration_Days" IS NOT NULL ORDER BY "Duration_Variance_Days" DESC NULLS LAST LIMIT 15 ``` </details> --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:51.631747
103 | tool | L0 | SQL-RAW | SQL RAW — Workfront block flag tasks in 2W window | sra_sql_agent | SQL RAW — Workfront block flag tasks in 2W window | {'question': 'Raw SQL: blocked tasks in 2W window', 'project_key': '101', 'raw_sql': 'SELECT "Task_Key", "Task_Name", "Activity_Code", "Domain_Code", "Forecast_Start_Date", "Forecast_Finish_Date", "Workfront_Block_Flag", "Is_WorkFront_Available", "Total_Float_Days", "LookAhead_Priority_Score" FROM public.tbl_03_project_task WHERE "Project_Key" = 101 AND "In_2W_Start_Window" IS NOT NULL ORDER BY "LookAhead_Priority_Score" DESC NULLS LAST LIMIT 20'} | PASS | All expected content present | 0.1 |  | ## 📊 Ad-Hoc Schedule Query Results *Question: Raw SQL: blocked tasks in 2W window* *Scope: Project 101* *Rows returned: 20* --- ¦ Task_Key ¦ Task_Name ¦ Activity_Code ¦ Domain_Code ¦ Forecast_Start_Date ¦ Forecast_Finish_Date ¦ Workfront_Block_Flag ¦ Is_WorkFront_Available ¦ Total_Float_Days ¦ LookAhead_Priority_Score ¦ ¦----------¦-----------¦---------------¦-------------¦---------------------¦----------------------¦----------------------¦------------------------¦------------------¦--------------------------¦ ¦ 10184851 ¦ PR ¦ PR ¦ PRC ¦ 22 Jan 1970 ¦ 22 Jan 1970 ¦ False ¦ False ¦ — ¦ 40 ¦ ¦ 10185379 ¦ MRN ¦ MRN ¦ PRC ¦ 16 Jan 1970 ¦ 19 Jan 1970 ¦ False ¦ False ¦ — ¦ 40 ¦ ¦ 10115574 ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 08 Feb 1970 ¦ 17 Feb 1970 ¦ False ¦ — ¦ — ¦ 40 ¦ ¦ 10115555 ¦ MRN ¦ MRN ¦ PRC ¦ 27 Feb 1970 ¦ 09 Jan 1970 ¦ False ¦ False ¦ — ¦ 40 ¦ ¦ 10184799 ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 16 Jan 1970 ¦ 14 Jan 1970 ¦ False ¦ False ¦ — ¦ 40 ¦ ¦ 10184873 ¦ PO ¦ PO ¦ PRC ¦ 16 Jan 1970 ¦ 05 Feb 1970 ¦ False ¦ False ¦ — ¦ 40 ¦ ¦ 1013115 ¦ P&ID Drawing for CWR cum Pump House at IBPS-1- (Ganjam Scheme-1) ¦ — ¦ ENG ¦ 11 Jan 1970 ¦ 22 Jan 1970 ¦ False ¦ — ¦ — ¦ 40 ¦ ¦ 10115441 ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 16 Jan 1970 ¦ 19 Jan 1970 ¦ False ¦ False ¦ — ¦ 40 ¦ ¦ 1013782 ¦ Instrument list for IBPS-5 ¦ — ¦ ENG ¦ 24 Jan 1970 ¦ 22 Jan 1970 ¦ False ¦ — ¦ — ¦ 40 ¦ ¦ 1014165 ¦ Lighting Layout for Intake ¦ — ¦ ENG ¦ 20 Jan 1970 ¦ 22 Jan 1970 ¦ False ¦ — ¦ — ¦ 40 ¦ ¦ 10184883 ¦ Dispatch Clearance ¦ Dispatch ¦ PRC ¦ 16 Jan 1970 ¦ 12 Feb 1970 ¦ False ¦ False ¦ — ¦ 40 ¦ ¦ 10184824 ¦ PO ¦ PO ¦ PRC ¦ 16 Jan 1970 ¦ 27 Feb 1970 ¦ False ¦ False ¦ — ¦ 40 ¦ ¦ 10115556 ¦ PR ¦ PR ¦ PRC ¦ 02 Mar 1970 ¦ 01 Mar 1970 ¦ False ¦ False ¦ — ¦ 40 ¦ ¦ 1013689 ¦ 33/11 kV Switchyard Layout for IBPS 1 ¦ — ¦ ENG ¦ 14 Jan 1970 ¦ 22 Jan 1970 ¦ False ¦ — ¦ — ¦ 40 ¦ ¦ 1013050 ¦ Architectural Detail of Chlorine Building for Scheme-1 ¦ — ¦ ENG ¦ 26 Feb 1970 ¦ 22 Jan 1970 ¦ False ¦ — ¦ — ¦ 40 ¦ ¦ 10184999 ¦ Numeration and RC Detail of Cascade aerator, Parshall flume, Distribution chamber and Flash mixer for Scheme-1 ¦ — ¦ ENG ¦ 01 Jan 1970 ¦ 22 Jan 1970 ¦ False ¦ — ¦ — ¦ 40 ¦ ¦ 1013740 ¦ Overall Single Line Diagram for IBPS 12 ¦ — ¦ ENG ¦ 14 Jan 1970 ¦ 22 Jan 1970 ¦ False ¦ — ¦ — ¦ 40 ¦ ¦ 10184910 ¦ MFC ¦ MFC ¦ PRC ¦ 16 Jan 1970 ¦ 26 Jan 1970 ¦ False ¦ False ¦ — ¦ 40 ¦ ¦ 1013102 ¦ Design Calculation of Intermediate Sump-1 for Scheme-1 ¦ — ¦ ENG ¦ 16 Feb 1970 ¦ 22 Jan 1970 ¦ False ¦ — ¦ — ¦ 40 ¦ ¦ 1012376 ¦ Surge Analysis Report for Clear water Pumping main from IBPS-09 (PM-2) to OHTs Ganjam WSS (Scheme-1) ¦ — ¦ ENG ¦ 30 Jan 1970 ¦ 22 Jan 1970 ¦ False ¦ False ¦ — ¦ 40 ¦ --- <details><summary>📋 SQL Executed</summary> ```sql SELECT "Task_Key", "Task_Name", "Activity_Code", "Domain_Code", "Forecast_Start_Date", "Forecast_Finish_Date", "Workfront_Block_Flag", "Is_WorkFront_Available", "Total_Float_Days", "LookAhead_Priority_Score" FROM public.tbl_03_project_task WHERE "Project_Key" = 101 AND "In_2W_Start_Window" IS NOT NULL ORDER BY "LookAhead_Priority_Score" DESC NULLS LAST LIMIT 20 ``` </details> --- 📌 **Reference Thresholds** │ SPI ≥ 1.0 │ PEI ≤ 1.0 │ Max Forecast Delay ≤ 30d │ Workfront Readiness ≥ 70.0% │ LAC ≥ 80.0% |  | 2026-02-27T09:56:51.736254
104 | tool | L0 | SQL-EDGE | SQL EDGE — Blocked: INSERT statement attempt | sra_sql_agent | SQL EDGE — Blocked: INSERT statement attempt | {'question': 'Security test: INSERT attempt', 'raw_sql': 'INSERT INTO tbl_01_project_summary VALUES (1)'} | WARN | Expected keywords missing: ['Project', 'Activity', 'Task'] | 0 |  | ## 🚫 Query Not Permitted The proposed SQL statement was not executed for the following reason: > Statement contains disallowed DML/DDL keywords. Only read-only `SELECT` statements are permitted. Please revise and resubmit. |  | 2026-02-27T09:56:51.737253
105 | tool | L0 | SQL-EDGE | SQL EDGE — Blocked: DELETE statement attempt | sra_sql_agent | SQL EDGE — Blocked: DELETE statement attempt | {'question': 'Security test: DELETE attempt', 'raw_sql': 'DELETE FROM tbl_01_project_summary WHERE 1=1'} | WARN | Expected keywords missing: ['Project', 'Activity', 'Task'] | 0 |  | ## 🚫 Query Not Permitted The proposed SQL statement was not executed for the following reason: > Statement contains disallowed DML/DDL keywords. Only read-only `SELECT` statements are permitted. Please revise and resubmit. |  | 2026-02-27T09:56:51.737253
106 | tool | L0 | SQL-EDGE | SQL EDGE — Blocked: DROP TABLE attempt | sra_sql_agent | SQL EDGE — Blocked: DROP TABLE attempt | {'question': 'Security test: DROP TABLE attempt', 'raw_sql': 'DROP TABLE tbl_03_project_task'} | WARN | Expected keywords missing: ['Project', 'Activity', 'Task'] | 0 |  | ## 🚫 Query Not Permitted The proposed SQL statement was not executed for the following reason: > Statement contains disallowed DML/DDL keywords. Only read-only `SELECT` statements are permitted. Please revise and resubmit. |  | 2026-02-27T09:56:51.738251
107 | tool | L0 | SQL-EDGE | SQL EDGE — Blocked: Multiple statements (semicolon) | sra_sql_agent | SQL EDGE — Blocked: Multiple statements (semicolon) | {'question': 'Security test: multiple statements', 'raw_sql': 'SELECT 1; DROP TABLE tbl_01_project_summary'} | WARN | Expected keywords missing: ['Project', 'Activity', 'Task'] | 0 |  | ## 🚫 Query Not Permitted The proposed SQL statement was not executed for the following reason: > Statement contains disallowed DML/DDL keywords. Only read-only `SELECT` statements are permitted. Please revise and resubmit. |  | 2026-02-27T09:56:51.739252
108 | tool | L0 | SQL-EDGE | SQL EDGE — Ambiguous question (should request clarification) | sra_sql_agent | SQL EDGE — Ambiguous question (should request clarification) | {'question': 'Show me everything', 'project_key': '101'} | PASS | All expected content present | 0 |  | ## 🔍 Ad-Hoc Query — Clarification Required The question **"Show me everything"** falls outside the coverage of the structured schedule intelligence tools, and could not be automatically translated into a targeted database query. To proceed, please provide one of the following: 1. **A more specific question** — include the grain (task/activity/project), domain (ENG/PRC/CON), and the specific metrics or conditions you need. 2. **A raw SQL SELECT** — pass it via the `raw_sql` parameter. ### Available Tables ¦ Table ¦ Grain ¦ Key Columns ¦ ¦-------¦-------¦-------------¦ ¦ `tbl_01_project_summary` ¦ One row per project ¦ Project_Key, SPI_Overall, PEI, EOT_Exposure_Days, Schedule_Health_RAG ¦ ¦ `tbl_02_project_activity` ¦ One row per activity ¦ Activity_Code, Domain_Code, Forecast_Delay_Days, Float_Days, LAC_Pct ¦ ¦ `tbl_03_project_task` ¦ One row per task ¦ Task_Key, Activity_Code, Float_Days, Is_Critical_Wrench, Task_Health_RAG ¦ 💡 *Example: "Show all Construction tasks in project 101 with negative float" or "List activities with CON_LAC_Week_Pct below 60% for project 101"* |  | 2026-02-27T09:56:51.739252
109 | tool | L0 | SQL-EDGE | SQL EDGE — No question, no SQL (empty inputs) | sra_sql_agent | SQL EDGE — No question, no SQL (empty inputs) | {'question': 'general question with no direction'} | PASS | All expected content present | 0 |  | ## 🔍 Ad-Hoc Query — Clarification Required The question **"general question with no direction"** falls outside the coverage of the structured schedule intelligence tools, and could not be automatically translated into a targeted database query. To proceed, please provide one of the following: 1. **A more specific question** — include the grain (task/activity/project), domain (ENG/PRC/CON), and the specific metrics or conditions you need. 2. **A raw SQL SELECT** — pass it via the `raw_sql` parameter. ### Available Tables ¦ Table ¦ Grain ¦ Key Columns ¦ ¦-------¦-------¦-------------¦ ¦ `tbl_01_project_summary` ¦ One row per project ¦ Project_Key, SPI_Overall, PEI, EOT_Exposure_Days, Schedule_Health_RAG ¦ ¦ `tbl_02_project_activity` ¦ One row per activity ¦ Activity_Code, Domain_Code, Forecast_Delay_Days, Float_Days, LAC_Pct ¦ ¦ `tbl_03_project_task` ¦ One row per task ¦ Task_Key, Activity_Code, Float_Days, Is_Critical_Wrench, Task_Health_RAG ¦ 💡 *Example: "Show all Construction tasks in project 101 with negative float" or "List activities with CON_LAC_Week_Pct below 60% for project 101"* |  | 2026-02-27T09:56:51.740251